## Slide 1: SESSION 2: GLOBAL BASELINE STRATEGY
Report Overall Status and Issues
G. Dyke

## Slide 2: Presentation Overview
CEOS GFOI Strategy Elements (a reminder)
Element 1 Status Summary
Milestones
Writing Team
Element 1 Strategy Structure
Major Issues to be Addressed
What Are We Missing?
Session 2 Overview

## Slide 3: CEOS GFOI Strategy Elements
Guiding document CEOS Plenary 2011 (Lucca)
  THE CEOS STRATEGY FOR SPACE DATA COVERAGE AND CONTINUITY IN SUPPORT OF THE GEO GLOBAL FOREST OBSERVATIONS INITIATIVE (GFOI) AND FOREST CARBON TRACKING (FCT) TASK
Element 1
  baseline, coordinated global data acquisition strategy involving a number of ‘core data streams’ that can be used free-of-charge for GFOI purposes
Element 2
  coordinated strategy for national data acquisitions
Element 3
  data supply in support of the FCT (R&D? session 4) activities

## Slide 4: Element 1 Status Summary
Very significant evolution in December-January
Significant revision to the document structure
  Much of the detailed content was removed to try and focus on the narrative
  “v26” latest
Framed around CEOS annual cycles
  Annual updates anticipated

## Slide 5: Milestones
Delivery of a complete element 1 global baseline strategy to SIT-28 is required
  In order not to miss one full year of the CEOS cycle
  In order to confirm support from CEOS agencies for 2013 implementation activities
  In order to develop element 2 in 2013
Expect that at SIT-29 (2014)
  Element 1 will be updated
  Element 2 will be ready for endorsement

## Slide 6: Writing Team
Core: Ake, John, Stephen, George
  Working at maximum capacity
  Good analysis support from SEO
Deadline for SIT-28 materials is 1 March
  15 working days post-SDCG-3
Additional contributors are needed in the next three weeks to succeed at SIT-28
  In particular review and contributions to agency-specific content

## Slide 7: Element 1 Strategy Structure
Governance (S.9)
Requirements (S.2)
Strategy
(S.3)
Approach
(S.4)
Gap Analysis
(S.5)
Implementation
(S.6-8, 2013, 2014, 2015+)
Does this work?

## Slide 8: Element 1 Strategy Structure
Requirements: Based on consultation
  UNFCCC/IPCC (informal), GOFC-GOLD, others
  Still not formal requirements
Strategy: Core data streams and roles, phases, dynamic
Approach: Baseline, Regional, Selective (element 2)
Gap Analysis: Roles for non-core data streams
Implementation: Acquisition requests for data providers 2013, 2014, 2015+

## Slide 9: 2013 Element 1 Strategy Summary
LS-7/LS-8 Global Coverage
What about clouds?
Assess impact of clouds (SEO)
Suggest Mitigations
LTAP Modifications
Pixel Mining
Wait for the cavalry
  Selective C-Band SAR
  CBERS/S-2 for revisit
  SAOCOM-1 for L-Band?
Does this work?
Element 2

## Slide 10: 2014 Element 1 Strategy Summary
+ Sentinel-1
+ CBERS-3
LS-7/LS-8 Global Coverage
What about clouds?
Assess impact of clouds (SEO)
Suggest Mitigations
LTAP Modifications
Pixel Mining
Wait for the cavalry
  Selective C-Band SAR
  CBERS/S-2 for revisit
  SAOCOM-1 for L-Band?
Does this work?
Element 2

## Slide 11: 2015+ Element 1 Strategy Summary
+ Sentinel-1
+ CBERS-3
+ RCM
+ Sentinel-2
+ SAOCOM?
LS-7/LS-8 Global Coverage
What about clouds?
Assess impact of clouds (SEO)
Suggest Mitigations
LTAP Modifications
Pixel Mining
Wait for the cavalry
  Selective C-Band SAR
  CBERS/S-2 for revisit
  SAOCOM-1 for L-Band?
Does this work?
Element 2

## Slide 12: Major Issues to be Addressed
Section 4.2 – 4.4 “Capacity Assessment” of each mission except Landsat is weak
  Both in terms of text and actual assessment
  Difficult to assess capacity of future missions without agency support
Section 5 “Gap Analysis” remains incomplete
  Needs a section where the gaps are highlighted?
Sections 6, 7, 8 – IMPLEMENTATION require significant review and confirmation by agencies
  With a particular focus on 2013 and 2014

## Slide 13: What Are We Missing?
References to high resolution verification data?
MODIS-derived deforestation mask?
  This is not data delivery to a country, but an important product to support the strategy
Anything else?

## Slide 14: Cloud Coverage Analysis
SEO has analyzed DRC and Guyana
  Are we happy with the methodology?
There is a short opportunity to update and expand the analysis before SIT-28 – what should the priority be?
  Expand the analysis to cover the 16 2013 countries
  Assess which of those countries might most require element 2 treatment
  Quarter scene analysis
  Demonstrate potential of pixel mining for one scene?

## Slide 15: SESSION 2 Overview
1h40m to discuss the global baseline strategy
30m: Basic requirements and data products
  Frank Martin
1h10m: Basic strategy and core data stream roles
  Stephen
(lunch)
Followed by session 3 on implementation

## Slide 16: SESSION 2 Objectives
Confirmation that we are happy with the structure of the element 1 strategy
Confirmation that we feel the element 1 strategy addresses all it needs to
Develop list of tasks for report delivery for discussion and assignment confirmation in Session 5 (tomorrow)

## Slide 17: Thanks!
Questions?
30m: Basic requirements and data products
  Frank Martin
1h10m: Basic strategy and core data stream roles
  Stephen