## Slide 1: CEOS Support to Disaster Risk Management (DRM) Status & Recommendations
CEOS Work Plan section 2.6
Ivan Petiteville, ESA
Notes: <number>

## Slide 2: Activities: Status & Next Steps
<number>
Achieved:
one-year activity initiated after go ahead from 2011 Plenary
ad hoc Team created with volunteers (ASI, CNES, CSA, DLR, ESA, EUMETSAT, JAXA, NASA, NOAA, USGS )
2 team meetings + 5 teleconferences
draft Report issued (July 2012) for internal review by ad hoc team
Next Steps for 2012:
first issue of the Report (SIT Workshop , Sep. 2012) , 2nd issue at CEOS Plenary (Oct. 2012) and final issue after Plenary (Dec. 2012)
dedicated session at 2012 CEOS plenary (Report presentation, Decision on follow-on activities / actions)
Issues:
no major issue related to the team work.
Notes: <number>

## Slide 3: Near Future Plan
<number>
Additional Expected Achievements by the end of 2012:
  Report to be updated for 2012 CEOS Plenary
  Participation to on-going consultations for preparation of 2015 World Conference on Disaster Risk Reduction
Contribution to 2012 Events (e.g., GEO-IX, COP-18/SBSTA-37):
  Activity to be reported in CEOS report to GEO-IX plenary
Information on any decisions that need to be made at CEOS Plenary:
  Plenary to endorse document with recommendations (see slide # 9 )
Notes: <number>

## Slide 4
Disaster Risk Reduction: Key Milestones
2015-2025
NEW
POST

## Slide 5: Actions: Principles
<number>
Ultimate Objective:
  Increase and strengthen the contribution of EO satellite to DRM through a series of coordinated enlarged actions
How ? …
Improve the coordination between EO satellites observations and take appropriate actions aiming at better distributing EO satellite data and fostering its use by the DRM users…
  to enable both the geospatial analysis and the production of higher-level added value products & information to support DRM users
If successful, it demonstrates space agencies’ capacity to provide EO data that can be transformed into high-value information
Facilitate the positioning of EO from Space in the 2015 post-Hyogo framework of actions …
  through the lobbying to the major stakeholders in charge of defining the 2015 post-Hyogo FA
Notes: <number>

## Slide 6: Actions: Challenges & Constraints
<number>
Find a few “big ideas” capable to attract CEOS Principals in order to get their approval at 2012 CEOS Plenary
  Actions based on users’ real needs but feasible with resources available in contributing space agencies (budget, space assets, staff, ..) and compatible with their mandates, interests, data policies, …
  Maximum reuse of past, on-going and future planned relevant Space Agencies’ activities and assets.
  Beneficial for the user community (based on user needs) but also for the space agencies.
  High profile to politicians, decision makers, major stakeholders, media,…
  Synchronized with major world events on Disaster Risk Reduction
Notes: <number>

## Slide 7: Actions: Proposed Actions
<number>
5 Major Actions:
Define a Global Satellite Observation Strategy for DRM
  Detailed assessment of needs, gaps and definition of requirements in terms of EO data (similar to FCT and JECAM)
  better coordination of EO missions for improved contribution to user DRM communities; includes definition of a DRM Baseline Dataset (data at no cost for selected observations/selected themes & limited geography). Includes existing strategic plans such as Charter.
Implement the Global Satellite Observation Strategy for DRM
  each CEOS agency to acquire, process and archive the EO satellite data and products (e.g. L0 to L2)
Set up a virtual repository for DRM-relevant data / products / information from both space agencies and DRM-Users and make the repository content accessible to all DRM users
  provide DRM user community with a series of tools to discover & access EO data through DRM-dedicated web portal (one stop shop); includes access to DRM Baseline Dataset
Set up DRM Data Processing Platform:
  a capacity to enable access to EO based Value Added products, tools & on demand processing - support science & services exploitation of Satellite EO (requires infrastructure for science data) – enable EO based content generation & hosting user generated content
Ensure the positioning of Earth Observation from Space in the 2015 post-Hyogo Framework of Actions
  2015 post-Hyogo FA Plan (2015-2025) to be adopted at 2015 World Conference on Disaster Risk Reduction and UN Nations Assembly
3 Supporting Actions: 6. DRM Outreach & Evaluation of CEOS DRM Actions,
7. EO Capacity Building for DRM,
8. Satellite EO DRM Projects Database
Notes: <number>

## Slide 8: Actions: definition & implementation processes
<number>
Assessment of needs and on-going activities
  User needs: Analysis of existing documentation from user communities on the use of sat EO for DRM
  Agencies projects: Review major DRM-related projects at national level within each of the team member agencies and identified links to key hazard types.
  Requirements: 3 types of hazards studied in detail (flooding, earthquakes and landslides). For each type, a summary statement of requirements was produced. A few types of hazards might be added in the coming months.
Response to user needs through 5+3 enlarged actions :
  clear and comprehensive strategy in 8 actions to be executed in a progressive, feasible (i.e. affordable) fashion, based on best efforts contributions and low hanging fruits
  5+3 actions are “cross-hazards” responses to requirements that are common to several types of hazards.
Implementation (not covered by current report):
  Current report is not binding: approval of the document by the team members and the endorsement by the Plenary Principals do not mean that their Agencies are automatically engaging themselves to execute all the actions.
  Step-by-step approach : execution of some action might be conditioned by successful completion of other one(s)
  Actions “à la carte”: some Agencies might support only a subset of the actions or part of an action proposed in the report.
  Open participation: some new Agencies might join the implementation group
Notes: <number>

## Slide 9: Report: Way Forward / Recommendations
<number>
Endorse the Study Consensus Report incl. the “5+3 Actions”
Establish a CEOS DRM Project Team beginning of 2013
  Project team structure similar to the CEOS FCT/GFOI and CEOS JECAM/GEO-GLAM ones
  First tasks for the March 2013 SIT meeting: generate Terms of Reference and a draft Implementation Plan.
If needed, extend the mandate of the current ad hoc Disaster Team to the March 2013 SIT meeting to ensure continuity of the activity until the establishment of the Project Team;
Mandate the current ad hoc Disaster Team to begin coordination with the UN ISDR in the lead-up to the May 2013 post-Hyogo Framework for Action activities (Global Platform for Disaster Risk Reduction);
  Consultation have started on August 27, 2012
Mandate the current ad hoc Disaster Team to liaise with UN ISDR, other major stakeholders and users to prepare the future Implementation Plan.
  Start just after 2012 CEOS Plenary
Notes: <number>

## Slide 10: Implementation: possible steps in 2013
<number>
  To be ready for 2015, start with “easy-to-reach” objectives such as:
  Limited number of types of hazards & limited geographical coverage to quickly produce concrete results.
    As showcase studies, the report focuses on 3 specific hazard types (plain flooding, seismic hazards, landslides) for which the information needs, ability of satellite EO to address them and the main gaps concerning EO capacities have been assessed and discussed.
  3-year demonstrator project 2013-2015 (R&D activity to get data more easily).
    each CEOS DRM Action to be lead by champion agency with support from other Agencies
  If demonstrator successful  operationalize in 2015 onwards, and potentially enlarge to other types of hazards .
  In parallel, establish closed dialog with right stakeholders (e.g. some UN agencies, World Bank, GFDRR, scientific community, value added industry, end users, key national governments, …) to prepare the 2015 World Conf. on Disaster Risk Reduction …
    … and intermediate milestones such as Global Platform for Disaster Risk Reduction (2013)
Notes: <number>

## Slide 11
Thank
you ….

## Slide 12: Way Forward / Recommendations
<number>
BACKUP SLIDES
Notes: <number>

## Slide 13: 1. Define a Global Obs. Strategy: Users
<number>
Improve the coordination between the space agencies through the definition of Global Observation Strategy, for DRM activities
  Benefits:
  Coordination results in optimized use of resources from agencies.
  Data acquired will be tailored to the needs of the DRM community.
  Definition of baseline datasets (no cost, no restriction):
  widely requested by user community.
  designed to meet a minimum use threshold, but will not address all DRR needs.
  mechanism to encourage EO data uptake and might lead to broader (paid) use of EO data by global DRM stakeholders and end users.
  By no means, a commitment by CEOS agencies to make all DRR data available at no cost.
  User information needs refined by:
  knowledge of the needs from the community of users, by each agency and
  closer relationship with major stakeholders (UN agencies, GFDRR, etc.)
Notes: <number>

## Slide 14: 1. Define a Global Obs. Strategy: Implementation
<number>
Improve the coordination between the space agencies through the definition of Global Observation Strategy, for DRM activities
  Requires agreement on strategic objectives (projects, initiatives, types of hazards, geographical zones, ..) to serve. Partially based on interactions with major stakeholders to get an indication of needs / priorities.
  Some missions have no specific background missions (e.g. Landsat, Sentinels) as instruments observe in permanence according to scenarii defined in advance
  Some space agencies are not directly responsible for the planning and operation of some satellites (e.g. CNES and SPOT, DLR and TerraSAR-X, CSA and Radarsat-2) ; access and use conditions are ruled by Data Policies; could be circumvented the first two or three years if we build a pilot project.
  Similar to SDCG for FCT/GFOI and soon for JECAM/GEO-GLAM.
  Global Strategy Plan to be revised annually. First issue for 2013 CEOS Plenary.
  Includes the definition of a baseline dataset (as promoted by the GEOSS Data Sharing Principles & CEOS Data Democracy).
Notes: <number>

## Slide 15: 2. Implement the Global Obs. Strategy: Users
<number>
Implement the Coordinated Global Observation Strategy, for DRM activities
  Benefits:
  Populating CEOS agencies’ archives with useful data is necessary to enabling many DRM activities (e.g. flood risk studies over time or the rapid generation of change detection products during the response phase).
  Today, technical intermediary users rely on informal consultations with mission managers from individual agencies to ensure archives are populated, with varying degrees of success.
  Agreeing on collective priorities would reduce overlaps, ensure better coverage and optimize existing resource allocation.
Notes: <number>

## Slide 16: 2. Implement the Global Obs. Strategy: Implementation
<number>
Implement the Coordinated Global Observation Strategy, for DRM activities
  Each CEOS Agency to proceed with acquisition, “standard” data processing (L0 to L2) and products archiving
  Some space agencies are not directly responsible for the planning and operation of some satellites (e.g. CNES and SPOT, DLR and TerraSAR-X, CSA and Radarsat-2) but limited impact during demonstration phase (R&D activities thus easier to get free data)
Notes: <number>

## Slide 17: 3. DRM Virtual Repository: Users
<number>
Implement a Virtual Repository for DRM-relevant data, products & information from both space agencies and DRM Users and make the repository content accessible to all DRM users
  Benefits:
  Finding and access the right data can be a challenge of the international DRM community: search many distributed data repositories and catalogues, data gaps, …
  Users may identify more easily usable data sets through a single interface and then link directly to the data providers.
  Could be presented as a contribution in kind from the space agencies to other relevant infrastructures such as the GFDRR Labs.
  Easy access to the DRM Baseline Dataset, at no cost and no restriction,
Notes: <number>

## Slide 18: 3. DRM Virtual Repository: Implementation
<number>
Implement a Virtual Repository for DRM-relevant data, products & information from both space agencies and DRM Users and make the repository content accessible to all DRM users
  Includes also a web interface and a virtual catalog. More than a replication of GEO Web Portal: User interface incorporates functions / features specific to DRM.
  For DRM Users, “one stop shop” web interface to discover data, products and information (distributed catalogs seen as single virtual catalog) Query results provide necessary information to provide “easy” access to data / products / information
  Distributed architecture for the physical repositories of data & information
    no repatriation of data / products / information to a unique centralized repository
    may include existing repositories such as GeoHazards Virtual Archive
  User access to data might be constrained by data policy issues especially data from commercial distributors
Notes: <number>

## Slide 19: 4. DRM Processing Platform: Users
<number>
Implement a platform to enable access to EO based Value Added products, tools & on demand processing:
support science & services exploitation of Satellite EO
enable EO based content generation & hosting user generated content
  Benefits:
  Many users (end users or intermediate users) lack the tools and capacity to fully exploit EO satellite data. Even when proper EO data is easily available from CEOS agencies, it may remain unexploited due to lack of resources to transform this data.
  DRM Processing Platform offers high-level tools and services not available in-house through a shared infrastructure at an affordable cost. Enable extracting information from EO data and putting it into a form people can readily use
  The Processing Platform provides the user community with the full set of tools to better support vertical thematic applications.
  May foster the development by third-parties of new specialized applications for targeted segments of DRM.
Notes: <number>

## Slide 20: 4. DRM Processing Platform: Implementation
<number>
Implement a platform to enable access to EO based Value Added products, tools & on demand processing:
support science & services exploitation of Satellite EO
enable EO based content generation & hosting user generated content
  Relevant prototypes are being assembled e.g. European cloud computing platform. "Helix Nebula “ (with CERN, ESA and EMBL)
    2-year pilot phase just starting. Business plan requires further consolidation
  No reuse of existing space agencies infrastructure
Notes: <number>

## Slide 21: 5. 2015 post-Hyogo Framework Actions: Users
<number>
Ensure the positioning of Earth Observation from Space in the 2015 the post-Hyogo framework of actions (e.g. in the declaration of the and the post-Hyogo framework of actions)
  Benefits:
    will increase the awareness of the DRM stakeholders and decision-makers on the use of EO data in support to DRM and hopefully, as a consequence might lead to an increased role of EO space agencies in DRM.
Notes: <number>

## Slide 22: 5. 2015 post-Hyogo Framework Actions: Implementation
<number>
Ensure the positioning of Earth Observation from Space in the 2015 the post-Hyogo framework of actions (e.g. in the declaration of the and the post-Hyogo framework of actions)
    Requires identification of the right / proper interfaces (influential persons & organizations, ..).
    Space Agencies’ lobbying can be done also via National Governments
    Prerequisite for this activity is a successful demonstration of space agencies’ performance in the execution of the 2 other activities (coordinated BRM & DRM Virtual Repository)
    The post-Hyogo framework will be endorsed at the 2015 UN World Conference on Disaster Reduction1 but there some key intermediate milestones such as the Global Platform for Disaster Reduction (May 19-23, 2013 – Geneva)
1. Japan is willing to host the 3rd UN World Conference on Disaster Reduction
Notes: <number>

## Slide 23: Supporting Actions: Users
<number>
6. DRM Outreach & Evaluation of CEOS Actions
Animate the scientific & technical content of the Virtual Repository & Exploitation Platform, linking to practitioners/users of DRM communities, measuring impact & evaluating effectiveness – manage, explain & promote the content
7. EO Capacity Building for DRM
Develop capacity building programs on a regional basis that support regional DRM users in the use of EO.
8. Sat EO DRM Project Database
Create a web-hosted data base that CEOS member agencies and eventually users and stakeholders could search to find related DRM projects or potential partners for a specific activity. The database is meant to showcase existing DRM activities within CEOS member agencies.
Notes: <number>

## Slide 24: Report - Table of Contents
<number>
0. Executive Summary
I. Introduction & background
  Purpose of document (incl. intended audience )
  Why is DRM important?
  A CEOS Disaster Initiative – background and rationale
  CEOS Disaster Ad Hoc Team establishment, mandate and objectives
  Historical context, other initiatives
II. Global Disaster Risk Management Activities
  Who are the stakeholders and DRM users?
  Who are the potential partners and what are their major programs and initiatives?
  What are the information needs ?
  What are the observation strategy ?
  What exists now and what works well?
  What are the (major) gaps?
III. CEOS Agency Risk Management Activities
  Overview of collective CEOS satellite capability
  CEOS strengths and weaknesses
  Major categories of space agency contributions to DRM with examples
  Existing CEOS activities relating to Disasters
IV. Potential CEOS Contributions
  Identify options for major CEOS contributions, including specific proposals
  Identify supporting CEOS contributions
V. Conclusions and Recommendations
  Main conclusions of the ad hoc team regarding opportunities and threats/risks
  Benefits and potential issues for various options from section IV
  Structured list of recommendations
  Recommended course of action and main thrusts for implementation
ANNEXES
References
Annex 1 – Global User Needs
Annex 2 – CEOS Agency-by-Agency Disaster
Activity Review
Annex 3 – CEOS Disaster Ad Hoc Team
membership and acknowledgements
Notes: <number>

## Slide 25
Requir.
DRM Virtual Repository
NEEDS
NEEDS & MEANS
NEEDS
Requir.
EO Data
EO Data
EO Data
INFLUENCE
Lobby, Communication
Potential Future Projects
Requir.
EO Data
EO Products & Information
EO Products & Information
New NEEDS
New NEEDS
Existing DRM-related
Projects e.g. Charter
Existing DRM-related
Projects e.g. Charter
Existing DRM-related
Projects e.g. Charter
Existing DRM-related
Projects e.g. Charter
Existing DRM-related
Projects e.g. Charter
EO data
NEW
Post-Hyogo FA
(2015 World Conference on DR,
Global Platform for DRR 2013)
NEW
CEOS
Space
Agencies
End Users
(Scientists,
Decision makers,
Value-Added
Geospatial Services,..)
UN Organizations,
World Bank,
GFDRR, GEO,
Donor Organizations…
Coordinated Global
Observation Strategy
(define+implement)
NEW
DRM Processing
Platform
NEW
EO Data
Notes: <number>