## Slide 1: Summary of Status of Remaining CEOS Actions in Support of GEO Priorities
Kerry Ann Sawyer
Deputy CEOS Executive Officer

## Slide 2: Overview
Genesis of the “actionable” CEOS Actions
Why are Actions important?
A little bit of statistics
Current state of affairs
Reminder messages – what do you do?
A look toward the future
  Near-term
  Long-term

## Slide 3: Genesis of the “Actionable” CEOS Actions – Remapping
November 2007
  Following endorsement of the annual update of the GEO 2007-2009 Work Plan, the SIT Chair started a large consultation within CEOS to define a set of CEOS Actions supporting the Tasks of the Work Plan
  Collaborated with GEO Secretariat
February 2008
  Workshop organized by SIT gathering CEOS Virtual Constellation Co-Leads, Working Group Chairs, CEOS SBA Coordinators, SEO, CEO
  Defined first list of 147 “actionable” actions
Each CEOS Agency identified as the Lead Agency for these Actions committed the resources necessary for the accomplishment of the Actions

## Slide 4
GEO Document and CEOS Action Traceability c.2008
GEO Group on Earth Observations
GEOSS Global Earth Observation System of Systems
GCOS Global Climate Observing System
CEOS Committee on Earth Observing Satellites
GEO 2007-2009 Work Plan
39 Continuing 32 New
GEOSS 10-Year Implementation Plan Feb-2005
107 (2-year) 82 (6-year) 52 (10-year)
GCOS Implementation Plan Oct-2004, GCOS-92
24 Key Actions 32 Atmosphere 41 Ocean 37 Terrestrial 21 Cross-Cutting
28 Essential Climate Variables (ECVs)
CEOS Implementation Plan Oct-2007
CEOS Response to the GCOS Implementation Plan Sep-2006
59 Total Actions
32 (2-year) 28 (6-year) 18 (10-year)
Systematic Observational Requirements for Satellite-Based Products for Climate Sep-2006, GCOS-107
12 Atmosphere 19 Ocean 6 Terrestrial 22 Cross-Cutting
155 Total Actions
78 Total Targets
241 Total Targets
71 Total Tasks
“SIT Remapping”
294 Observational Requirements (ORs)
Space-based
GLOBAL
Space-based 32 High-category
GLOBAL
New CEOS Actions
Space-based 21 High-category
Courtesy I. Petiteville Feb 2008
Notes: 4

## Slide 5: Why Are CEOS Actions Important?
Highlight the commitment of Space Agencies to implement the Global Earth Observation System of Systems (GEOSS)
  Actions focus exclusively on space segment aspects and efforts of Space Agencies to implement Components of the GEO Work Plan and GEOSS
Captured in the annual CEOS Implementation Plan

## Slide 6: A Little Bit of Statistics
Chart: CEOS Actions in Support of GEO Tasks 2008-2012
| 39479 | 39845 | 40210 | 40575 | 40940
Open | 147 | 93 | 54 | 46 | 50

## Slide 7: More Statistics
 | 2008 | 2009 | 2010 | 2011 | 2012
Cat 1 | 60 | 47 | 33 | 22 | 50
Cat 2 | 56 | 26 | 21 | 24 | 0
Cat 3 | 18 | 8 | 0 | 0 | 0
Cat 4 | 13 | 12 | 0 | 0 | 0
Total | 147 | 93 | 54 | 46 | 50

## Slide 8: CEOS Actions Remapping to GEO Priority Actions
Actions support identified CEOS Priorities/Expected Outcomes from the 2012 CEOS Work Plan as well as the 26 Tasks/ 60 Components of the GEO 2012-2015 Work Plan
To be an Action, the activity must:
  Have the cooperation of at least two CEOS Agencies1
  Have a “significant” level of effort and good coordination (e.g., publication of an article does not need to be followed as an action. The article might be published on www.ceos.org)
  Contribute significant and citable benefits towards meeting societal needs
  Be “Actionable” (properly described, feasible with Lead Agencies (or WG, VC), at least one Contributor, clear Milestones and Deliverables, potential support might be indicated
  1 WG and VC considered “multi-agency’” group
OBJECTIVE: Fewer but more useful CEOS Actions
Notes: Each of the Components has a number of Priority Actions identified
  “Practical actions and outputs supporting the Component implementation”
  “Defined and implemented by Leads and Contributors”
CEOS Actions will be accomplished in support of the GEO Component Priority Actions
  Many Actions focus specifically on those Components where CEOS is already identified as a Component Lead or a Contributing Agency

## Slide 9: Current State of Affairs
50 Actions for 2012
To date, 3 have been CLOSED (2 are “Yay!!”)
  ID-04-C1_1: Kudos to ESA and the EO Handbook Team for producing the special edition for the Rio+20 Summit
  SB-01-C2_1: ESA, NASA, and ISRO finalized the INSITU-OCR White Paper
Of the 47 Remaining OPEN Actions:
  31 have been updated within the past month (Thank you)
  Which leaves 16 Actions that are “unaccounted” for…and I am not one to publicly shame…well

## Slide 10: …Maybe I Am
Action | Lead Agency | Short Description | Last Update
AG-01-C1_1 | USGS, ISRO, INPE | Provision of optical satellite data through LSI for JECAM | 7 Jun 12
CL-01-C2_1 | NOAA | CEOS Response to the GCOS IP | 13 Sep 11
CL-01-C2_2 | EC-JRC | ECV Inventory | 13 Sep 11
DI-01-C1_1 | CSA | Satellite needs and gap analysis for Disaster Management Systems | 22 Mar 12
DI-01-C2_1 | ESA | Volcanic ash monitoring from space | 1 Jun 11
DI-01-C2_3 | CSA | Develop topographic and bathymetric data | 
DI-01-C2_4 | CSA | Global operational fire warning | 
HE-01-C2_1 | CNES | Water quality and coastal water policies | 1 Feb 12
HE-01-C3_1 | CNES | Addressing vector-borne diseases | 1 Feb 12
IN-01-C2_1 | NASA | IOCCG Report for Level 1 OCR requirements | 30 Jan 12
IN-01-C2_4 | NASA | Long-term ozone record harmonization | 15 Feb 12
Green text means that updates have been promised

## Slide 11
Action | Lead Agency | Short Description | Last Update
IN-02-C1_2 | UKSA | DOME-C multi-sensor experiment | 12 Feb 12
IN-02-C1_3 | USGS | CEOS QA4EO implementation | 31 Jan 12
IN-02-C1_4 | USGS, ESA | Cal/val portal for QA4EO | 13 Feb 12
IN-02-C1_5 | USGS | Data and information interoperability and harmonization in CEOS and GEO | 10 Feb 12
WA-01-C5_2 | ESA | Follow-on TIGER activities | 28 Feb 12

## Slide 12: What is This?

## Slide 13: Actions Reminders
To: Primary POC Subject: CEOS-GEO Action Update Greetings: You are receiving this email message because you are listed as the Primary Point-of-Contact (POC) for the CEOS-GEO Action listed below. Your action is either due for completion within one month, has not been updated in the past 3 months, or is past due. Please visit the CEOS-GEO Actions tool (http://www.ceos-actions.com) and provide an update to your action in the "Summary and Accomplishments" section. If you have any questions about the use of the tool or editing access, please contact Kim Keith, CEOS SEO (Kim.E.Keith@gmail.com). Thank you. Action: ????? Deputy CEOS Executive Officer (CEO)

## Slide 14: What to do when you get the Reminder
Step 1: PLEASE…do NOT delete the message; send the message to your SPAM or Junk Mail, or ignore the message.
Step 2: Go to the Actions tracker and update the action; if there is nothing to report or change, please at least change the date so we know you are keeping track of the action.
Step 3: Enjoy the fact that since you have updated the action, you will not receive another pleasant reminder message for at least another three months (or sooner, if the action is due).

## Slide 15: A Look Toward the Future
How do we address actions that are being accomplished in execution of other high priority CEOS initiatives?
  SDCG
  Disaster
  GCOS Climate Actions
2012 CEOS Implementation Plan – December 2012
Updates to the 2012-2015 GEO Work Plan
  Call for Proposals for new CEOS Actions to support GEO Components – January 2013
  Workshop – February 2013?