## Slide 1: SIT Technical Workshop Disasters SBA Report September 2013
<number>
WP section 4. Disaster Risk Management
Francis Lindsay and Karen Moe, NASA

## Slide 2
<number>
Objective of the presentation
This presentation is intended to provide the SIT with the current status and updated progress on the disaster activities supported within CEOS.
Currently CEOS is engaged in ten disaster actions/activities:
  C1_1: Satellite data Needs and Gaps: PoC Guy Seguin, NASA
  C1_2: Architecture: PoC Karen Moe, NASA
  C1_3: Global Observation Strategy for DRM: PoC, Ivan Petiteville, ESA
  C1_4: Hyogo Framework stakeholder: PoC Ivan Petiteville, ESA
  C1_5: Use of Satellite data for coastal zones: PoC Guy Seguin, NASA
  C2_1: Global web-based volcanic ash service: PoC Claus Zehner, ESA
  C2_2: Supersite proposal evaluation: PoC Jörn Hoffmann, DLR
  C2_4: Supersite data provision coordination: PoC Jörn Hoffmann, DLR
  C3_1: Caribbean Satellite Disaster Pilot: PoC Stuart Frye, NASA
  C3_2: Southern African Flood and Health Pilot: PoC Stuart Frye, NASA

## Slide 3: Disasters SBA Report Summary
<number>
  Accomplishments since the 2012 Plenary
      Report on the progress of the Disaster Task at the GEO Symposium (June 2013)
      A Gap analysis was developed for flood observations
      A high-level model/architecture was developed for Disaster management
      Contributed to a Global Observation Strategy being developed under DRM
      A proposal was received from the Coastal Zone CoP
      Supersites proposals are being developed for Iceland
      A report on the 2012 Caribbean Satellite Disaster Pilot was produced
      Flood event in Namibia was used for a Cal/Val exercise
  Future remaining activities and milestones
    Completion/wrap-up of actions and plan for disaster SBA activity continuity
  Leadership Changes
    Note, Francis Lindsay (NASA) is assuming Disaster SBA Coordinator position from Karen Moe (NASA)
  Main Issues/concerns?
    Impact of decisions at the CEOS Plenary on the continuity of activities
    Organization and leadership of the Disaster activities

## Slide 4
<number>
A mapping of the CEOS and GEO Disaster Tasks
  C1_1: Satellite data Needs and Gap
  C1_2: Architecture
  C1_5: Use of Satellite data for coastal zones
  C2_1: Global web-based volcanic ash service
  C2_2: Supersite proposal evaluation
  C2_4: Supersite data provision coordination
  C3_1: Caribbean Satellite Disaster Pilot
  C3_2: Southern African Flood and Health Pilot
  C1_3: Global Observation Strategy for DRM*
  C1_4: Hyogo Framework stakeholder
GEO Disaster Task
C1 Disaster Management Systems
International Charter on Disaster
Enhance use of Satellite data …
Perform a gap analysis …
…
C2 Geohazards Monitoring …
Global Earthquake Model
Supersites
Volcanic Ash monitoring
C3 Regional End to End Systems
Regional end to end projects
Not in the WP
A new component was proposed
These activities are a mix of CEOS-led and CEOS acting as a contributor.
  * Note, this activity leverages the efforts of several tasks shown here.

## Slide 5
<number>
Essential contribution to the component C1 of the Disaster Task “Disaster Management Systems” to Enhance the use of satellite data and to perform Gap Analysis.
- Flood Gap Analysis released in draft form (SIT 28, March 2013)
  From established user needs => identify key observational requirements => relevant sensors and performed outward looking gap analysis
  Paper available at http://ceos.org/images/Floods_Analysis_030713.pdf
DI-01-C1_1 Satellite data Needs and Gap Analysis

## Slide 6: DI-01-C1_2 Architecture
<number>
GEOSS Architecture for Disasters
  Describe and document a high-level reference model for the use of satellites and associated data to support disaster management and risk assessment
2013 Achievements/Outcomes:
  Contributions to ad hoc WG on DRM regarding architecture and data considerations
  Co-hosted GEOSS Future Products Workshop (featuring architectures) March 2013
  GEOSS Architecture Implementation Pilot (AIP-5) contributions of targeted satellite images as tiled overlays for dashboard display enabling users to customize view of selected data product layers accessed using Cloud-technology January 2013
Enterprise Viewpoint:
Activities for Satellite Products in DRM
User-generated postings
Routine / Global
Monitoring
1. Event detection
Routine / Global model outputs
4. Modeling
Task sensors
In situ
Remote
Acquire data
3. Data acquisition
Archive
Visualize
Ongoing updates
Alerts / Notices
Publish product
6. Dissemination
Preprocess
Analyze
5. Analysis
Interpret
Decision Analysis: Act / Plan
2. Situational Awareness
Gather / Assimilate Information
Local Forecast
Hindcast
Nowcast
Future remaining milestones
  Final Architecture document to be presented at WGISS-36 September 17, 2013
  New capability enabling mobile device users to request customized data products to be demonstrated at AIP-6 January 2014
  WGISS project completes in January 2014
  Continuing information systems and services architecture contributions anticipated in future CEOS disasters initiatives

## Slide 7
<number>
At CEOS Plenary in October 2012
  CEOS accepted Hawaii as a “Permanent Supersite”
  CEOS committed to support this Supersite with these resources:
    (ASI) 100 scenes/yr COSMO/Skymed
    (CNES) 1 coverage @ 2.5m SPOT-5
    (CSA) archive data Radarsat-1 200 scenes of archive Radarsat-2
    (DLR) 250 scenes by end 2014 TerraSAR-X
    (ESA) complete archive ERS-1, -2, Envisat any available acquisition Sentinel-1, -2
    (NASA) any available acquisition EO-1
DI-01-C2_2 Supersite data provision coordination
CEOS Plenary approved proposed Supersite selection process
− includes mandating the CEOS Supersites Coordination Team (SCT) as a CEOS SBA Disaster subgroup for preparing decisions by SIT and Plenary

## Slide 8
<number>
Iceland Supersite Proposal:
Requested data includes an extensive set of InSAR images for crustal deformation studies. These data will complement the available ground based in-situ data presently available and that will be made available through the FUTUREVOLC project.
DI-01-C2_2 Supersite data provision coordination
TerraSAR-X coverage of Iceland Supersite
Under evaluation by the CEOS Supersites Coord. Team
TerraSAR-X: (250 acquisitions per year suggested)
COSMO SkyMed: (250 acquisitions per year suggested)
Radarsat-2: (120 acquisitions per year
suggested)
ALOS-2: (200 acquisitions per year suggested)
SAR Data Archive (all Iceland data suggested)
SPOT: (40 acquisitions per year suggested)
ASTER: (Archived data for the Eyjafjallajökull 2010 and Grímsvötn 2011 eruptions, future events.)

## Slide 9
<number>
Pilot team worked with CIMH, CDEMA, UWI, and CATHALAC to provide satellite coverage for hurricanes: Ernesto, Isaac, and Sandy for Haiti, Jamaica, Barbados, St Lucia, and British Virgin Islands. Support to other events include: Flooding in Panama
Earthquake in Guatemala
Algal bloom in El Salvador
Wildfires in Belize
Landslides in Trinidad
A total of 34 Radarsat-2, 19 EO-1 images and MODIS daily coverage.
DI-01-C3_1 Caribbean Satellite Disaster Pilot 2012 Report
Haiti, Port of Prince area: August 31, 2012
EO-1 ALI pan-sharpened product courtesy of NASA
After Isaac
Note increase of sediment
plume from river discharge
Note increase of flooded
Area in coastal lagoon
EO-1 ALI Image Change Detection:Significant Increase in River Discharge
Notes: I don’t want to point fingers, but only ESA, ASI, CSA and DLR are fully engaged.
Most crucial gap is JAXA (Alos/Alos-2), but also CDTI (PAZ), CRESDA (HJ-1C), ISRO (RISAT?)
NASA, CNES would be interesting once use moves beyond SAR
How about taking an action for all CEOS agencies to provide a name/contact to CEOS Sec by xyz date / or decline as not interested?

## Slide 10: DI-01-C3_2 Southern African Flood and Health Pilot
<number>
Ground Cal/Val Exercise with Radarsat, EO-1, Ground Team, Helicopter team, OpenStreetMap, Crowd Sourcing on Kavango river in Namibia 1-30-13
EO-1 Water Edge Detection (red)
Radarsat Water Edge Detection (yellow polygon)
Team 1 walking bank to collect GPS point s (red X’s)
Team 2 walking bank to collect GPS point s (green X’s)
One of 500 GPS photos from helicopter
This pilot project represents a good example of cooperation with local authorities and other stakeholders and will also contribute to the development of a multi-hazards Global Observation approach.
Notes: I don’t want to point fingers, but only ESA, ASI, CSA and DLR are fully engaged.
Most crucial gap is JAXA (Alos/Alos-2), but also CDTI (PAZ), CRESDA (HJ-1C), ISRO (RISAT?)
NASA, CNES would be interesting once use moves beyond SAR
How about taking an action for all CEOS agencies to provide a name/contact to CEOS Sec by xyz date / or decline as not interested?

## Slide 11: Near Future Plan
<number>
Additional expected achievements by the end of 2013:
  Complete GEO WP review for the Disaster Task (2 news components)
  Assess applicability of Flood Gap Analysis to other type of disasters (there is a proposal is to develop a tool to automate future gap assessment)
  The Caribbean flood pilot will continue to monitor storms through the 2013 season
  Finalize resource proposal for Iceland and Turkey Supersites
  Finalize resource agreement for the Coastal Zone demonstrator
Contribution to 2013 Events (e.g., GEO Ministerial Summit, COP-19/SBSTA-38):
  Contribution to the GEO AIP video booth and to the CEOS video on tsunami/QA4EO/disasters, which will be shown in the CEOS booth during the GEO Ministerial Summit.

## Slide 12: Near Future Plan
<number>
Information on any decision(s) that need to be made at CEOS Plenary:
  None at present, pending the possible reorganization of activities proposed by the Disaster Study Team proposal.
  However, ongoing disaster activities as presented here will continue on in their development.