## Slide 1: GEO Work Plan update Espen Volden evolden@geosec.org CEOS SIT Technical Workshop Pasadena, 11-12 Sept 2013
© GEO Secretariat

## Slide 2: GEO Work Plan – What is it? Framework for implementing the GEOSS 10-Year Implementation Plan (2005-2015) Set of practical Tasks carried out by various GEO Members and Participating Organizations Living Document – Annually updated (Task Component sheets in online Work Plan continuously updated)
Notes: <number>
Seven shortcoming were identified as target areas that GEOSS could address:
Lack of access to data and associated benefits in the developing world
Eroding technical infrastructure
Large spatial and temporal gaps in specific data sets
Inadequate data integration and interoperability
Uncertainty over continuity of observations
Inadequate user involvement
Lack of relevant processing systems to transform data into useful information

## Slide 3: * Implementation of operational & sustainable GEOSS (full & open access; interoperable systems) * Reinforcement of coordination, user engagement & resource mobilization * Development of information products and end-to-end systems across 9 Societal Benefit Areas
3 Main Objectives

## Slide 4: 3-Part Structure
1. INFRASTRUCTURE (5 Tasks)
(Architecture and Data Management)
2. INSTITUTIONS AND DEVELOPMENT (5 Tasks)
(Data Sharing, Capacity Building, Science and Technology, User Engagement)
3. INFORMATION FOR SOCIETAL BENEFITS (16 Tasks)
(9 GEOSS Societal Benefit Areas)

## Slide 5: Work Plan Revision 2.1 (27 August 2013)
Incorporates technical comments from GEO community May-July 2013
Draws from recommendations of 2013 Work Plan Symposium (4-6 June, Geneva)
No major change to Rev. 2 (17 Dec 2012)

## Slide 6: Work Plan Revision 2.1 (27 August 2013)
Two Task Components are created:
a. DI-01-C4 “Global Wildfire Information System” (proposed by EC)
b. DI-01-C5 “Foster utilization of Earth observation remote sensing data for all phases of Disaster Risk Management” (proposed by CEOS)
Two Task Components are removed or merged:
a. ID-04-C3 “Global Environment Information Platforms” removed (proposed by EEA)
b. ID-02-C1 “Institutional Development” merged with ID-02-C2 “Individual Development” to become “Institutional and Individual Development” (proposed by South Africa on behalf of ID-02 Task Team)
Task descriptions and Priority Actions are revised and Task Leads are updated (e.g. IN-01, IN-04, ID-03; proposed by related Task Teams)

## Slide 7: Work Plan 2.1 -> 2.2
Revision 2.1 submitted for official review until 22 October 2013 (17 October to Kerry!)
Revision 2.2 will be prepared and submitted to GEO-X Plenary in Jan 2014 for acceptance

## Slide 8
Cryosphere
Global Carbon Cycle
Geohazards
Ocean
Water Cycle (IGWCO)
Community of Practice: Cryosphere (under discussion)
Task: WA-01-C3 Information Service for Cold Regions
Community of Practice: Carbon
Task: CL-02 Global Carbon Observation and Analysis
Communities of Practice: Forest, Global Agricultural Monitoring
Tasks: SB-02 Land Cover; SB-03 Global Forest Observation; EC-01 Global Ecosystem Monitoring; AG-01 Global Agricultural Monitoring
IGOS Themes
GEO CoPs and Work Plan Tasks
Community of Practice: Integrated Global Water Cycle Observations
Task: WA-01 Integrated Water Information (incl. Floods and Droughts)
Communities of Practice: Air Quality, Health & Environment, Carbon
Tasks: HE-01-C1 Air-borne Diseases, Air Quality and Aeroallergens; HE-02 Tracking Pollutants; CL-02: Global Carbon Observation
Community of Practice: Geohazards; Supersites Initiative
Task: DI-01 Informing Risk Management and Disaster Risk Reduction
Community of Practice: POGO
Task: SB-01 Oceans & Society – Blue Planet
Community of Practice: Coastal Zone
Tasks: SB-04 Global Urban Observation and Information;
DI-01 Informing Risk Management; EC-01 Ecosystem Monitoring
Atmospheric Chemistry (IGACO)
Coastal Observations
Land (IGOL)
Status of IGOS Transition into GEO (2013)