## Slide 1: WGClimate
John Bates NOAA
SIT Workshop Agenda Item #8
WGClimate Work Plan progress & Issues CEOS SIT Technical Workshop
CNES, Montpellier, France 17th-18th September 2014

## Slide 2
WGClimate Work Plan
Background
WGClimate was the trial Working Group for the new form of the CEOS-CGMS 3-year Work Plan
Work Plan elements implement WGClimate objectives in sequential order
Activities include Climate Monitoring, Research, and Services (CMRS)
  Coordinate development of Climate Data Records (CDRs) and related datasets addressing Essential Climate Variables (ECVs) established by the Global Climate Observing System (GCOS)
  Continue cooperation with Group on Earth Observations (GEO), Global Climate Observing System (GCOS), and the World Meteorological Organization (WMO), in the development of a space-based system to support climate information and adaptation.

## Slide 3
WGClimate Work Plan
The first 3 CMRS activities form an iterative cycle, acknowledged in the last CMRS activity
CMRS-1: ECV inventory (first version) – ECV inventory status reviewed and Version 1 (V1) status identified
  Status – Delayed one quarter - Issue identified need to fix ECV/CDR pairs and establish version control – Complete, however, took more time than anticipated
CMRS-2: Gap analysis (first version) – Define reference process for gap analysis and necessary tools to support this
  Status - Delayed one quarter - Reference process for assessment has been discussed at WGClimate meeting and SST VC CDR assessment report. Assessment of process metrics (i.e., documentation, access, etc.) is moving forward with WGClimate members evaluating CORE-CLIMAX system maturity matrix
  Fitness for purpose for scientific objective/societal benefit metrics are much more difficult and no consensus exists. WGClimate is working with WCRP Data Advisory Committee and US National Academies on approaches

## Slide 4
WGClimate Work Plan
The first 3 CMRS activities form an iterative cycle, acknowledged in the last CMRS activity
CMRS-3: Action plan (first version) – Identify actions Space Agencies can take to mitigate any gaps –
  Status – Delayed one quarter - For ECVs, we are clarifying that this refers to gaps in continuity of the ECV that can occur due to a variety of causes and these are being better identified
CMRS-9: Update of ECV inventory, gap analysis and action plan (version 2) – The above sequence forms the basis for an ongoing analysis cycle, in agreement with the new GCOS plans
  Status – This action is dependent on the sequence above.

## Slide 5
WGClimate Work Plan
The next two CMRS activities seek to assure that climate products are connected to user applications and decision support
CMRS-4: Case studies linking CDRs to societal applications and informed policy decisions – Identify examples from current work and map it to the Climate Monitoring Architecture
  Status – In progress and on for Q1 2015 – A concept of capturing science objectives/societal application requirements and mapping them to GCOS ECV requirements is being developed
CMRS-5: Contributions to the Global Framework for Climate Services (GFCS) – Work to identify existing examples of Climate Services that can be applied or adapted to the GFCS focus areas
  Status – Chair WGClimate has been invited to the GFCS Meeting in Implementation Coordination in late September and will report on results at CEOS Plenary

## Slide 6
WGClimate Work Plan
The final three elements identify important interactions with external communities
CMRS-6: Report to UNFCCC Subsidiary Body for Scientific and Technological Advice-Research and Systematic Observation (SBSTA-RSO 41) 2014
  Status – On Schedule – See separate report under item 17
CMRS-7: Report to GCOS implementation plan activities accomplished by Space Agencies on climate observations
  Status – Tight Schedule for SIT-30 - The draft CEOS response to the GCOS IP and Satellite Supplement 2010 will be presented for endorsement at SIT-30 in Spring 2015. Following endorsement, it will be integrated into the GCOS Progress Report in August/September 2015 for submission to COP-21.
  Other activities and deliverables have been proposed for COP-21. WGClimate is working with CEOS Chair to help clarify roles and responsibilities
CMRS-8: Incorporation of in situ data holdings within the ECV inventory – reuse original ECV questionnaire framework. Data base analysis and follow up will not be done by CEOS

## Slide 7
WGClimate Work Plan
Final thoughts on challenges
ECV Inventory needs additional inputs both from Space Agencies and beyond to include individual Scientific Investigators
  Consider working with WCRP and GCOS to invite contributions as an outcome of the 2014 Climate Symposium
ECV Inventory maintenance and updating will require ongoing involvement of WGClimate members and CEOS core support
  Thanks to NASA and ESA for supporting current development
WGClimate membership does not have a consensus on accepting future oversight of Strategy for Carbon Observations from Space
  Continue to work with the Ad Hoc CEOS Carbon Strategy Implementation Study Team (CSIST) to define appropriate CEOS entities and processes for disposition and tracking of actions
  Hopefully CSIST results will clarify actions so that WGClimate burden for future leadership of CEOS Carbon activities will be viewed as more realistic by a majority of WGClimate members

## Slide 8
WGClimate Work Plan
Presenter Guidance
Note the