## Slide 1: CEOS Strategy for Carbon Observations from Space – Report of Implementation Study Team
Stephen Briggs
European Space Agency
SIT Workshop Agenda Item #13
CEOS Plenary outcome : 3.2
SIT Technical Workshop
CNES, Montpellier, France 17th-18th September 2014

## Slide 2
SUMMARY
  History and Background
  Establishment of Implementation Study Team
  Progress since SIT 29 (April 2014)
  Status as of SIT Workshop, September 2014
  Discussion and way forward

## Slide 3
Title
History and Background
GEO Carbon Report developed in June 2010 by team led by Ciais et al. (GCP).
CEOS Strategy for Carbon Observations from Space – written in response to above, completed in March 2014 – Wickland et al.
Proposed results presented to SIT Workshop and CEOS Plenary in 2013.
42 Actions identified in the report for specific response including Action for Carbon Team to manage response via CEOS(/CGMS) Working Group Climate – first discussed at SIT Technical Workshop in September 2013
  Issue remained open until April 2014,
At SIT-29:
  The CEOS Strategy for Carbon Observations from Space was endorsed during Plenary session
  Proposed establishment of a study team to take forward the Actions and also identify formal CEOS mechanism to manage Actions.

## Slide 4
Title
Establishment of CEOS Carbon Strategy Implementation Study Team (CSIST)
SIT-29 suggested further study of report to elucidate concrete way forward because of expressed concern about the nature and wording of the recommended actions, noting that several of the more substantive ones were well beyond the scope of what CEOS can or should do.
CSIST set up in May 2014: S Briggs (ESA), K Sawyer (CEO), J Bates (WGClimate/NOAA), C Ishida/M Nakajima (JAXA), A von Bargen (WGCV/DLR), Z Zhu (USGS), D Wickland/C Bognar (NASA), J Ometto (INPE), C Deniel (CNES)
ToR established by CEOS Chair / SIT Chair. Objective to analyse recommendations of Carbon report and propose concrete way forward.
Team led by S Briggs, K Sawyer met 28 July 2014 at ESA Office, Washington DC.
Produced draft spreadsheet of outcomes distributed before SIT Workshop. Documents distributed: ToR, report of progress, spreadsheet.
Not intended to go through all spreadsheet actions individually here.

## Slide 5
Title
3. Progress and current status (i)
  Spreadsheet of 42 Actions, based on Table 6.1 of the CEOS Strategy, completed by CSIST. Each analysed for:
    Type of action (mission, cal/val, product, ……..)
    Action description text
    mid/near/long term action (end 2015, end 2017, >2017)
    CEOS lead and contributing entities
    Compatibility with available CEOS Resources (Green/yellow/red)
    Estimated effort (minor, major, significant new entity/activity)
    Linkage to GEO Community of Practice
    Need for partnerships with external agencies
Items in red above were new analysis of the CSIST; items in blue were originally identified in Table 6.1 but were reviewed and revised, as necessary, by the CSIST.

## Slide 6
Title
3. Progress and current status (ii)
  Spreadsheet identified lead CEOS “Agency” as:
    AC-VC: 6 Actions
    LSI-VC: 4 Actions
    WGClimate: 7 Actions
    WGCV: 11 Actions
    SIT: 6 Actions
    N/A: 2 Actions
    ??: 1 Action

## Slide 7
Title
Status as of SIT Workshop
Draft spreadsheet completed at meeting of 28th July and subsequent revisions by email among CSIST
Identified 12 Actions that will require further discussion to implement
Discussions with some Carbon team members
Current spreadsheet circulated by CEO to SIT Workshop participants and CEOS SEC, along with report (KAS) and ToR of group
Several additional comments received 10 Sept from D Wickland, responded to separately by SAB but not included in current version (but comments and outcomes are manageable)
Further quick comments invited on content of spreadsheet
Discussion on way forward to Plenary.

## Slide 8
Title
Discussion and way forward
  Comments invited on spreadsheet content at/after Workshop
  Incorporate comments of D Wickland and any further comments before Plenary (not problematical(?))
  Need to propose way forward in terms of overall management/governance:
    Separate carbon group,
    WGClimate,
    SIT Chair
    Other?
  Agree proposed way forward at Workshop
  Make proposal to Plenary 2014 for Progress.
  Thank CSIST members for efforts to respond to task rapidly and effectively