## Slide 1: Climate Coordination for CEOS Response to GCOS SIT-25 Side Meeting
Mitch Goldberg, CEOS Climate Coordinator
Monday 12th April 2010
Tokyo, Japan

## Slide 2: Meeting Objectives
  1) Overall strategy discussion to develop the CEOS response to the new GCOS-IP. 2) Development of the timeline to provide updates to the CEOS Progress Report to SBSTA, which will include a section on the highlights of the new CEOS response. This is due September. 3) Development of the timeline to produce the final CEOS response document (Spring 2011??) The official GCOS IP does not come out until August 2010. 4) Report from each lead on status of development of new CEOS actions in response to the new GCOS IP actions.

## Slide 3: Two main tasks: Task 1
  CEOS Progress Report to UNFCCC SBSTA
    Provide highlights of CEOS climate actions, including 17 priority 2 actions which were started last year.
    Need to include Forest Carbon Tracking
    Include “movie trailer” of the new CEOS response
    First draft – June 30
    Internal review by CEOS – July 31
    Final draft for review August 31
    Sent to UNFCCC – September 30
Draft (for discussion)

## Slide 4: Task 2
  CEOS Response to new GCOS-IP
    CEOS provided final review comments to GCOS-IP Feb 2010.
    GCOS-IP released August 2010
    CEOS Response First Draft November 2010 (INPE)
    Second Draft January 2010 (CEOS planning meeting)
    Final Draft for CEOS Climate Advisory Group February 2010
    Release in May 2010 (CEOS SIT)
Draft (for discussion)

## Slide 5: CEOS response to GCOS
  CEOS climate actions responds to GCOS Implementation Plans (IP)
  GCOS IP provides the requirements for climate quality observations, products and cal/val.
  GCOS-92: GCOS IP released in 2004
  GCOS-107: 2005 GCOS Satellite Supplement contains the attributes associated with satellite-based climate products
  New GCOS IP for 2010.

## Slide 6
Two climate action paths
CEOS IP for GEOSS in 2007
GEOSS 10-year plan in 2005
CEOS response 2006
GCOS-107 in 2006
GCOS-92 in 2004
GCOS-82 in 2003

## Slide 7: CEOS 59 Climate Actions in response to GCOS-92 (IP2004) and GCOS-107 (satellite supplement)
  Action plan adopted by CEOS in Sep. 06
  Overall goals
    Ensuring continuity of climate-relevant satellite measurements (13 actions);
    Taking a systematic approach to generating fundamental climate data records (FCDRs) (11 actions);
    Preserving climate data records (4 actions);
    Ensuring access to climate data products (10 actions);
    Coordinating international communities and interaction with users (10 actions); and
    Addressing future measurement needs (11 actions).

## Slide 8: CEOS UNFCCC 2008 Report
  The status of the Priority 1 actions and plans for new tasks were detailed in the CEOS UNFCCC report.
  The updated progress report was presented to the UNFCCC Subsidiary Body on Scientific and Technological Advice (SBSTA) at its 29th session in December 2008.

## Slide 9: UNFCCC SBSTA Response
  Encourages CEOS to continue coordinating and supporting the implementation of the satellite component of the Global Climate Observing System;
  The SBSTA invited CEOS to report at its thirty-third session on progress made in its efforts to meet the relevant needs of the Convention.
  SBSTA also interested in terrestrial domain, particularly forest carbon tracking.

## Slide 10: Initiated Priority 2 Actions
  Initiated 17 CEOS-GCOS climate actions based on readiness and critical mass from CEOS in working these actions
  Need to report on the progress of these tasks in the progress report to SBSTA, due September 2010.

## Slide 11: Organizational groups where CEOS agencies are members
  GSICS
  SCOPE-CM
  CGMS
  WCRP
  International Working Groups
Need to capture these activities in CEOS Progress Report

## Slide 12: Future CEOS Response to GCOS Needs

## Slide 13: Satellite-based ECVs

## Slide 14: New CEOS Response to GCOS-IP 2010
  Good opportunity for a new CEOS response with actionable actions
  New actions can supersede the existing actions
  Use 2006 CEOS response as a template
  Estimate level of effort and completion time
  Begin with development of actionable actions

## Slide 15: Next Steps
  Identified domain leads (atmos, ocean, land)
  Assign working groups, constellations, and experts to develop actions responding to the GCOS IP10 actions.
  Action must be actionable with resources identified. (see following example)
  Groups need to reach into the expert community, including authors contributing to the original CEOS
  The CEOS Response will be made available for comments

## Slide 16: Domain Leads
  Atmosphere - Goldberg, Eckman, Zehner, Osamu, Wilson, Ector
  Ocean – Dowell, Digiacomo,Lindstrom, Wilson, Counet
  Terrestrial – Csiszar, Cecil, Holm
  Cal/Val – Stensass/Lecomte
  Data - Pakorn

## Slide 17: CEOS Virtual Constellations
CEOS Response supported by the 6 CEOS Virtual Constellations ..
  Precipitation
  Land Surface Imaging
  Atmospheric Composition
  Ocean Surface Topography
  Ocean Color
  Ocean Surface Vector Winds

## Slide 18: CEOS Working Groups Support to GCOS
  Working Group on Cal/Val
    GEO Data Quality Assurance Guideline document
    Antarctic Dome C calibration campaign
      verified Dome C as excellent satellite intercalibration and long term monitoring site,
      transfer SeaWiFS stable lunar calibration to AVHRR and other sensors at Dome C
  Working Group on Information Systems and Services
    Developing a portal for easy access to climate diagnostics
  Working Group on Education
    Workshops/training for data utilization

## Slide 20
A.2
A19
A-5

## Slide 27: A18 - Implement and evaluate a satellite climate calibration mission, e.g. CLARREO
  Point of Contact
  Contributors: NASA, NOAA, WGCV (Nigel Fox)
  Significance
  Current Status:
  Accuracy requirements (target (desired) and planned)
  CEOS Action with current and planned resources:
    Supersede any existing CEOS climate actions?
  CEOS Action with additional resources:
    Include significance of the shortfall without additional resources

## Slide 28: Next Steps
  Questions?
  Discussion
  Reports from domain leads