## Slide 1: First UNFCCC Global Stocktake (GST) Lessons Learned Study
Wenying Su, NASA
WGClimate Vice-Chair
Agenda Item 4.2
38th CEOS Plenary, Montreal, Canada
23rd-24th October 2024

## Slide 2: Climate Policy Impact
Climate policy impact is one of the JAXA SIT Chair term priorities
The objective is for CEOS to explore both the challenges and opportunities in maximizing the impact of CEOS agency data in the key climate policy processes (e.g., GST of the Paris Agreement)
With the GST1 behind us, it’s time to reflect on whether our current relationship and activities are optimal for enhanced uptake of CEOS agency data in future GSTs
At SIT-39 in Tokyo, the SIT Chair tasked Working Group on Climate (WGClimate) to lead a review, aiming to identify the lessons learned from our engagement in GST1.

## Slide 3: Lessons Learned are Categorized in Three Areas
Lessons Learned from inputs to the GST process, including GHG flux datasets and Research and Systematic Observation (RSO) synthesis report.
Lessons Learned from engagement with the UNFCCC (including COP) and key stakeholders.
Lessons learned from the existence of and need to address communication gaps

## Slide 4: Background on Inputs to the GST Process
The pilot atmospheric CO2 and CH4 budgets delivered to the first Global Stocktake (GST1) were well received at the UNFCCC COP in 2021 and 2022. These were presented at the Earth Information Day (virtually in 2021) and various national and inter-governmental events.
However, these top-down budgets were not widely utilized by the national inventory community to compile or validate inventories submitted to GST1.
In response to a direct request from the SBSTA, CEOS, in collaboration with the WMO and GEO, developed the report titled “The Role of Systematic Earth Observations in the Global Stocktake” in early 2022.
Despite the significance of space-based data, they currently play no formal role in key UNFCCC processes, such as national communications, biennial reports, transparency reports, NDCs, or adaptation communications required under the Paris Agreement.

## Slide 5: Lessons Learned from Inputs to the GST process
GHG flux datasets
  L1.1: Need to reconcile GHG estimates between top-down and bottom-up approaches and better quantify uncertainties in both methods.
  L1.2: Need to reduce the uncertainty in the top-down flux estimates for mid- and small-size countries.
RSO synthesis report
  L1.3: Decision not to include the RSO inputs was made by the COP delegations, as the RSO community did not have a single champion among the COP delegations.

## Slide 6: Lessons learned from Engagement with UNFCCC (incl. COP) and Stakeholders
L2.1: UNFCCC is the facilitator in the GST process and the COP delegations are the decision makers.
L2.2: Need to engage national inventory communities/compilers when developing the flux products.
L2.3: CEOS worked very closely with UNFCCC points-of-contact who were strong advocates for the RSO community for the first GST, but did not have a close link with COP delegations to foster champions who can advocate for the RSO community.

## Slide 7: Lessons Learned to Address Communication Gaps
L3.1: The GST process is still evolving and not fully understood, requiring close collaboration with the UNFCCC to stay informed.
L3.2: National inventory compilers lack a full understanding of the top-down flux datasets and how to integrate them with the bottom-up data.
L3.3: COP delegations are not fully aware of the capabilities of space-based observations.

## Slide 8: Recommendations to Improve GHG Products for Science Application
R1: Improve uncertainty evaluation in both top-down and bottom-up emission estimates and reconcile these approaches for a more accurate GHG budget (L1.1).
R2: Develop higher spatial resolution atmospheric inverse models to better utilize space-based GHG estimates and provide flux data at finer resolution to increase the utility of these data for mid- and small-size countries (L1.2).
R3: Operationalize the GHG monitoring system to sustain the long-term availability of GHG products and services, providing policy-relevant information (L1.1 and L1.2).

## Slide 9: Recommendations for GHG Product Development and User Engagement
R4: CEOS and CGMS agencies to co-develop GHG flux products and emission information with national inventory agencies/compilers and other users. This will increase the uptake of satellite data to meet the IPCC 2006 guidelines for bottom-up inventory development and validation (L2.2).
R5: CEOS and CGMS agencies to identify and collaborate with early adopters to demonstrate the value of space-based data, and to start a set of dedicated projects with national inventory compilers to promote satellite data integration(L2.2).
R6: Through WGClimate and WGCapD, CEOS and CGMS to develop training materials and step-by-step guidance for national inventory communities on utilizing top-down flux products to support the bottom-up inventory development and validation, fostering advocates for top-down approach (L3.2).

## Slide 10: Recommendations to enhance the uptake of space-based observation for future GSTs
R7: CEOS and CGMS agencies to consider engaging directly with national inventory compilers, COP delegations, and the UNFCCC to contribute GHG and AFOLU products for the Information Collection phase (2026-2027). Additionally, they should work to cultivate champions within these communities to represent RSO products during the Technical Assessment for GST2 (2027-2028). (L2.1, L2.3).

## Slide 11: Recommendation on Addressing Communication Gaps
R8: CEOS and CGMS to clearly communicate the benefits of space-based GHG data to the inventory community, highlighting their role in providing top-down quality assurance for assessing collective progress and supporting the Enhanced Transparency Framework (L3.2).
R9: CEOS and CGMS to emphasize the value of space-based GHG and AFOLU products in supporting national mitigation and adaption goals to national COP delegations, foster advocates for the RSO community at the decision-making level (L2.3 and L3.3).
R10: CEOS and CGMS will identify space-based products that support GST adaptation and mitigation objectives and develop presentation and capacity-building materials that highlight the role of space-based observations in achieving the Paris Agreement objectives.(L3.2 and L3.3).

## Slide 12: Recommendations on UNFCCC Engagement and Collaboration within RSO
R11: WGClimate should establish a formal relationship and communication channel with the UNFCCC, designating the CEOS-CGMS WGClimate chair as the primary point of contact. (L3.1)
WGClimate should contribute to the themes and agendas of UNFCCC COP and SBSTA events in collaboration with organizations like WMO and GCOS.
Request two badges from the UNFCCC to ensure annual attendance of WGClimate leadership at key events, such as Earth Information Day at COPs and the Bonn Climate Change Conference.
R12: CEOS, alongside organizations like CGMS, WMO, GCOS, UNEP, GOOS, and IOC, to consider a unified process for representing the RSO community at COP/SBSTA events
WGClimate is invited to participate in the WMO Climate Policy Advisors (CPA), chaired by Mr. Carlos Fuller (SBSTA chair in 2017-2018).
WGClimate and its GHG TT to collaborate with WMO G3W to provide inputs and presentations on GHG at UNFCCC meetings and events.

## Slide 13: Recommendations for Engagement with Other Organizations
R13: CEOS and CGMS to establish and maintain relationships with IPCC. CEOS agencies to nominate scientists from the GHG TT and the AFOLU team to serve as the Coordinating Lead Authors, Lead Authors, and Review Editors for the IPCC AR7 (L2.3).
R14: CEOS and CGMS to develop a long-term strategy to engage with the IPCC Task Force on National GHG Inventories and provide input into the anticipated next update of the National GHG Inventory Guidelines to optimize EO representation (L2.2).
R15: CEOS and CGMS to foster a closer collaboration among the GHG TT, AFOLU Team, and the Global Carbon Project to produce comprehensive national flux products and advocate for their inclusion in future GSTs (L2.2).

## Slide 14: Summary and Request
Summary
The lessons learned from GST1 were categorized into three key areas, accompanied by recommendations aimed at improving the integration of EO data in future GSTs.
Request
We invite your feedback on these lessons learned and recommendations.
If any of these recommendations have already been implemented within your program, we would appreciate it if you could share the outcomes with us.