## Slide 1: LSI-VC-3 Action Status
Matthew Steventon
LSI-VC-4
6th September 2017
Committee on Earth Observation Satellites

## Slide 2
25 Actions, 17 Complete
1 in progress, 2 stalled, 2 on hold, 3 to be progressed at LSI-VC-4/SIT TW
LSI-VC-3 Actions

## Slide 3
In progress
LSI-VC-3 Actions
LSI-VC-3-16 | Paul Briand to explore the possibility of sharing a new Canadian SAR flood mapping algorithm with Brian Killough, in support of the Vietnam Data Cube pilot. | IN PROGRESS

## Slide 4
Stalled
LSI-VC-3 Actions
LSI-VC-3-07 | Bimal Bhattacharya to share coverage maps that summarise the quantity and location of available AWiFS data. Jenn Lacey to share any related information obtained by USGS. | April 2017 Jenn has shared USGS information via email. Matt has sent emails to Bimal seeking an update.
LSI-VC-3-23 | Mark Dowell to reach out to GEO regarding having GEO Carbon and GHG Initiative experts fill out any carbon requirements template supplied by LSI-VC/CEOS. | May 2017

## Slide 5
On hold
LSI-VC-3 Actions
LSI-VC-3-01 | Jenn Lacey to coordinate LSI-VC mission timelines with the CEOS MIM Database team. | ON HOLD
LSI-VC-3-22 | CEOS SEO to look at the terrestrial chapter of the CEOS Strategy for Carbon Observations from Space, constrain the rows currently in the requirements matrix, and assess what high-level requirements exist. Mark Dowell to reach out to Stephen Plummer for guidance. | ON HOLD

## Slide 6
To be progressed at LSI-VC-4/SIT TW
LSI-VC-3 Actions
LSI-VC-3-04 | Jonathon Ross and Adam Lewis to revise the CARD4L definition wording around ‘atmospheric correction directional scattering’. | July 2017 Brian clarified that this is related to BRDF, noting that there’s an open discussion around whether BRDF fits under ‘threshold’ or ‘target’ ARD.
LSI-VC-3-13 | Adam Lewis to work with the FDA-AHT at the 2017 SIT Technical Workshop (September) to ensure that lessons learned from the FDA Pilots are fed back into the work of the LSI-VC (i.e., in the areas of CARD4L and MRI). | 2017 SIT Technical Workshop
LSI-VC-3-19 | Paul Briand to share some Canadian examples of work done with the private sector to release down-sampled/higher-level products derived from commercial datasets. | IN PROGRESS
Notes: 10, 2