## Slide 1: LSI-VC Action Status
5 September 2018
Joint Research Centre, Ispra (Italy)

## Slide 2: LSI-VC-5 Actions
LSI-VC-6
26 actions.
22 actions completed, including those being closed out at LSI-VC-6.
Actions that will be closed as of LSI-VC-6 are related to the trial assessment and production of CARD4L, as well as new SAR PFS.

## Slide 3: Actions Requiring Closing
LSI-VC-5-02 | Shin-ichi Sobue, Stephen Ward, Jonathon Ross, and Brian Killough to explore alternative options for ALOS data processing. | LSI-VC-6
Delegated to Ake and Brian at the last teleconference?
LSI-VC-6

## Slide 4: Actions Requiring Closing
LSI-VC-5-19 | Jonathon Ross to follow up with Dave Hudson regarding identification of a Chinese LSI-VC contact. | March
LSI-VC-6

## Slide 5: Actions Requiring Closing
LSI-VC-5-21 | Brian to follow up with Jeff Masek regarding the specifics of the HLS dataset interpolation. | ONGOING
The word ‘interpolation’ is not correct, however Jeff and Brian are following up regarding whether there is a way to package the processing steps associated with generating a HLS product, such that it could be integrated into the Data Cube work flow.
LSI-VC-6

## Slide 6: Actions Requiring Closing
LSI-VC-5-24 | Alyssa and Brian to discuss improvements to COVE that would aid gap analyses. | ONGOING
Brian is broadly progressing this action through various CEOS tool related discussions with Alyssa, the COVE team, George Dyke (MIM DB), and Dave Jarrett.
LSI-VC-6