## Slide 1: Maturity Index and ESA CCI programme
WGClimate #2
NOAA Asheville
Wednesday April 18th, 2012.

## Slide 2: CCI Status April 2012
`2012
`2010
`2011
`2013
requirements
algo dev, inter-comp, selection
system & product proto-typing
product validation & User assessment
Operational system specification
Phase 1
Phase 2
Notes: This is the schedule of the first set of 10 projects. The last 3 are delayed by 18 months.
The product validation and User assessment task will be an opportunity to address for the first time the ECV Maturity Index for each ECV independently.
An activity similar to the one ran by S. Bojinsky for the User Requirements in 2011 will be performed for the Comprehensive Error Characterisation Report in 2012-2013.
Part of the results of this activity will be summarised in the form of Maturity Index.
The next slides are just expressing this idea.
The concept of “Developing a Consensus Maturity Matrix” Exercise is a good idea.
The CCI is a good opportunity to run such an exercise on a larger scale (i.e. larger than a single product), and also to run it on a variety of ECVs.
This exercise implies the development of methods to assess the quality and the consistency across the ECVs.
This is probably not a simple concept. We shall see how it works and progress along these concepts step by step.
There will be a lot to discuss and share along that process.
<number>

## Slide 3: CCI Schedule
The CCI Programme is finalising the prototype system to produce the first set of ECV products
The purpose of these products is to demonstrate that the implementation of the selected algorithms are compliant with the objectives.
These products are then fed into the Product Validation and Assessment task.
It is as part of that task that a first Maturity Index evaluation will be produced.
A Research Fellow will start at the ESA Climate Office on September 1st, 2012 to address, across the CCI programme, issues related to:
  Error Characterisation
  Data Assimilation Method to assess ECV quality and inter-consistency.
  Maturity Index.
Notes: <number>

## Slide 4: CCI Phase 2
One of the objectives of Phase 2:
  Extension of ECV data sets to generate the most complete ECV to tackle key science challenges:
    Processing of complete data sets, in time with science need
    Flexibility to allow algorithm upgrades and rapid reprocessing
  This objectives include the ECV production but also the demonstration that this ECV can be use to tackle key science challenges.
    That implies a proper assessment of its quality  Maturity Index
The CCI shall be an example of an exercise to
Develop a consensus maturity matrix
Notes: <number>

## Slide 5: Consensus Maturity Matrix
The CCI shall be an example of an exercise to
Develop a consensus maturity matrix
By the end of 2013 (end of CCI Phase 1), we should have a first example spanning across at least 10 of the 13 CCI projects.
The exercise will be repeated and reviewed during CCI Phase 2 (2013 – 2016)
Notes: In practice, I propose to
<number>