## Slide 1: The ESA CCI programme
WGClimate #2
NOAA Asheville
Wednesday April 18th, 2012.

## Slide 2: CCI Project Teams
ECV | Science Leader
cloud_cci | DWD
ozone_cci | BIRA
aerosol_cci | DLR/FMI
ghg_cci | U Bremen
sst_cci | U Edinburgh
Land_cover_cci | UCL
Sea_level_cc | CLS
Ocean_colour_cci | PML
glaciers_cci | U. Zurich
fire _cci | U.Alcala
CMUG | UKmetO - Hadley Centre
Notes: 10 projects were started between July and November 2010.
One proposal on Sea_Ice_cci was considered as not acceptable and was re-opened mid 2011 (next slide).
All these projects were called in an opened tender competition.
The CMUG (Climate Modelers User Group) was the only one in Direct negotiation and was kicked-off earlier (April 2010).
<number>

## Slide 3: CCI Project Teams
ECV | Science Leader
Sea_Ice_cci | NERSC
Soil_Moisture_cci | TU Wien
Ice_Sheet_cci | DTU Space
Notes: These three new projects were kicked-off in January 2012.
Sea_Ice_cci and Ice_Sheet_cci are part of the first set of ECV.
Sea_Ice was initially considered as not acceptable.
According to GCOS 107, there was no real distinction between Glaciers and Ice_Sheets and the first call for tender in 2009 was titled “Glaciers and Ice Caps”.
It became clear the we were talking about two different projects and the initial call was focused on Glaciers only. Thus the second call for Ice_Sheet as a specific project.
This is coherent with GCOS 147.
From the logical point of view, the only “new” project is Soil_Moisture_cci.
This is linked to a particular interest from Austria.
<number>

## Slide 4: CCI Status March 2012
`2012
`2010
`2011
`2013
requirements
algo dev, inter-comp, selection
system & product proto-typing
product validation & User assessment
Operational system specification
Phase 1
Phase 2
Notes: This is the schedule of the first set of projects.
The three new projects have a 18-month delay with respect to this schedule.
There is no plan to recover this 18-month delay even if it is clear that the new projects take benefit of the existing results.
ESA is for example pointing the new projects to existing results in similar projects to make the new projects more efficient.
<number>

## Slide 5: In the First 12 months
The 10 CCI user requirements documents have been completed and put on the web
  Based on these input, an ESA CCI response to GCOS has been published
The Data Requirements have been finalized and a delivery plan for ESA data is being prepared.
The CCI teams prepared first versions of their ECV product specifications
  On the same principle as the URD analysis, a Consolidated Product Specification Document will be produced.
First ECV Collocation Meeting: September 15th to 14th, 2010, ESRIN
CMUG convened a first meeting of climate scientists from all CCI teams (March 14th to 16th, 2011)

## Slide 6: In the more recent months
CCI teams provided inputs for the update and review of GCOS Satellite Supplement – open review
The ESA Executive pursued European coordination on climate with EUMETSAT & EC.
The ESA Executive will contribute actively and channel CCI output to CEOS WGClimate (first WGClimate held on May 26th and 27th, 2011
The ITT for three new ECVs have been issued and successfully awarded.
Second ECV Collocation Meeting: October 12th to 14th, 2011, ESRIN
  Including the participation of the Sea_ice_cci, the Soil_moisture_cci and the Ice_sheet_cci

## Slide 7: Ongoing activities
Preparation of the Consolidated Product Specification Document
Initiate work on the System Engineering Aspect of the CCI
Preparation of the Phase 2 Statement of Work
Initiate thoughts on the CCI Science Agenda
CCI Web site: www.esa-cci.org

## Slide 8: CCI Phase 2
2010
2011
2012
2013
2014
2015
2016
2009
Phase 2
ITT
ITT
ITT
ITT
Phase 1
3
1
2
collocation
mid-term programme review

## Slide 9: Phase 2 Team Role
The CCI shall remain Science driven
  The lead of each project is the Science Leader.
    The Science Leader shall be an internationally recognised expert from the EO science community with a proven track record on research activities relevant for the concerned ECV and with expertise in coordinating large scale research projects involving generation of long time series data products relevant to the ECV concerned. The Science Leader shall contribute to the Programme through the Science Impact Working Group
    The Science Leader of each ECV is the interface to ESA for all issues. They shall be responsible for setting up the project in a manner that facilitates interaction, exchange and coordination with the objective to contribute to resolving specific science needs.
  The Science Leader is supported by the Project Manager.
    The Project Manager provides support in the overall management of the project and ensures that all tasks are executed in a coherent, consistent and efficient manner. They shall have a proven track record on managing large scale international projects and an understanding of the scientific issues being tackled in the project.

## Slide 10: Phase 2 Team Role
The EO Science, Climate Research and System Engineering Teams provide support to the Science Leader
  The EO Science Team
    The EO Science Team shall comprise key experts who are at the forefront of developing methodologies and next generation algorithms required for generating high quality climate relevant data sets, have already developed, demonstrated and validated pre-cursor systems and will orient their future research activities to support the CCI initiative. They shall contribute to the Data Standards Working Group to ensure data harmonisation and product consistency.
  The Climate Research Group
    Internationally recognized experts involved in understanding climate dynamics specifically related to the concerned ECV will be a central part of the team. They will contribute to the realising programme objectives through the Climate Research Working Group and shall actively participate in major data-model inter-comparison exercises.
  The System Engineering Team
    The System Engineer(s) shall have previous expertise in development of large EO data processing and product delivery systems driven by scientific need. Systems development shall emphasise high scientific quality, flexibility and modularity to allow rapid reprocessing and algorithmic updating. Knowledge of the latest related technologies like GRID or CLOUD computing is an asset. Members of the team will contribute to the System Engineering Working Group

## Slide 11: Phase 2 focal points
Product generation
  Extension of ECV data sets to generate the most complete ECV to tackle key science challenges:
    Processing of complete data sets, in time with science need
    Flexibility to allow algorithm upgrades and rapid reprocessing
System development
  Development of the Operational System for ECV Production,
    Modular system designs to allow for new instruments (ESA and/or Third Party) to be introduced with minimum further investment
    Exploitation of new technologies e.g. GRID, CLOUD focusing on minimising in particular data transfers
    Systematic production of ECVs with capacity for rapid reprocessing, algorithm updating (modularity and flexibility),
  Post-CCI operational considerations with emphasis on delivery to science requirements/communities