## Slide 1: Schedule for Space Agency Response to GCOS IP
Pascal Lecomte - WGClimate Chair
March 9th, 2016

## Slide 2: Timeline for the GCOS Implementation Plan
Preparatory work in 2013 – 2015 (GCOS panel meetings and three workshops with GFCS/UNFCCC/IPCC; Publication of Status Report)
15 November 2015 Draft Table of Contents submitted to COP21
2-4 February 2016 First Writing Team meeting, JRC, Italy
2-4 March 2016 Open GCOS Conference
April 2016 Bring work in progress to GCOS panel meetings
24-26 May 2016 Second Writing Team meeting, JRC, Italy
July 2016 Public review (6 weeks)
September 2016 Final version prepared in light of comments on the draft
September 2016 Final Version submitted to GCOS SC-24
October 2016 Final plan submitted to COP22

## Slide 3: WGClimate response to GCOS Implementation Plan
2-4 March 2016
7-9 March 2016
24-26 May 2016
July 2016
September 2016
February 2017 – WGClimate #7
July 2017 – WGClimae #8
November 2017
Open GCOS Conference
WGClimate #6
2nd Writing Team meeting
IP Public review (6 weeks)
Preparation for the Space Agency response
IP Final Version
1st meeting of the Writing Team
2nd meeting of the Writing Team
Space Agency Response