## 2020
Number | Source/ Origin | Related Action | Category | Description | Actionees | Due Date | Status | Comments
2019-01 | Interop Tiger Team Meeting | WGISS-48-08 | Data Interoperability and Use | Chris Lynnes (lead) and Rob Woodcock to convert the notes from discussion below into 2-4 paragraphs each of definitions and circulate early next week to the Interoper Tiger Team. | Chris Lynnes and Rob Woodcock | 2019-12-16 | Closed
2019-02 | Interop Tiger Team Meeting | WGISS-48-08 | Data Interoperability and Use | Interop Team to provide feedback on these drafts by Thursday 9am Canberra time (AEDT) Thursday 19 to Rob Woodcock. | Interop Team | 2019-12-19 | Closed
2019-03 | Interop Tiger Team Meeting | WGISS-48-08 | Data Interoperability and Use | Rob Woodcock to collate responses and table the final draft for WGISS Exec meeting Thursday 19th. | Rob Woodcock | 2019-12-19 | Closed
2019-04 | Interop Tiger Team Meeting | WGISS-48-08 | Data Interoperability and Use | Assuming the response is agreeable to WGISS Exec it will be sent to LSI VC for consideration. | Rob Woodcock | 2019-12-19 | Closed
2019-05 | Interop Tiger Team Meeting | WGISS-48-08 | Data Interoperability and Use | It was noted that the 5 terms discussed are topics for further expansion in the Data Cube interoperability and FDA-08 technical notes and work program. It was decided not to task this work until the New Year since there is enough work to complete at this time and Christmas and New Year break is about to occur. | Interop Team | Q1-2020 | In progress | Apr 2020: Worthy of one more revision. Rob will re-send
Exec 2019-10-1 | Exec 2019 |  | WGISS 49 Planning | Michelle to ask Homero for guidance in inviting potential participants from South America. | Michelle Piepgrass |  | Closed
Exec 2019-10-2 | Exec 2019 |  | WGISS 49 Planning | Yonsook to contact AmeriGEOSS, Rob to contact Doug Cripe to link to AfriGEOSS and Mirko to contact EuroGEOSS regarding participation in WGISS-49. | Robert Woodcock |  | Closed
Exec 2019-10-3 | Exec 2019 |  | WGISS 49 Planning | Rob to discuss with Doug Cripe any participation with the Infrastructure Dev Task Team. | Robert Woodcock |  | Closed
Exec 2019-10-4 | Exec 2019 |  | WGISS 49 Planning | Michelle to contact Homero and Lubia about seeking participation from the regional AmeriGEOSS. | Michelle Piepgrass |  | Closed
Exec 2019-10-5 | Exec 2019 |  | WGISS 49 Planning | Rob and Chris to refine the statement on what Technology Interest Group will present (agenda details), and maybe reach out to LSI VC on ARD ecosystem. This touches WGCV as well. | Robert Woodcock |  | Closed
Exec 2019-10-6 | Exec 2019 |  | WGISS 49 Planning | Michelle to contact Nancy Searby to see if WGCapD people at CONAE may like to participate. | Michelle Piepgrass |  | Closed
Exec 2019-10-7 | Exec 2019 |  | Working Groups Cooperation | Rob to contact Nancy Searby about being the PoC for WGISS for participation in regular inter-sessional teleconferences led by NOAA, starting discussions to establish an expert group on cloud services interoperability. Also notify Vanessa Griffin and Klaus-Peter Renner. | Robert Woodcock |  | Closed
Exec 2020-01-1 | Exec 2020 |  | General | Robert Woodcock to invite members to take the role of Technology Exploration Interest Group co-lead (with Yousuke Ikehata, JAXA). | Robert Woodcock |  | Closed
Exec 2020-01-2 | Exec 2020 |  | General | Rob Woodcock to solicit a WGISS representative to support the CEOS-COAST initiative. | Robert Woodcock |  | Closed
Exec 2020-01-3 | Exec 2020 |  |  | Chris to develop a collection template for the Jupyter Notebooks activity, and contact Nancy Ritchey and Kenton Ross for input. | Chris Lynnes |  | Closed
Exec 2020-01-4 | Exec 2020 |  | WGISS 50 Planning | Mirko to put Makoto in contact with Tamara Ganina (ROSCOSMOS) for WGISS-50 planning. | Mirko Albani |  | Closed
Exec 2020-01-5 | Exec 2020 |  | WGISS 49 Planning | Michelle to contact the CEOS working group leads about their sessions, and also the SDG Adhoc team, the SEO, CEO, and GEO-SEC. | Michelle Piepgrass |  | Closed
WGISS-47-01 | WGISS-47 |  | General | Michelle Piepgrass to finalise and post the WGISS organizational structure chart | Michelle Piepgrass | 2019-05-20 | Closed
WGISS-47-02 | WGISS-47 |  | General | Iolanda Maggio to update the WGISS Work Plan based on the CEOS Work Plan 2019-2021 | Iolanda Maggio | 2019-06-15 | Closed | July 17: The file has been circulated
WGISS-47-03 | WGISS-47 |  | General | Michelle Piepgrass to contact Cindy Ong to obtain the BP and Guidelines for WGCV | Michelle Piepgrass | 2019-05-31 | Closed
WGISS-47-04 | WGISS-47 |  | General | Mirko Albani to request SIT Chair Team to include a WGISS representative to the CEOS Study Team on WGs | Mirko Albani | 2019-05-20 | Closed
WGISS-47-05 | WGISS-47 |  | General | Mirko Albani and Robert Woodcock to provide SIT Chair Team with the name of WGISS representative for the GEO Implementation Task Force to be proposed to GEO Secretariat | Mirko Albani | 2019-05-20 | Closed
WGISS-47-06 | WGISS-47 |  | Data Discovery and Access | Iolanda Maggio to complete the Google Dataset Search Tool CEOS report using input from NASA/ESA/DLR/NOAA | Iolanda Maggio | 2019-06-30 | Closed | June 6: Iolanda is finalizing the document and will see if USGS has anything to add. July 17: the document has been circulated and input requested to NOAA and USGS August 20: New input received from STFC. The white paper will be updated also adding the agencies report as annexes. September 24: The white paper was finalized and circulated to WGISS all.
WGISS-47-07 | WGISS-47 |  | Working Groups Cooperation | WGISS-Exec to follow-up GEO Work Plan preparation and identify where WGISS can contribute with • Data Management Principles (DSIG) • WGISS Connected Data Access • Future Data Architectures | WGISS-Exec | 2019-06-30 | Closed | July 17: DMP WG will be merged with Data Sharing WG and included in Foundational Task “GEOSS Data, Information and Knowledge”. Review of latest version and definition of possible contribution from WGISS is ongoing (WGISS Chair). August 20: still ongoing September 18: WGISS will contribute with DMP. Ad-hoc calls are being followed by DSIG team. They have accepted to change the wording such that we can contribute.
WGISS-47-08 | WGISS-47 | FDA-08 |  | Robert Woodcock to define next steps and schedule for FDA-08 White paper | Robert Woodcock | 2019-05-20 | Closed | June 6: Iolanda is finalizing the document and will see if USGS has anything to add. July 17: the document has been circulated and input requested to NOAA and USGS August 20: New input received from STFC. The white paper will be updated also adding the agencies report as annexes. September 18: The white paper will be finalized and circulated to WGISS all by the end of next week. Oct. 11: Superseded by new action WGISS-48.
WGISS-47-09 | WGISS-47 | FDA-09 |  | Mirko Albani and Iolanda Maggio to complete FDA-09 Inventory deliverable. | Mirko Albani | 2019-07-31 | Closed | June 6: the team is investigating different platforms. Final document will be issued by end of July. August 20: still ongoing September 18: dedicated presentation during WGISS-48 meeting.
WGISS-47-10 | WGISS-47 |  |  | ESA to present progress of DCFS Data Cube at next WGISS | ESA | WGISS-48 | Closed
WGISS-47-11 | WGISS-47 |  |  | Ad-hoc team led by Valerie Dixon (Michael Morahan, Andrea Della Vecchia, Chris Lynnes, Cristiano Lopes, Richard Moreno) to define proposal for metadata model for services addressing a set of high priority use cases. Proposed model to be circulated to WGISS-all for review and approval | Ad-hoc team | 2019-07-31 | Closed | June 6: Valerie noted a good deal of analysis and a path forward to a back-end integrated service model, and further work needed for the front-end model. The team is on track to have an updated UMM out for review by end of June. July 17: SLT start reviewing UMM-S and Yves Coene shared OGC TB-15 report
WGISS-47-12 | WGISS-47 |  | Data Discovery and Access | Michael Morahan to register services/tools from inventory tables (FDA elements and SW/tools) into IDN starting from the ones presented at WGISS-47 | Michael Morahan | WGISS-50 | Closed | June 6: Iolanda will send the last version to Michael Morahan soon. July 17: The files have been sent Oct 9: Waiting until the UMMT Nov 12: The model will not be done till early next year. Dec 19: Under consideration; Michael will see if there is software attached to this. Jan 38: The UMM-Tools work at NASA is on hold while the UMM variable is being worked. Therefore, better to close this action and then reopen this next year if this is still needed.
WGISS-47-13 | WGISS-47 |  |  | Andrea Della Vecchia and Robert Woodcock to define with SEO a roadmap and short term activities on interoperability between ODC / HMDC / DCFS Data Cubes (e.g. Jupyter notebooks with XArray API and WCS / WPS) | Andrea Della |  | Closed | June 6: Iolanda will send the last version to Michael Morahan soon. July 17: The files have been sent Oct 9: Waiting until the UMMT Nov 12: The model will not be done till early next year.
WGISS-47-14 | WGISS-47 |  |  | Cristiano Lopes to inform WGISS-Exec about outcomes of ongoing OGC standardisation activities (including OGC test-beds) and ask for any additional support as needed | Cristiano Lopes | WGISS-48 | Closed | June 6: Cristiano will have more information after the OGC meeting. Need to ponder how to make this more collaborative and engage more audiences, perhaps incorporating into Tech Expo. Oct 11: presentation at WGISS-48.
WGISS-47-15 | WGISS-47 |  |  | Andrea Della Vecchia and Robert Woodcock to define with WGCV colleagues (Medhavy Thankappan, Phillipe Goryl, and Cindy Ong) coordinated roadmap and short term activities on WGISS-WGCV Data Cubes (ESA and ODC DEA) and possibly demo to be shown at SIT TW in September 2019 |  | 2019-06-30 | Closed | June 6: Rob will follow up with Cindy and Medhavy. Aug 20: Rob met with Medhavy, who suggests revising one of the actions. This will be discussed with Mirko and Cindy.
WGISS-47-16 | WGISS-47 |  |  | Robert Woodcock to liaise with AquaWatch representatives to gather their requirements/needs and further define how WGISS could support. | Robert Woodcock | 2019-06-30 | Closed | Oct 11: Rob will discuss with the leads of CARD4L. Nov 12: Rob will meet with them this week to see how they can engage. WGISS could be a liaison, but the activity will be under LSI. Dec 19: Can be closed.
WGISS-47-17 | WGISS-47 |  |  | WGISS CDA System Level Team (SLT) to | CDA-SLT |  | Closed
WGISS-47-17a | WGISS-47 |  | Data Discovery and Access | Identify the best approach to implement a single map-based front-end/portal within the IDN to discover and access CEOS agencies data through WGISS CDA back-end. Agree on way-forward with WGISS-Exec. Due by June 30, 2019. |  | 2019-06-30 | Closed | July 17: Discussion on this topic during the SLT meeting.
WGISS-47-17b | WGISS-47 |  | Data Discovery and Access | Start Actions as agreed (e.g. implement CEOS branding on IDN portal and underlying FedEO and CWIC when appearing for second step searches, etc.) Due by December 31, 2019. |  | 2019-12-31 | Closed | uly 17: CWIC has been branded with CEOS, and the same has been requested from FedEO. Michael will demonstrate this at WGISS-48. Nov 12: Progress continues. Dec 19: FedEO landing page branded CEOS (http://geo.spacebel.be/opensearch/readme.html ), TTO ongoing on https://fedeo.esa.int/opensearch/readme.html Jan 28: Completed; action can be closed
WGISS-47-17c | WGISS-47 |  | Data Discovery and Access | Assess advantages and feasibility to implement (part of) CEOS Data Usage Metrics in the IDN portal / WGISS Connected Data Assets. Due by December 31, 2019. |  | 2019-12-31 | Closed | July 17: The NASA EarthData Search Tool will be used. Searches will be the same, but the interface will be quite different. Nov 12: There will be a beta version of the new IDN client and next year it will be possible to gather some metrics. Dec 19: Part of this has already been implemented and the assessment is done. Next steps are to discover hat common metrics can be implemented? Can be closed.
WGISS-47-18 | WGISS-47 |  |  | Chris Lynnes, Yousuke Ikehata and Kent Ross to organise a webinar in September focusing on existing (pre)operational Exploitation and Application Platforms targeting the academic community. Following webinars should target the new developing countries on the same topics | Chris Lynnes | 2019-09-30 | Closed | June 6: Chris is looking to Rob to lead one or two webinars and proposes first week in September and Rob agreed. Chris will begin the planning. Sept 9: Webinar occurred.
WGISS-47-19 | WGISS-47 |  |  | Iolanda Maggio and Andrew Cherry finalise SW Inventory database tool, present to WGISS-Exec and publish on CEOS website | Iolanda Maggio | 2019-07-31 | Closed | July 17: the teams are in contact to finalise it and to implement a prototype for the FDA element as well August 20: meeting scheduled in this week. September 18: Dedicated presentation and final demo at WGISS-48 meeting (the technical decision seems to be to have one server for both inventories to reduce the impact of security internal audit) Oct 11: Mirko and Iolanda will contact to Brian Killough. Nov 12: Awaiting feedback from CEO, SEO, and Kerry Sawyer. Jan 28: Mirko will contact Kerry Sawyer, interim CEO. Feb 3: Both inventories are in the following web page: http://ceos.org/data-tools/
WGISS-47-20 | WGISS-47 | CARB-15 |  | Liping Di and Kenneth Casey to confirm EXEC of closure of Action CARB-15 (i.e. when next version of Carbon portal is available online) | Liping Di |  | Closed | Aug 20: The new version is online
WGISS-47-21 | WGISS-47 |  |  | Marco Leonardi to circulate first version of SSO White Paper to WGISS-all for review and comments | Marco Leonardi | 2019-05-31 | Closed | June 6: Document circulated to WGISS-All June 2, 2019. July: Feedback from DLR received.
WGISS-47-22 | WGISS-47 |  |  | David Borges to share with WGISS the WGDisasters Generic RO white paper when it becomes available, to identify any integration opportunities where WGISS could support WGDisasters Generic RO technical requirements | David Borges |  | Closed | July 17: paper being finalized. Aug 28: WGDisasters Generic Recovery Observatory White Paper distributed.
WGISS-47-23 | WGISS-47 |  |  | Chris Lynnes to provide a more nuanced version of the “Entities and Connections” for the GEO Knowledge Hub by July 31, 2019 | Chris Lynnes | 2019-07-31 | Closed | June 6: Rob will determine where GEO is in connection to this action, and see if Simon Cox is interested.
WGISS-47-24 | WGISS-47 |  |  | Mirko Albani to distribute to WGISS the draft version of the GEO Work Plan by May 20, 2019 | Mirko Albani | 2019-05-20 | Closed
WGISS-47-25 | WGISS-47 |  |  | Andrea Della Vecchia to put together a guide (e.g. video, short doc, demo) on the use of SKOS interface and tool by July 31, 2019 | Andrea Della Vecchia | 2019-07-31 | Closed | July 17: The guide has been circulated
WGISS-47-26a | WGISS-47 |  |  | Iolanda Maggio to liaise with Ge Peng to find out when the WMO documents on stewardship are approved by October 31, 2019 | Iolanda Maggio | 2019-10-31 | Closed | July 17: This effort is ongoing. August 20: still ongoing September 18: ongoing Nov 12: Iolanda is reviewing the WMO documents. Dec 19: Comments to WMO Maturity Matrix prepared and after a final review with WGCV the input will be sent to Ge Peng. Feb 28: The decision will be presented at WGISS-49. Action can be closed.
WGISS-47-26b | WGISS-47 |  | Data Preservation and Stewardship | Iolanda Maggio to liaise with WGCV to collect comments on WGISS and WMO maturity matrices (once the WMO documents are approved) by December 31, 2019 | Iolanda Maggio | 2019-12-31 | Closed | July 17: Awaiting feedback from WGCV. August 20: still ongoing September 18: first meeting held with ESA quality team and a dedicated presentation at WGISS-48 meeting. Nov 12: Iolanda will be meeting with WGCV end of November. Dec 19: Input from WGCV integrated in DMS-MM together with the FAIR indicators. A dedicated presentation at next WGISS meeting will be organised. Action can be closed after adding to the WGISS-49 agenda. Feb 28: Action can be closed.
WGISS-47-27 | WGISS-47 |  | Data Preservation and Stewardship | Iolanda Maggio to define way forward for finalization of WGISS Maturity Matrix using WMO matrix and RDA-FAIR WG results; finalise input for DMP by June 30, 2019 | Iolanda Maggio | 2019-06-30 | Closed | July 17: The proposal has been finalized and it will be presented at WGISS-48. Oct 11: Superseded by new action (WGISS-48).
WGISS-47-28 | WGISS-47 |  |  | Mirko Albani to send to Liping Di a packet of slides describing CEOS/WGISS for presentation at the ISO 48th Plenary by May 31, 2019 | Mirko Albani | 2019-05-31 | Closed
WGISS-47-29 | WGISS-47 |  | Data Discovery and Access | CDA SLT to analyse what kind of effort and solution can be accomplished by WGISS to automate future ECV Inventory updates [last slide of presentation] | CDA SLT | Q3 2020 | Closed | Nov 12: Mirko confirmed that all the ECVs are in the structure. The next step is to work with WGClimate. Dec 19: Awaiting feedback. Mar 19: The activities for the registration of collections have been completed respectively on IDN and FedEO. IDN has raised only one problem and reported to the data owner whether FedEO managed to validate all the collections against DIF10 but some, for which geographical footprint had to be stripped out, since it was containing corrupted information. The collections on FedEO are currently visible on the instance at reference platform and will be officially delivered to ESA operational instance at the next delivery cycle, hopefully before the WGISS-49. The requested automation is also implemented and an excel received would be automatically processed.
WGISS-47-30 | WGISS-47 |  |  | CDA SLT to send to WGClimate the list of elements in the inventory that should be made mandatory so they can be registered automatically | CDA SLT | 2019-06-30 | Closed | June 6: The SLT is organising with WGClimate to determine which activities can be done by the ESA team. July 17: ECV Team notified with email sent on 28/05/2019 16:00 (Iolanda and Mirko in cc). No answer yet. June 6: The NASA updates have been done, and Andrea is progressing with ESA’s. July 17: Michael Morahan and Yves discussed the remaining issues with respect to FedEO collection records, particularly the ECV records. In the ECV records, geographical extent needs to be machine readable and the organisation responsible for collection needs to be identified in a consistent way. ESA will indicate which ECV records to put into IDN. Nov 12: There is a mismatch been the WGClimate inventory and IDN fields. Jan 28: Some mapping done of WGClimate inventory fields to IDN fields; 535 records ingested into the IDN as a result. Action can be closed.
WGISS-47-31 | WGISS-47 |  |  | Mirko Albani and Yonsook Enloe to contact the KMA and JMA to get their assets connected | Mirko Albani | 2019-09-30 | Closed
WGISS-47-32 | WGISS-47 |  | Data Preservation and Stewardship | Mirko Albani to send information to Joerg Schultz about the Purge Alert procedure | Mirko Albani | 2019-06-30 | Closed | Sept 18: information sent.
WGISS-47-33 | WGISS-47 |  |  | WGISS to give a demonstration of the Carbon Portal at the WGClimate meeting in September | WGISS |  | Closed | July 17: Mirko plans to contact Joerg on the feasibility of this.
WGISS-47-34 | WGISS-47 |  |  | Mirko Albani to liaise with Marc Paganini on discovery and access of data and platforms identified in the SDG slides | Mirko Albani | 2019-07-31 | Closed | August 20: discussion started. New feedback ready on September after a scheduled meeting. September 18: Waiting for meeting scheduling
WGISS-47-35 | WGISS-47 |  |  | CDA SLT and Ad-hoc team led by Valerie Dixon (Michael Morahan, Andrea Della Vecchia, Chris Lynnes, Cristiano Lopes, Richard Moreno) to look into OGC Testbed 14 results and assess possible use and application within WGISS FDA interoperability activities | CDA SLT | 2019-07-31 | Closed
WGISS-47-36 | WGISS-47 |  | Technology Exploration | Technology Exploration IG to define a template suitable for gathering inputs from agencies (domain, use case, datasets, labels, dataset accessible accessibility) in the areas of Machine Learning and Artificial Intelligence | Technology Exploration IG | 2019-08-31 | In Progress | June 6: Chris noted that he has someone in NASA to involve and Esther added that she is reaching out to some people in the UK, specifically from organisations in involved in the British Antarctica Survey. Dec 19; Manil Maskey is the NASA contact. Chris will message Manil to work on developing the template. Change due date to March 2020. Jan 28: Chris Lynnes cannot be Tech Expo lead any longer. Andy will reach out to a potential candidate who can come to WGISS meetings. Feb 28: After three iterations, the template is complete. Awaiting confirmation from Rob Woodcock. Apr 10: Template is ready. Rob will send it out for completion.
WGISS-48-01 | WGISS-48 |  | General | WGISS Exec to consider creation of a subgroup under the Data Interoperability and Use Interest Group to focus on “Services and Tools: discovery, access and interoperability”. Due by end 2019. | WGISS Exec | Dec 31 2019 | Closed | Nov 12: Mirko recommended making the Services/Tools activity explicit under Discovery and Access and the data cubes activity under the Interoperability. Michelle will included this on the WGISS website. Dec 19: Action can be closed.
WGISS-48-02 | WGISS-48 |  | General | WGISS Exec to await GEOSEC announcement and submit nomination of WGISS point of contact in GEO WP Foundational Tasks. Due by end 2019. | WGISS Exec | Dec 31 2019 | Closed | Dec 19: GEOSS Infrastructure Development Task Team is being assembled. GEO-SEC asked to nominate 2 individuals (a principal and an alternate) to serve on the Team, by 9 December. KOM will be held on18 Dec. http://earthobservations.org/documents/gwp20_22/tor_geoss_infrastructure_development_task_team.pdf First face-to-face meeting will be on 21 Feb 2020 during the GEO Data and Knowledge Week (Registration f open until 31 Dec at: http://earthobservations.org/geodataweek20.php. GEO-SEC confirmed that no formal letter was received from CEOS SIT Chair to confirm Rob as member of the Team. Action can be closed.
WGISS-48-03 | WGISS-48 |  | General | WGISS Exec to review and comment potential Actions on WGISS in the new CEOS Work Plan 2020-22 in relation to ARD Strategy. Due by February 2020. | WGISS Exec | 2020-02-01 | Closed | Nov 12: Ongoing. Dec 17: There have been discussions; Rob is anticipating that with a new CEO WGISS may be asked to have another look at the Plan.
WGISS-48-04 | WGISS-48 |  | Data Discovery and Access | Michelle Piepgrass to discuss with Brian Killough the possibility of restoring the URL wgiss.ceos.org since it is referenced in several brochures. Due by November 2019. | Michelle Piepgrass | 2019-11-30 | Closed | Apr 10: Cannot be done. Decided to leave as is.
WGISS-48-05 | WGISS-48 |  | Data Discovery and Access | WGISS CDA-SLT to organise a session at WGISS-49 on services discovery and access with the goal to align the approaches of OGC, CDA, and GEO. Due by WGISS-49. | WGISS CDA-SLT, Yonsook Enloe | WGISS-49 | Closed | Nov 12: To be added to the WGISS-49 agenda. Dec 19: Can be closed.
WGISS-48-06 | WGISS-48 |  | Data Discovery and Access | WGISS CDA-SLT to review VC data collection inventories spreadsheet and confirm if/what information is missing to generate DIF-10 metadata for the datasets therein included. Due by December 2019. | WGISS CDA-SLT, Michael Morahan, Mirko Albani, Andrea Della Vecchia | 2019-12-31 | In Progress | Nov 12: An analysis similar to one done with WGClimate of VC datasets registered in the IDN. Michael will resend the response from a few months ago. Dec 19: Michael resent but has not received a response. Jan 28: Michael completed his part of action. ESA/Mirko will take the next step. Mar 19: Communication with data owners is on going for the registration of the collection, in particular with NOAA at the moment. Apr 10: Emails have been sent to all agencies involved. Nitant is planning to respond. Ask Damiano if this action should be closed.
WGISS-48-07 | WGISS-48 |  | Data Discovery and Access | WGISS CDA-SLT to prepare a template for VC Leads to gather information for IDN registration. Ask for specific needs (e.g. One-stop-shop data discovery and access for relevant data sets and tools? Community portals?). Due by December 2019. | WGISS CDA-SLT | 2019-12-31 | Closed | Nov 12: The VC leads needs to be identified. Dec 19: Awaiting response. Jan 28: Draft MMT (Metadata Management tool) can be used for this. However, VC leads do not own the VC data. Multiple individual data providers own the data. The action can be closed.
WGISS-48-08 | WGISS-48 |  | Data Interoperability and Use | WGISS Interoperability Tiger Team to follow-up interoperability activities between data cubes as defined in the roadmap outlined in the WGISS#48 session (including definition of relevant milestones). The team will include Rob Woodcock (Lead), Andrea Della Vecchia, Brian Killough, Philippe Mougnaud, Chris Lynnes, Damiano Guerrucci, Valerie Dixon, and Michael Morahan. WGISS are to share with LSI-VC any background information on terminology definitions work (e.g. Data Stewardship Glossary) and schedule a telecon to discuss next steps and lay out a plan for moving forward. | WGISS Interoperability Tiger Team | 2019-12-31 | Closed | Nov 12: LSI has a draft, and Rob will circulate his updates. Rob will organize a meeting of the Tiger Team in December. Nov 17: CEOS Terminology Definitions: ESA-USGS Joint Task on Landsat/Sentinel-2 ARD Products document circulated to WGISS-Exec. Dec 19: The team met, shared with LSI VC; Rob will break the task into parts. It was noted that the 5 terms discussed are topics for further expansion in the Data Cube interoperability and FDA-08 technical notes and work program. It was decided not to task this work until the New Year since there is enough work to complete at this time and Christmas and New Year break is about to occur.
WGISS-48-09 | WGISS-48 |  | Data Interoperability and Use | WGISS Exec (Rob Woodcock and Chris Lynnes) to reformulate FDA-08 with a short umbrella clarifying the FDA business case and high level picture plus a set of underlying papers on specific topics (e.g. cloud-native formats, OGC-API evolutions, data cubes interoperability, and STAC). Due by December 2019. | WGISS Exec (Rob Woodcock and Chris Lynnes) | 2019-12-31 | In Progress | Nov 12: In progress. Apr 10: Rob will handle
WGISS-48-10 | WGISS-48 |  | Data Interoperability and Use | WGISS Exec (Mirko Albani and Iolanda Maggio) to define a governance process to update and maintain the OSS and FDA Elements Inventory. Due by February 2020. | WGISS Exec (Mirko Albani and Iolanda Maggio) | 2019-02-20 | Closed | Dec. 19: Work to be started. Feb 28: The decision will be presented at WGISS-49. May 25: Proposal was sent and feedback received. Action can be closed.
WGISS-48-11 | WGISS-48 |  | Data Interoperability and Use | WGISS Exec (Iolanda Maggio) to ensure coordination of inventory activities with ongoing SLT work on UMM-S/UMM-T and with discovery/access through WGISS CDA. Due by February 2020. | WGISS Exec (Iolanda Maggio) | 2019-02-20 |  | Apr 10: Delayed to June
WGISS-48-12 | WGISS-48 |  | Data Preservation and Stewardship | Iolanda Maggio to update the Persistent Identifiers Best Practice and circulate it to WGISS by December 31, 2019. | Iolanda Maggio | 2019-12-31 | Closed | Nov 12: New version of BP will be circulated by end of November. Dec 19: The new release is under final review and it will be circulated by January. Feb 28: Document ready for circulation and posting.
WGISS-48-13 | WGISS-48 |  | Data Preservation and Stewardship | Iolanda Maggio to organise a session at WGISS-49 to discuss persistent identifiers, including use cases of DOI (i.e. software). Due by WGISS-49. | Iolanda Maggio | WGISS-49 | Closed | Nov 12: To be added to the WGISS-49 agenda. Dec 19: Can be closed
WGISS-48-14 | WGISS-48 |  | Data Preservation and Stewardship | Ken Casey to make a presentation at WGISS-49 to demonstrate the NOAA CoMET tool and the Maturity Matrix Self-Assessment tool. Due by WGISS-49. | Ken Casey | WGISS-49 | Closed | Nov 12: To be added to the WGISS-49 agenda. Dec 19: Can be closed.
WGISS-48-15 | WGISS-48 |  | Data Preservation and Stewardship | Mirko Albani and Iolanda Maggio to organise a teleconference/meeting with WGCV representatives to review the Maturity Matrix. Due by November 2019. | Mirko Albani and Iolanda Maggio | 2019-11-19 | Closed | Nov 12: Iolanda meeting with WGCV end of November. Working in parallel with WGISS-47-26b. Dec 19: Feedback received, action can be closed.
WGISS-48-16 | WGISS-48 |  | Data Preservation and Stewardship | Iolanda Maggio to issue the Maturity Matrix to WGISS for review by February 2020 and to request approval to finalise at WGISS-49. Due by WGISS-49. | Iolanda Maggio | WGISS-49 | Closed | Nov 12: To be added to the WGISS-49 agenda. Dec 19: Input from WGCV integrated in DMSMM together with the FAIR indicators. Matrix will be circulated in February and presentation for approval will be held at WGISS-49. Added to the WGISS-49 agenda.
WGISS-48-17 | WGISS-48 |  | Technology Exploration | WGISS Exec to assess Blockchain as a potential topic for the Technology Exploration Interest Groups and see if there is interest in WGISS to proceed with it further. Due by February 2020. | WGISS Exec | 2019-02-20 | Closed | Dec 19: ESA will circulate a short report on Blockchain use cases to stimulate discussion. This is a potential topic for WGISS-49/50; Chris said that at AGU one of the NOAA reps is looking at BlockChain. Feb 28: Decision made; action can be closed.
WGISS-48-18 | WGISS-48 |  | Technology Exploration | WGISS Exec to develop a plan/solicit volunteers to write sections of the Future Data Architecture Whitepaper as it applies to STAC/OGC-API/Datacube interoperability), now that IDN (through CMR) has a STAC API (OGC WFS 3.0-compliant). Due by January 2020. | WGISS Exec, Rob Woodcock | 2019-01-20 |  | Apr 10: Pending outcomes of WGISS-49
WGISS-48-19 | WGISS-48 |  | Technology Exploration | Technology Interest Group to explore the possibility to organise a dedicated session on ARD products SW and tools at WGISS-49. Due by WGISS-49. | Technology Interest Group | WGISS-49 | Closed | Nov 12: To be added to the WGISS-49 Dec 17: Added to the WGISS-49 agenda
WGISS-48-20 | WGISS-48 |  | Working Groups Cooperation | WGISS Exec to consider having a joint workshop with GEOSS at WGISS-49. Due by WGISS-49. | WGISS Exec, Rob/Mirko | WGISS-49 | Closed | Nov 12: To be added to the WGISS-49 agenda. Dec 17: Added to the WGISS-49 agenda; action can be closed
WGISS-48-21 | WGISS-48 |  | Working Groups Cooperation | Andrea Della Vecchia and Michael Morahan to analyse feedback from WGClimate for IDN registration (see Joerg Schultz slides) and check if registration can be completed or we need additional feedback or to wait ECV inventory update V4. Due by November 2019. | Andrea Della Vecchia and Michael Morahan | 2019-11-30 | Closed | Nov 12: In progress Dec 19: About 200 ESA related collections will be registered in IDN without waiting for ECV Inventory V4. Can be closed. Jan 28: Platform and instrument names (column AJ) may be slightly different from GCMD vocabulary; a dump of the WMO/OSCAR database that contains the names used can be extracted. Note: can the WMO use GCMD keywords? If not, why not? Due to differences in keywords, a unique ID is being considered.
WGISS-48-22 | WGISS-48 |  | Working Groups Cooperation | Liping Di and Rich Baldwin to check with Joerg Schultz if an additional Carbon Portal Demo / Presentation is needed at WGClimate-12 in Q1-2020. Due by January 2020. | Liping Di and Rich Baldwin | 2019-01-20 | Closed | Nov 12: Michelle will follow up with Ken.
WGISS-48-23 | WGISS-48 |  | Working Groups Cooperation | DSIG to consider updating the WGISS Glossary of Terms to add ECV definitions and other interoperability-related terms to help in communicating with external entities: cooperation with WGClimate/LSI-VC/WGCV. Due by January 2020. | DSIG, Mirko will monitor | 2019-01-20 | In Progress | Nov 12: Document circulated by LSI on definitions around ARD; suggest including with WGISS glossary of terms. Mirko contacted them, but no one took the lead. He will follow up with Matt Stevenson. Dec 17: Discussions ongoing between Rob and Steve Labahn. Suggested to keep the ARD and WGISS Glossary Documents separate at least for the moment. No action so far on WGCV/Climate definitions. Dec 19: This document is with the Interop Tiger Team for review. The LSI VC added some examples, and Brian, Rob and Chris have added a section that talks more about access and cloud data formats, focused on ARD. May need to be split into two documents to separate categories of terms. Will be sent to LSI VC Dec 17. Feb 28: DSIG will update the glossary to introduce new acronyms, but most likely will not merge the two glossaries. Apr 10: will be circulated soon.
| CEOS | WGISS-48-08 WGISS-48-23 |  | CEOS Glossary of Terms Related to Analysis Ready Data, Future Data Architectures, and Interoperability: In the context of Earth remote sensing interoperability, many terms are often used inconsistently. To rectify this, WGISS will prepare, and seek CEOS endorsement of a summary of interoperability terms related to Analysis Ready Data discovery and analysis, in order to bring clarity and consistency to CEOS communications both internally and externally. This effort will address Task 1.4 of the CEOS ARD Strategy and will build upon and expand foundational work done by a subset of the LSI-VC and WGCV (IVOS). | Rob Woodcock with contributions from LSI-VC, WGCV IVOS | Q4 2020
Action WGISS-49-01 | WGISS-49 |  | Working Groups Cooperation | WGISS to identify members to participate in the four GEO working groups that were created under the GEO Engagement Priorities Coordination and GEOSS Data, Information and Knowledge Resources Foundational Tasks of the 2020-2022 GEO Work Programme. | WGISS Exec | 2020-09-01 | closed | May 27: Brian Killough will participate; Andy Mitchell is looking within NASA and Esther Conway within the UK). Mirko is also searching within ESA.
Action WGISS-49-02 | WGISS-49 |  | Working Groups Cooperation | WGISS, in cooperation with WGCapD, to develop FDA webinars for the following possible topics: cloud-native data formats, cloud data discovery and use (STAC), EO analytics on Kubernetes, ARD and ODC on Kubernetes, cloud-based analytics architectures, Jupyter Notebooks for EO. | WGISS-Exec |  | In progress | May 27: Chris Lynnes and Nancy Searby are working on several Other options: Data Cubes. NASA CMR STAC, Jupyter Notebooks demostration and online workshops. UK has several research projects underway but these would need to be presented in conjunction with other agency's activities. A standard coming out of CEOS CNES work with Pangeo/STAC. Esther suggested starting a documentary conversation on this. June 29: Rob to reach out to Yousuke to coordinate.
Action WGISS-49-03 | WGISS-49 |  | Working Groups Cooperation | WGISS to determine how to achieve collaboration with WGCapD in the Interoperability Lab, such as a training facility. | Rob Woodcock |  | In progress | May 27: Rob met with the SEO to get the lab established. The goal is to set up interoperability experiments. The team will be speaking with COAST about two projects regarding needs in terms of tools, services, leading to a set of interop experiments. COAST will be enabled to perform their experiments, and thus begin to learn how this can be done more effectively to feed back into a Best Practice. Mirko added that a practical item would be with the GEO Hazards Lab. Rob will work on forming a team for this project; it is still in the explore stage. June 29: (see chair report)
Action WGISS-49-04 | WGISS-49 |  | Working Groups Cooperation | WGISS to determine joint WP Deliverables in collaboration with WGDisasters in the Interoperability Lab.
Action WGISS-49-05 | WGISS-49 |  | Working Groups Cooperation | Liping Di to work with Cindy Ong on developing a project for multiparty standards on calibration and validation for products. | Liping Di, Cindy Ong |  |  | June 29: The standard project (ISO 19124-1) has just started and ISO TC 211 will work with CEOS WGISS and CAL/VAL WGs on the development of the standard. Cindy has been contacted on this standard. The 19124-1 project team is drafting the first version of the standard and will be distributed to WGUSS and CAL/VAL for comments and inputs. I will brief the progress on the standard development at the next WGISS meeting.
Action WGISS-49-07 | WGISS-49 |  | Data Discovery and Access | WGISS to review impacts of cloud data availability and STAC in line with the changes at USGS. |  |  | In progress | May 27: Suggestion is to collectively work on a common implementation of STAC; this could be an area of cooperation with GEO, expanding beyond space data. The CDA-SLT needs to look at this. June 29: Michael Morahan reported that this will affect the metadata, so the IDN team is investigating this. Robert will copy Michael on email with LSI-VC in reference to ARD product specifications.
Action WGISS-49-08 | WGISS-49 |  | Data Interoperability and Use | WGISS to coordinate an initial survey of agencies to learn targeted datasets and associated Jupyter Notebooks, and key datasets for WGCapD and associated notebooks. Survey could include input of relevant capabilities and needs and Notebook standards and CEOS endorsement. | Esther Conway, Chris Lynnes |  | In progress | May 27: Esther suggested drafting a form of the survey to send to Exec for approval, and also reaching out to Nancy Searby to work through the WGCapD. Andy will follow up with Chris. June 29: Esther is working on developing a survey of agencies in four sections to understand resources, networks, need for Best Practice and CEOS approved notebooks. Next step: Esther will submit the survey to Exec for review.
Action WGISS-49-09 | WGISS-49 |  | Data Interoperability and Use | WGISS to break down the problem of defining the Jupyter Notebooks/Interoperability Lab to develop a clear idea of what this involves and where to go with it. | Esther Conway |  | In progress | May 27: The survey needs to be conducted first. It is hoped that the survey will generate a network of resources. The SEO has a Data Cube library on Jupyter Notebooks.
Action WGISS-49-10 | WGISS-49 |  | Data Discovery and Access | WGISS to discuss with LSI-VC the task of developing a list of common names in STAC how they are derived for consideration and feedback. |  |  | In progress | May 27: Rob suggested that the CDA-SLT consider this. Richard Moreno added that it would be interesting to have a wider-level vocabulary; he will investigate. Rob agreed to inquire with SEO on the possibility of a vocabulary service within the Interoerability Lab.
Action WGISS-49-11 | WGISS-49 |  | Data Preservation and Stewardship | DSIG to collect challenges/lessons learned/questions from WGISS members on PID/DOI usage/implementation (e.g. PID assignment to Document and SW by NOAA, Minor releases management, etc.) Collect from presentations and email from WGISS members. | DSIG |  | In Progress | May 27: Iolanda received feedback and comments from JAXA, and has provided answers to Makoto. Jun-29: The list of possible topics to be discussed will be available by Mid of July.
Action WGISS-49-12 | WGISS-49 |  | Data Preservation and Stewardship | DSIG to organize a PID session to address/discuss questions and challenges and propose an updated version of PID Best Practice at WGISS-50. | DSIG |  |  | Jun-29: session will be based on topics identified in action 49-11
Action WGISS-49-13 | WGISS-49 |  | Data Preservation and Stewardship | DSIG to investigate how to handle replicas of data for example in the cloud: PID assignment? Using watermarks? Mechanism for handling that to be further discussed and recommendation issued. | DSIG |  |  | Jun-29: the topic is under analysis. The outcomes will be shared with WGISS members.
Action WGISS-49-14 | WGISS-49 |  | Data Preservation and Stewardship | DSIG to work on a BP on Data Associated Information management and preservation and discuss at WGISS-50. | DSIG |  | In Progress | Jun-29: The new version of the BP will be available for review by 19th of July.
Exec 2020-04-1 | Exec 2020 |  | Data Preservation and Stewardship | WGISS to review the WGISS Data Management and Stewardship Maturity Matrix 1.2 by Mid of May; Iolanda Maggio to integrate any comments and input by the End of May | Iolanda Maggio, All |  | Closed | Jun-29: The new version of the BP will be available for review by 19th of July.