## StatusSummary
WGISS Action Item Status Summary as of June-29-2006
| Due: Pre-June-2006 | Due: June-2006 | Due: WGISS-22 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 3 | 1 | 5 | 19 | 28
WGISS-21 | 1 | 9 | 6 | 7 | 23
Total | 7 | 10 | 11 | 30 | 58
WGISS Action Item Status Summary as of September 15, 2006
| Due: Pre-WGISS-22 | Due: WGISS-22 | Due: Post WGISS-22 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 9 | 0 | 0 | 19 | 28
WGISS-21 | 7 | 5 | 0 | 11 | 23
WGISS-22 | 0 | 0 | 27 | 0 | 27
Total | 19 | 5 | 27 | 34 | 85
WGISS Action Item Status Summary as of October 27 2006
| Due: WGISS-22 | Due: Oct-2006 | Due: Post Oct-2006 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 6 | 0 | 0 | 22 | 28
WGISS-21 | 7 | 0 | 1 | 15 | 23
WGISS-22 | 0 | 14 | 13 | 8 | 35
Total | 16 | 14 | 14 | 49 | 93

## WGISSActions
WGISS Action Items
| Last Updated | Last Updated By
| 2007-11-07 | G. Dyke
No. | Action | Who | By | Open/CLOSED | Status
18-23 | As we close Global Mapping Book Task Team we propose that the Task Team lead should take the action to pass the information on to the WITT | Wyn Cudlip | 2005-10-31 | Open | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - WGISS-21 status: Still open. - Email sent 28-June-2006 - Sept 1, GD: Email sent. - Oct 19, '06 GD: Email sent.
18-27 | All Task Teams compile a template by WGISS 19. (Global Data Set doesn't have a template.) | Task Teams | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - Apr-29, SD: WITT completed. CLOSED
19-7 | WGISS liaisons to supply a description of their liaison area and their key documents to WITT for hosting. | Liaisons & WITT | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - Apr-29, SD: WITT waiting for inputs and will discuss with designated liaison reps at WGISS 21. - WGISS-21 status: liasons who have not submitted are requested to send inputs to Stu. - Email sent 28-June-2006 - Sept 1, GD: Email sent. - Oct 19, '06: Email sent. - 27 September 2007: Descriptions provided and posted. CLOSED
19-24 | Make an approach to the Global Land Cover Facility to determine any collaboration areas. | Wyn Cudlip | WGISS21 | Open | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - WGISS-21 status: Wyn to follow-up, still open. - Email sent 28-June-2006 - Sept 1, GD: Email sent. - Oct 19, '06 GD: Email sent.
19-25 | Try to get a full set of 1999 and 2000 global Landsat coverage tapes to EO Data Portal Project. | Lorant Czaran John Faundeen | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - Jan-12, JF: Imagery being sent to Lorant, should be completed in a few weeks, action remains open. - Jan-12, LC: We will then also provide the data to the ICEDS team as needed, in coordination with Wyn Cudlip, as this was from the beginning in the context of the WGISS EO Portal project. - WGISS-21 status: CLOSED
19-26 | EO Data Portal Project to talk to the IDN Task Team Chair to coordinate access to the url. | Wyn Cudlip | 2005-11-01 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - WGISS-21 status: Coordination complete, CLOSED
19-32 | Set up a liaison with GSDI - WGISS could become an ex-official member - identify any potential areas of interaction. | Allan Doyle | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - Jan-19, AD: GSDI will be sending Dr. Dr. Gábor Remetey- Fülöpp to WGISS-21 to help work out the details of the arrangement. Potential areas of interaction to be identified in the leadup and followup to WGISS-21. - WGISS-21 status: CLOSED
20-1 | Update the WGISS menu and transfer to WITT. | Wyn Cudlip | 2005-10-31 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - Apr-29, SD: Completed. CLOSED
20-2 | Review WGISS 5-year plan starting at WGISS 21. | WGISS | WGISS 22 | CLOSED | - Email sent 20-Jan-2006 - WGISS-21 status: Agreed to address this topic at WGISS-22. - Sept 1, GD: 1 hour discussion topic on the WGISS-22 agenda for WGISS 5-year plan. - Oct 19, '06 GD: Email sent to IP, WC. - Oct 26 06, IP: Emailed newly updated WGISS 5-Year Plan. CLOSED
20-3 | Core Test Sites transition plan needs to be documented by WGISS-21 or 22. Will be reported to Plenary as closing or transitioning in 2006. | John Faundeen | WGISS 21 or 22 | CLOSED | - Email sent 11-Jan-2005 - Jan-12, JF: This will be based upon a report being compiled by our Science sponsor, WGCV. They are to have that completed prior to WGISS-21 so a transition plan could realistically be prepared for WGISS-22, action remains open. - WGISS-21 status: Transition planning has begun as captured by WGISS-21-10. CLOSED
20-4 | What does "custom processing of data" mean to CAL/VAL - report to Projects and Applications Subgroup and copy WGISS as to whether this phrase implies new development work for the WTF or is merely more operational work. | John Faundeen | 2005-11-30 | CLOSED | - Email sent 11-Jan-2005 - Jan-12, JF: To date, there has been no elaboration by our WGCV partners. I will report this to be "operational" unless the WGCV report, mentioned above, sheds any new light. - Jan-22: Email confirmation from JF that action remains open. - WGISS-21 status: CLOSED
20-5 | Contact agencies for updates to OGC Compliance Web Services. | Wyn Cudlip | 2005-10-31 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - WGISS-21 status: Requests sent, now ongoing activity. CLOSED
20-6 | At the end of ICEDS activity ensure project output (software, reports, documentation…) to the WITT. | Wyn Cudlip | 2006-02-01 | Open | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - WGISS-21 status: Activity has been completed, information will be forwarded. - Email sent 28-June-2006 - Sept 1, GD: Email sent. - Oct 19, '06 GD: Email sent.
20-7 | To procure a presentation on SAFE. | Kengo Aizawa | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - WGISS-21 status: CLOSED
20-8 | Implement an "Ask WGISS" to the Chair | WITT | 2005-12-01 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - Apr-29, SD: WITT waiting movement to new server and deployment of PHP to implement. - WGISS-21 status: Still open. - June-10, SD: Email sent to indicate that Ask WGISS was now operational. - June 29: CLOSED
20-9 | To implement a forum capability (on-line discussion tool). | WITT | 2005-12-01 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - LO, Apr-21-2006: This one was for the IDN. This has been done and is known as the Interoperability Forum. http://idn.ceos.org/IDN/IDN_Newsletters - Apr-29, SD: WITT waiting movement to new server and deployment of PHP to implement. - WGISS-21 status: Follow-up at WGISS-22, LO and SD to present prototypes for comparison. - Sept 5, SD: Presentation planned and scheduled for WGISS-22. - WGISS-22: SD has two proposed platforms that will be evaluated in the next month. - Oct 19, '06 GD: This item could be closed in lieu of 22-35. - Oct 19, '06: Email sent. - 27 September 2007: WITT responsibilities to transition after WGISS-24. New WITT team to decide direction. CLOSED
20-10 | Technology and Services Subgroup will document recommendations from one or two task teams as a start on a handbook and provide to Chair and Vice Chair. | Paul Kopp Dingsheng Liu | 2005-12-31 | CLOSED | - Email sent 11-Jan-2005 - Jan-11, PK: Hope to have something ready by the end of Jan-2006, action remains open - Feb-3, PK: Here are my first thougths about WGISS Action item 20-10: Technology and Services Subgroup will document recommendations from one or two task teams as a start on a handbook and provide to Chair and Vice Chair. - Feb-8, IP: Materials submitted are an excellent start, further discussion should follow at WGISS-21. Action's original intentions have been addressed. CLOSED
20-11 | Each Task Team to provide to the Subgroup, for validation and coordination, two FAQ questions and answers. | Task Team Leads | 2005-11-01 | CLOSED | - Email sent 11-Jan-2005 - Apr-29, SD: WITT has only received two FAQs from Core Test sites and has initial page of FAQs at http://wgiss.ceos.org/faq.html. - WGISS-21 status: Awaiting inputs from Task Teams, Chair and Vice Chair to review the inputs provided. - Email sent 28-June-2006 - June 28, SM: Will reply ASAP. - June 29, SK: Will be dealt with, after closing 21-5. - Juen 29, KA: Ongoing discussion with Stu. - June 30, LG: Forwarded FAQ to Stu. - July 4, LO: Sent FAQs, which have been forwarded to Stu for addtion to the website. - July 7, KA: Please wait 20-11 for a while. - July 28, KA: I sent ATT FAQ to Stu which was AI 20-11. He will put them to WGISS HP. - Aug 18, SM: Sent inputs to SD. - Sept 1, GD: Emailed LC, JM, SK to request inputs to close this item out. - Sept 5, SK: Emailed draft question to DSTT. - Oct 19, '06: Email sent. - 27 September 2007: Task Team inputs received. CLOSED
20-12 | ICS to provide canned demo (with sound) of the INFEO system. | Jolyon Martin | 2005-10-15 | CLOSED | - Email sent 11-Jan-2006 - Email sent 21-Apr-2006 - WGISS-21 status: Work has started, but not yet complete. - Email sent 28-June-2006 - Sept 1, GD: Emailed JM to get the latest status. - Sept 1, JM: After attempts with a few tools (SnagIt, windows movie editor), the results were never acceptible (too low resolution/jerky to understand what was going on). Probably I need to look at producing something in flash, but this is outside the "best effort" that I can afford at this time. A non interactive tutorial is made available at http://catalogues.eoportal.org/tutorial/tutorial.html, unfortunately I think I have to close this action with only providing the tutorial and not interactive demo. - Oct 19, '06 GD: CLOSED based on JM's Sept 1 email.
20-13 | IDN to provide canned demo (with sound) of the IDN itself and the map server. | Lola Olsen | 2006-01-31 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - LO, Apr-21-2006: This Action has been completed and will be demonstrated at the upcoming meeting in Hungary. - LO, May-9-2006: Presenting this to the WGISS-21 group. - WGISS-21 status: Demos provided on a CD at WGISS-21, will also be put on the IDN website. CLOSED
20-14 | Provide statistics on the IDN CEOS and GEOSS portals that were developed. (Lola) | Lola Olsen | 2005-10-15 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - LO, Apr-21-2006: This action has also been completed and this statistics will be presented at the upcoming meeting. - LO, May-9-2006: Presenting this to WGISS-21 group. - WGISS-21 status: Demos provided on a CD at WGISS-21, will also be put on the IDN website. CLOSED
20-15 | Password-protect the IDN GEOSS portal and add a disclaimer. | Lola Olsen | 2005-10-15 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - LO, Apr-21-2006: Done. CLOSED.
20-16 | Move the GRID WIKI and Task Team pages to wgiss.ceos.org. | WITT | 2005-10-15 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - Apr-29, SD: Task Team pages moved completed. CLOSED
20-17 | Grid Task Team to request an EGEE presentation. | Li Guoqing | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - Jan-12, LG: Requested an introduction to EGEE from IP and LFusco at WGISS-21 meeting, action remains open. - WGISS-21 status: Presentation given at WGISS-21, available on the FTP site. CLOSED
20-18 | Informational briefing on European Commission Information Society Technology Program. | J.P. Antikidis | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - Jan-11, JP: Action progress is on schedule. - WGISS-21 status: Presentation to be given at WGISS-22. - Sept 1, GD: Request for update sent. - WGISS-22: A briefing was given at WGISS-22 by JPA. CLOSED
20-19 | To provide a straw man for service categorizing on services role. | Mike Burnett | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - WGISS-21 status: Presented at WGISS-21. CLOSED
20-20 | Provide examples of ontology activities. | Hiromichi Fukui | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - WGISS-21 status: Presented at WGISS-21, more examples to follow at WGISS-22, Open. - Sept 1, GD: Request for update sent. - Oct 19 '06, GD: Email sent. - 27 September 2007: Action overcome by events. CLOSED
20-21 | Chair to solicit the CEOS Representatives to the GEO Standing Committee for their ideas being perceived as needs. Get information regarding subject of a demo for GEO. | Ivan Petiteville | 2006-02-01 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - IP, Apr-21, 2006: Let's keep the action open, and we will discuss it at WGISS 21. - WGISS-21 status: Superceded by discussion at WGISS-21, GEO demo is pre-mature. CLOSED
20-22 | Find a replacement for Liping Di to represent CEOS on ISPRS. | Chair | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - Jan-11, IP: Send email to WGISS/All to solicit interest in the ISPRS representitive role. - WGISS-21 status: Prof. Fukui to serve in this role. CLOSED
20-23 | Each agency consider joining the Wide Area Grid activity. | All | WGISS 21 | CLOSED | - Email sent 20-Jan-2006 - WGISS-21 status: Some agencies have responded positivly, awaiting others, should be kept open. Further discussion at WGISS-22. - Oct 19 06, GD: Email sent to JPA asking if this item could be closed, overcome by 22-10, 22-11 and 22-12. - 27 September 2007: WAG activities have been discussed extensively at WGISS 21, 22 and 23. CLOSED
20-24 | Update paper on Browse and place on the shared documents section - web site; inclusion in CEOS WGISS Brochure. | Stuart Doescher | 2005-10-15 | CLOSED | - Email sent 11-Jan-2005 - Email sent 21-Apr-2005 - Apr-29, SD: Posting completed Jan 13 2006. CLOSED
20-25 | Liaison position will be established with eGY to report at each WGISS meeting. WGISS members will check with their agencies for their willingness to be a liaison. (Point of contact with eGY will be Dr. Charles Barton.) | All | WGISS 21 | CLOSED | - Email sent 20-Jan-2006 - WGISS-21 status: David Clark will serve in this liason position. CLOSED
20-26 | JAXA will make a prototype of multi-lingual of a CEOS WGISS web site. | Masatoshi Kamei | WGISS 21 | CLOSED | - Email sent 11-Jan-2005 - WGISS-21 status: Demo provided at WGISS-21. CLOSED
20-27 | CNES to provide a formal project plan for Wide Area Grid activity | J.P. Antikidis | 2006-03-01 | CLOSED | - Email sent 11-Jan-2005 - Jan-11, JP: Action progress is on schedule. - Email sent 21-Apr-2005 - WGISS-21 status: Work is in progress, Open. - Email sent 28-June-2006 - June-28, JPA: Push deadline back to Aug-15-2006. - Sept 1, GD: Request for updated status sent. - Sept 1, JPA: Provided draft by email. - Oct 19 06, GD: Email sent to JPA asking if this item could be closed, overcome by 22-10, 22-11 and 22-12. - 27 September 2007: A formal plan has been discussed at WGISS 21, 22 and 23. CLOSED
20-28 | Chair to determine if WGISS can formally endorse eGY. | Ivan Petiteville | 2005-12-31 | CLOSED | - Email sent 11-Jan-2005 - Jan-12, IP: Considering whether endorsing eGY is a WGISS or CEOS level function, action remains open. - WGISS-21 status: Is not apporpriate for WGISS to endorse eGY. CLOSED
21-1 | Liu Chuang to lead scoping of a booklet promoting WGISS benefits to Global Environmental Change programmes. | Liu Chuang | 2006-06-01 | Open | - Email sent 28-June-2006 - June 29, LC: Will be distributnig a framework in the next few days. - Sept 1, GD: Request for updated status sent. - Oct 19 06, GD: Email sent suggesting this item can be closed in lieu of 22-1 and 22-2.
21-2 | Task Team leaders to review WGISS WWW content to ensure their pages are up to date and to advise WGISS webmaster of any necessary revisions. | Task Team Leaders | 2006-06-01 | CLOSED | - Email sent 28-June-2006 - June 28, SM: Have replied to Stu. - June 29, SK: Will be dealt with, after closing 21-5. - June 29, KA: Have provided response to Stu. - Sept 1, GD: Request for updated status sent. - Oct 19, '06: Email sent. - 27 September 2007: This review has taken place. CLOSED
21-3 | Paul Kopp to issue requests for contributions to the CEOS Interoperability Handbook. | Paul Kopp | WGISS-22 | CLOSED | - Sept 1, GD: Request for updated status sent. - Sept 5, PK: Have issued a request for comment, not for contributions at this stage. Suggest we keep this action open, but to be closed by discussion at WGISS-22. - WGISS-22: PK presented a summary of current status, and issued a request for contributions to lead each chapter of the handbook. - Oct 19 06, GD: This was completed at WGISS-22. CLOSED
21-4 | Provide a sample package of SAFE data products and tools. | Gian Maria Pinna | WGISS-22 | Open | - WGISS-22: Deferred until WGISS-23, ping GMP. - Oct 19 06, GD: Email sent.
21-5 | Task Team leaders to review GEO Work Plan and to advise WGISS GEO Coordinator (WGISS Vice Chair) as to which activities their Task Team might potentially support and to nominate a suitable Point of Contact. | Task Team Leaders | 2006-06-01 | CLOSED | May-26: IP sent process document with some reference information to support the TT nominations of POCs. June-22: KA sent a request to the ATT for comments on a proposal. - Email sent 28-June-2006 - June 28, SM: Have replied to Ken. - June 29: SK: Ongoing, I will close it soon. - June 29, KM: Have recieved inputs from many task team leads - Paul Kopp and others - planning to synthesize and distribute for further review and prioritization. - June 29, KA: Ongoing discussion with Stu. - June 29, LG: We cannot find our suitable contribution to GEO 2006 Work Plan. Hope we can do more in the following 2007-2009 Work Plan. A discussion of Grid TT contribution to GEO is takeing between some agencies (CNES/ESA/NRSCC) and the wide discussion will be taken in WGISS22. - July 3, SK: Attached is a revised version of DSTT contribution on GEO WPs for 2006. - July 4, LO: Inputs sent to KM+ others. - July 7, KA: I will send final answer of 21-5 to Paul and Ken on 10th monday at latest. - July 7, PA: Sent inputs to KM for review and integration. - July 12, KA: Provided final inputs to KM. - Aug 12, KM: Emailed colsolidated list of items to WGISS-ALL. Aug 18: CLOSED
21-6 | Add the GCMD demonstration video to the IDN portal. | Lola Olsen | 2006-07-01 | CLOSED | June-5: Lola reported that the demo video is at: http://idn.ceos.org/IDN/Meetings/2005_05_Hungary/view_tutorial, CLOSED.
21-7 | Investigate how the IDN might be applied in support of the CEOS Response to the GCOS IP May 2006. | DeWayne Cecil, Lola Olsen | 2006-05-01 | CLOSED | June-1: Status request email sent. June-5: DC reported: Dr. Eric Lindstrom, the NASA HQ representative in Geneva for the Climate Task Team meeting presented the IDN portal that was developed to help CEOS respond to the GCOS action to review the climate variable/satellite document. - Email sent 28-June-2006 - June-29, LO: We are definitley still thinking about IDN support going forward. - June 29, IP: SW to follow-up with Paul Mason to get the complete picture on the IDN status. - June 30: Based on SW's coming follow-up discussion, this action will be CLOSED - its original intention has been fulfilled.
21-8 | Provide suggestions to WGISS regarding the organisation of the 2007 EOGEO meeting. | Liping Di | 2006-07-01 | CLOSED | - Email sent '06/28/2006' - June 29: LD is working this topic, expect an update in mid-July. Positive responses received to date. - July-2, LD: On target for end of July completion. - Sept 1, GD: Request for updated status sent. - WGISS-22: A presentation of suggestions was made at WGISS-22. - Oct 19 06, GD: Email sent suggesting we can close this item. - Oct 24 06: CLOSED.
21-9 | CLOSED, TRASNFERRED TO WGCV: Develop plans for a Cal/Val Portal workshop in the June 2007 timeframe. | Pascal LeComte | 2007-06-01 | CLOSED
21-10 | SHARED BETWEEN WGCV & WGISS: Report to WGISS-22 with a transition plan for the WTF Core Sites activity. | Jeff Morissette, Lyn Oleson | WGISS-22 | CLOSED | - Sept 4, GD: Request for updated status sent. - Sept 6, LO: Presentation planned for WGISS-22, hopefully will be able to close at WGISS-22. - Oct 19 06, GD: Email sent indicating that this item may be able to be closed based on WGISS-22 presentation. - Oct 20 06, LO: In the interest of keeping open actions to a minimum, I do think technically this action can be closed. However, the inherent action of completing a transition is continuing and I will be sure that a status report is provided at WGISS 23. LO to provide an updated status of this activity at WGISS-23. CLOSED
21-11 | CLOSED, TRASNFERRED TO WGCV: WGCV to verify that work related to the validation CEOS-WGCV Terrain mapping is incorporated in the 2007-2009 GEO Work Plan. | Stephen Unger | WGISS-22 | CLOSED
21-12 | Post the GEO Task Points of Contact on the WGISS website. | Stu Doescher | WGISS-22 | CLOSED | July 20, SD: AI 21-12 is completed. Reference http://wgiss.ceos.org/geopoc.html
21-13 | Contact WGEdu to confirm Dr. Liu as the WGISS liaison to the WG. | Ivan Petiteville | 2006-06-01 | CLOSED | May-19: IP sent email to YB to confirm that Dr. Liu is the nominated WGISS liason to WGEdu. CLOSED
21-14 | Contact GSDI to confirm Gabor as the WGISS liaison and to propose a way forward for cooperation. | Ivan Petiteville | 2006-06-01 | CLOSED | - June-7: IP circulated a draft letter to be sent. - Email sent 28-June-2006 - June-7: IP faxed the letter to GSDI, CLOSED.
21-15 | WGISS EXEC to provide comments to Wyn Cudlip on the WGISS Brochure. | Ivan Petiteville | 2006-06-01 | CLOSED | - Email sent 28-June-2006 - June 30, IP: Circulated PDF to EXEC for comments. - Sept 1, GD: Request for updated status sent. - Sept 1, IP: Provided comments some to Wyn. - 27 September 2007: This review has been put on the back burner. CLOSED
21-16 | Update the WGISS Brochure. | Wyn Cudlip | WGISS-22 | CLOSED | - Sept 1, GD: Email sent. - Oct 19, '06 GD: Email sent. - 27 September 2007: This brochure update has been put on the back burner. CLOSED
21-17 | WGISS WWW to be updated: - WITT: known info about all future WGISS meetings - WITT: GEO-related documents - WGISS Vice Chair: text for the WGISS website front page. | Stu Doescher , Ken McDonald | 2006-06-01 | CLOSED | - Email sent 28-June-2006 - July 6, KM: I consider myself "pinged". Unfortunately I have a couple of other actions to work on first, but I will get to it ASAP. - Sept 1, GD: Request for updated status sent. - Sept 1, SD: Awaiting inputs from KM. - Oct 19, '06: Email sent. - 27 September 2007: The WWW has been updated, and will be handled as an ongoing task in the future. CLOSED
21-18 | Circulate to WGISS Task Team leaders a brief analysis of the WGISS-related tasks from the GEO Work Plan | Osamu Ochiai | 2006-07-01 | CLOSED | May-26: OO distributed his analysis by email to all@WGISS. June-5: IP stated: Osamu, I was thinking to that through this action, you would help us to set up a list identifying precisely the relevant GEO tasks. - Email sent 28-June-2006 - June 29: CLOSED based in inputs recieved from OO.
21-19 | Confirm the process for WGISS management and reporting in support of the GEO tasks – including the proposed Points of Contact. | Ivan Petiteville | 2006-05-01 | CLOSED | May-26: IP sent email to all@WGISS to distribute the process document. CLOSED
21-20 | Transfer WGISS actions 21-9, 21-10 and 21-11 to WGCV. | Ivan Petiteville | 2006-05-01 | CLOSED | May-19: IP sent email to SU to transfer these items to WGCV. CLOSED
21-21 | GDTT leader to review position of liaison with the Global Map Project. | Lorant Czaran | 2006-06-01 | Open | - Email sent 28-June-2006 - Sept 1, GD: Request for updated status sent - Oct 19 06, GD: Email sent.
21-22 | Write a white paper on the topic of an International Virtual Earth Observatory. The white paper should be distributed to WGISS for internal review and follow-on discussion leading up to WGISS-22. | Liping Di | 2006-07-01 | CLOSED | - Email sent 28-June-2006 - June 29, LG: I have connected Dr. Stu to modify some words in Grid TT web pages. Some project update of agencies will be collected before WGISS-22. - July-2, LD: On target for end of July completion. - Sept 1, GD: Request for updated status sent. - WGISS-22: Presentation on this topic given at WGISS-22. - Oct 19 06, GD: Email sent suggesting we can close this item. - Oct 24 06: CLOSED
21-23 | Create a draft profile for a new WTF on Disaster Management. | Pakorn Apaphant | WGISS-22 | CLOSED | - June 29, IP: PA should look at the 2007-2009 Work Plan and ensure consistency with the GEO tasks for 2007-2009. PA confirmed he will perform this review. - Sept 1, GD: Request for updated status sent. - WGISS-22: Information presented to WGISS-22. - Oct 19 06, GD: Email sent to confirm that details were presented at WGISS-22. - Oct 24 06, PA: Since this taskteam was recommend from the WGISS22 meeting to revise the profile. We would then prefer to postpone the due date to WGISS23. I will need to talk with Prof.Fukui on the updated version. - 27 September 2007: Overcome by events within the GEO community. CLOSED
22-1 | Distribute a Table of Contents listing for the WGISS publication of its support of Global Environmental Change Research book. WGISS participants to provide feedback on the Table of Contents. | Liu Chuang | 2006-10-01 | Open | - Oct 19 06, GD: Email sent.
22-2 | Coordinate contributors to the support of Global Environmental Change Research publication. | Liu Chuang | 2006-12-01 | Open | - Oct 19 06, GD: Email sent.
22-3 | WGISS members should verify the accuracy of their email addresses in the current WGISS mailing lists, and provide updates to Stu Doescher. The lists for review can be found at: http://wgiss.ceos.org/ftp/WGISS22/WITT/ | WGISS-ALL | 2006-10-01 | CLOSED | - Sept 20: GD sent email to WGISS-ALL as a reminder. - Oct 19, 06, GD: Email sent to SD to propose closure plan. - 27 September 2007: Addresses reviewed at WGISS-24 and on an ongoing basis. CLOSED
22-4 | Review the activity on NASA list servers (CEOS-DS and CEOS-AS) and if they are inactive, recommend that they be de-activated. | Kathy Fontaine | 2006-11-01 | CLOSED | - Nov 21, KF: This item should be closed, and they are in the process of being deactivated. CLOSED
22-5 | Arrange a demonstration of the EO CalVal Portal at WGISS-23. | Ivan Petiteville | WGISS-23 | Open
22-6 | Contact all CEOS agencies who host OGC compliant servers (WMS, WCS) and have them ensure that the links to these servers are current and/or add any omissions. The links are at this URL: http://wgiss.ceos.org/eodp/index.html. | Wyn Cudlip | 2006-12-01 | Open | - Oct 19, '06 GD: Email sent.
22-7 | Update the information about the FAO activity on the EODP website. | Wyn Cudlip | 2006-10-01 | Open | - Oct 19, '06 GD: Email sent.
22-8 | Update the WGISS Five Year Plan. | Ivan Petiteville | 2006-09-01 | CLOSED | - Oct 19, '06 GD: Email sent. - Oct 26 06, IP: Emailed updated 5-Year Plan. CLOSED
22-9 | Organize a session at the WGISS-23 Plenary to discuss quality of data required for WGISS usage. | Paul Kopp | WGISS-23 | CLOSED | - 27 September 2007: WGISS-23 complete where the discussion took place.
22-10 | Issue, by email, a call for interest on WAG related matters, with a telecon to be organized before the end of 2006. | Jean–Pierre Antikidis | 2006-12-01 | CLOSED | - 27 September 2007: JP presented on this topic at WGISS-23. CLOSED
22-11 | Issue a reference WAG vision document in co-operation with NSAU, NRSCC, UN ant other organizations. | Jean–Pierre Antikidis | WGISS-23 | CLOSED | - 27 September 2007: JP presented on this topic at WGISS-23. CLOSED
22-12 | Present WAG WGISS plan and its applicability to GEO. | Jean–Pierre Antikidis | WGISS-23 | CLOSED | - 27 September 2007: JP presented on this topic at WGISS-23.
22-13 | When JAXA is ready, add a link to the JAXA multilingual prototype to the GCMD page. | Lola Olsen | 2006-11-01 | CLOSED | - WGISS-24: Currently there is no budget to formalize the JAXA multilingual support and this item should be closed. CLOSED
22-14 | T&S Task Team leaders to submit their reports to Paul Kopp by Oct-15-2006. | T&S Task Team Leaders | 2006-10-15 | CLOSED | - Oct 19, '06 GD: Email sent. - Oct 20 06, LD: Will provide report by Oct 25th. GD email to PK indicating that I will keep the item open and follow-up in a few weeks with him. - 27 September 2007: Item complete - closed as a part of action item cleanup. CLOSED
22-15 | P&A Task Team leaders should submit their reports to Pakorn by Oct-15-2006. | P&A Task Team Leaders | 2006-10-15 | CLOSED | - Oct 19, '06 GD: Email sent. - Oct 20 06, LD: Will provide report by Oct 25th. SM indicated that she had sent her report to Pakorn. - Oct 24 06, PA: Inputs were received from PA TT Leads. CLOSED
22-16 | Provide the deadline for submission of the WGISS report to CEOS Plenary. | Ivan Petiteville | 2006-09-01 | CLOSED | - Sept 20: IP reported that reports need to be to CEOS by Nov 1st, 2006 and that WGISS Sub Group reports are due by Oct 15th, 2006. CLOSED
22-17 | Confirm if SAFE is going to be a CCSDS format. | Gian Maria Pinna | 2006-10-01 | CLOSED | - Oct 19, '06 GD: Email sent. - 27 September 2007: Ivan discussed by email with Gian. Item closed as a part of action item cleanup. CLOSED
22-18 | Request to the WGISS-23 POC in Vietnam that all invitees receive an invitation letter to WGISS-23 to support visa proceses. | Satoko Miura | 2006-10-01 | CLOSED | - Oct 5, SM: VNRSC will prepare invitation letter to all registered participants. Now we are planning to open the registration web site in February, 2007. So if you need more than 3 months to obtain your VISA, please let me know. CLOSED
22-19 | Coordinate with Bernhard Buckl to discuss a change of date of WGISS-24 back to originally proposed date of the week of October 8-12 2007. | Ken McDonald | 2006-10-01 | CLOSED | - Oct 19, '06 GD: Email sent. - Nov 21, KM: This date change has been agreed by Bernhard, date will be confirmed and then this item can be closed. - Nov 30, KM: Confirmed that date for WGISS-24 has been moved to Oct 15-19, 2006. CLOSED
22-20 | Follow-up with Brian McLeod on the Canadian representation to WGISS in order to discuss the prospects for hosting a WGISS meeting in 2008. | Ken McDonald | 2006-10-01 | CLOSED | - Oct 19, '06 GD: Email sent. - 27 September 2007: Martha Maiden has taken over discussions on future WGISS meeting locations. CLOSED
22-21 | Discuss with Bernhard Buckl the possibility of having a three-way meeting between WGISS, WGCV and WGEdu (and possibly the CEOS SIT) in conjunction with WGISS-24 in September 2008. | Ken McDonald | 2006-10-01 | CLOSED | - Oct 19, '06 GD: Email sent. - 27 September 2007: Martha Maiden has taken over discussions on future WGISS meeting locations. CLOSED
22-22 | Discuss the prospects of a joint WGISS, WGCV and WGEdu meeting, possibly in the WGISS-24 timeframe, with the CEOS SIT, and if the response is positive then with the chairs of WGCV and WGEdu. | Ivan Petiteville | 2006-10-01 | CLOSED | - Oct 19, '06 GD: Email sent. - Nov 21, KM: WGCalVan is not interested in WGISS-24, but is proposing Feb-08 in China as a joint meeting. WGEdu was interested in the possibly of joining for WGISS-24. - Feb 13, '07: KM indicated that WGEdu has agreed to have some joint sessions at WGISS-24. Logistics and agenda to be worked out. - 27 September 2007: Martha Maiden has taken over discussions on future WGISS meeting locations. CLOSED
22-23 | Add a link to the GEO website documents listing to the documents section of the WGISS website. | Stuart Doescher | 2006-10-01 | CLOSED | - Sept 29, SD: Completed. CLOSED
22-24 | Coordinate the addition of the WGISS POC’s addition to the GEO Task mailing list for each GEO Task. | Osamu Ochiai | 2006-10-01 | CLOSED | - Oct 4: Received confirmation from GEO that our POCs had been added to the GEO task mailing lists. CLOSED
22-25 | Schedule a telecon between the WGISS GEO Task POC’s to discuss their progress in making contact with the GEO Task POC’s. This telecon should be held in early November, 2006. | Ken McDonald | 2006-11-01 | CLOSED | - Oct 19, '06 GD: Email sent. - Oct 27 06, KM: Meeting will likely take place after the CEOS Plenary meeting. - Nov 21, KM: Planning to setup this telecon for the week of Nov 27 pending feedback from the WGISS GEO group. - Jan 31, 2007: GEO Reps attended December WGISS-EXEC telecon and reported their current status. CLOSED
22-26 | Remind WGISS-22 participants to verify the list of presentation slides available on the FTP site (http://wgiss.ceos.org/ftp/WGISS22). Any missing presentations should be emailed to Stuart Doescher. September 2006. | George Dyke | 2006-09-01 | CLOSED | - Sept 20: GD sent email reminder to WGISS-ALL. - Sept 29: All presentations received. CLOSED
22-27 | Send the draft Report to the CEOS Plenary-20 presentation to WGISS-EXEC, Task Team Leads. | Ivan Petiteville | 2006-09-01 | CLOSED | - Sept 19: IP circulated a draft of the CEOS report to SIT to WGISS-EXEC, still working report to Plenary. - Oct 19 06, GD: Email to request latest status sent. - Nov 21, 06, GD: Draft report was distributed, revieiwed and finalized. CLOSED
22-28 | WGISS-EXEC and Task Team Leads to review the draft presentation CEOS Plenary-20 and provide feedback to Ivan Petiteville. | WGISS-EXEC and Task Team Leads | 2006-10-01 | CLOSED | - Oct 19, '06 GD: Email sent. - Nov 21, GD: Item closed - presentations were reviewed, feedback was given, and the persentation has been given. CLOSED
22-29 | Contact member CEOS agencies to provide information for an IDN entry to support an IDN Portal for CEOS member agencies. | Wyn Cudlip, Lola Olsen | 2006-10-01 | Open | - Oct 19, '06 GD: Email sent.
22-30 | Coordinate an session sharing of experiences of working with Google Earth or like visualization products. | Paul Kopp | WGISS-25 | Open | - 28 September 2007: PK requested to delay until WGISS-25.
22-31 | Provide information to WGISS-ALL on the expected quality of the network connection at WGISS-23. | Satoko Miura | 2006-11-01 | CLOSED | Oct 5, SM: At Melia Hanoi Hotel, the meeting venue, we will have "ONE" ADSL internet network with speed 1024Kbs. So, if you are planning to make a demo using internet, please keep it in mind that you will have to share this network with all other participants. CLOSED
22-32 | Coordinate the identification of the next Technology & Services Subgroup Vice Chair. | Paul Kopp | WGISS-23 | CLOSED | - 27 September 2007: People for these roles were identified at WGISS-23. CLOSED
22-33 | Create a WGISS-Representative mailing list based on the current WGISS-Representatve list on the WGISS website. The address will be wgiss-reps@wgiss.ceos.org. | Stuart Doescher | 2006-10-01 | CLOSED | - Sept 19: SD created this email list and forwarded the information to IP, GD, KM. - Oct 19, '06: Email sent. - 27 September 2007: Mailing list created and in use. CLOSED
22-34 | Contact members of wgiss-reps@wgiss.ceos.org and confirm they are the correct WGISS POC, or to give an updated WGISS POC. | Ivan Petiteville | 2006-10-01 | CLOSED | - Sept 20: IP emailed the list of representitives requesting an update of their status. - Jan 31, 2007: 2-3 responses have been received to date out of 60-70 members on the list. - 27 September 2007: Closed as a part of the action item clenup. CLOSED
22-35 | Coordinate a focused test team on an online collaborative tool for WGISS ('discussion forum'+). | Stuart Doescher | 2006-11-01 | CLOSED | - Sept 19: SD has sent GD a link to an online colloboration space that will be evaluated over the coming weeks. - Oct 19, '06: Email sent. - 27 Setember 2007: Severa discussions took place, but no definitive solution was determined. WITT responsibilities will transition after WGISS-24, and that group will decide future directions. CLOSED
23-1 | Ivan to distribute JAXA’s (Chu Ishida) analysis of the space segment of the SBAs defined in the CEOS IP to WGISS-ALL. | Ivan Petiteville | 2007-06-01 | CLOSED | - 7 June 2007: Ivan distributed the analysis to WGISS-ALL. CLOSED
23-2 | Ivan to distributed the targets and actions outlined in the CEOS IP to WGISS-ALL. | Ivan Petiteville | 2007-06-01 | CLOSED | - 7 June 2007: Ivan distributed the CEOS IP targets and actions to WGISS-ALL. CLOSED
23-3 | Ivan to provide Doug Nebert’s presentation on the GEOSS Component Registry to Lyn to upload to the WGISS-23 FTP server for group access. | Ivan Petiteville | 2007-06-01 | CLOSED | - 7 June 2007: Ivan distributed the presentation to WGISS-ALL. CLOSED
23-4 | Satoko to inquire about the details of the IP3 program to determine if the WTF CEOP could be of use to this program. | Satoko Miura | 2007-06-01 | CLOSED | - 11 October 2007: SM reported that there is no requirement/needs for WTF-CEOP participation in IP3. CLOSED
23-5 | Paul Kopp to provide Nguyen Thi Thuy Hang (ahangk3@gmail.com) with contact information for WGEdu and the WGISS website URL to the educational CD ROM. | Paul Kopp | 2007-06-01 | CLOSED | - 30 June 2007: PK provided these details. CLOSED
23-6 | Ivan to request all WGISS agencies with significant data archives to provide a name for a representatives on the ATT. | Ivan Petiteville | 2007-06-01 | Open
23-7 | Kengo to review the GEO Task DA-07-06 and advise if WGISS has a role to play in this task. | Kengo Aizawa | June 30 2007 | CLOSED | - 28 June 2007: AK sent a plan for JAXA to monitor this task and provide further recommendations if there are any. CLOSED
23-8 | Arturo to report back to WGISS-All on the awareness of the GEO task teams of the new IDN portals that have been created for those GEO tasks, and clarify what reviews are currently underway for the new GEO portals. | Arturo Restrepo | 2007-08-01 | CLOSED | - 23 June 2007: Lola and Aurturo distributed a memo describing the portals that are currently in place, and will register the GEO task IDN portals in the GEO registry this week. CLOSED
23-9 | Ivan to forward the web link for the most recent IDN Newsletter to the CEOS community (WGISS-ALL, CEOS-SEC) as soon as it published by the IDN team. And to determine if it can be circulated on an ongoing basis by the CEOS SEC. | Ivan Petiteville | 2007-06-01 | CLOSED | - 7 June 2007: Ivan distributed the most April 2007 IDN Newsletter to WGISS-ALL and the CEOS-SEC. Ivan to circulate to CEOS-SEC on an ongoing basis. CLOSED
23-10 | Arturo (IDN Team) to assess the differences between the platform and instrument descriptions in the IDN and those contained in the CEOS database (CEOS Earth Observation Handbook). | Arturo Restrepo | WGISS-24 | CLOSED | - 28 September 2007: Material to be presented at WGISS-24. - 30 September 2007: Material sent by email by Lola, to be presented at WGISS-24. - WGISS-24: A summary of the differences between the playform and instrument descriptions in the IDN and the CEOS EO Handbook was presented during the IDN session. CLOSED
23-11 | Osamu to coordinate participation for a GEO representative to attend the SUWG meeting June 19-20 at NASA/Goddard. | Osamu Ochiai | 2007-06-01 | CLOSED | - 12 June 2007: Ivan sent a reminder to Osamu on this item. - 27 Semteber 2007: CLOSED
23-12 | Yonsook to provide the contact information of the eGY representative for the ‘narrated Power Point’ initiative to WGISS-ALL. | Yonsook Enloe | 2007-06-01 | CLOSED | - May 31, 2007: Yonsook provided the details and contact information by email. CLOSED
23-13 | Kathy to coordinate with Kengo and the eGY to discuss the possibility of having an extended ATT session at WGISS-24 to which eGY members and participants would be specifically invited. | Kathy Fontaine | WGISS-24 | Open
23-14 | George to distribute the CEOS level conference proposal to WGISS-ALL. | George Dyke | 2007-06-01 | CLOSED | - 27 June 2007: George emailed the most recent draft of the CEOS Conference proposal. CLOSED
23-15 | Ivan to contact the IEEE representative to determine if its possible to hold the 2008 EOGEO meeting in conjunction with IEEE-GEOSS. | Ivan Petiteville | 2007-06-01 | Open | - 7 June 2007: Ivan sent an initial contact email.
23-16 | Bernhard to contact the organizers of the PV 2007 conference to investigate announcing WGISS-24 on the PV 2007 conference website. | Bernhard Buckl | 2007-07-01 | CLOSED | - 27 June 2007: Bernhard emailed indicating that he has coordinated with the PV 2007 organizers. CLOSED
23-17 | Kengo to investigate getting speakers at the WGISS-24 ATT session from the participants of PV 2007. | Kengo Aizawa | WGISS-24 | CLOSED | - 27 September 2007: Kengo, Bernhard and Ivan have worked this over the past couple of months. CLOSED.
23-18 | Terence to distribute the details of the DA-07-04 use case and project time lines to WGISS-ALL. | Terence van Zyl | 2007-06-01 | CLOSED | - 2 July 2007: TvZ provided the task details to WGISS-ALL. CLOSED
23-19 | Stu to create a WGISS email list to facilitate the work of the WGISS Sensor Web investigation team. | Stuart Doescher | 2007-06-01 | CLOSED | 18 July 2007: Stu has setup these lists. CLOSED
23-20 | George to contact WGISS agency representatives to invite and encourage their Sensor Web experts to attend discussions at WGISS-24. | George Dyke | 2007-06-01 | CLOSED | - 27 September 2007: George send email to WGISS-REPs. CLOSED
23-21 | Ivan to send an invitation to WGISS-ALL to Sensor Web experts to attend WGISS-24. | Ivan Petiteville | 2007-06-01 | Open
23-22 | The IDN team (Lola Olson) to perform a detailed analysis of user query patterns and present a summary of usage patters and lessons learned at WGISS-24. | Lola Olson | WGISS-24 | CLOSED | - WGISS-24: A summary of the usage patterns was presented during the IDN session at WGISS-24. CLOSED
23-23 | The ATT (Kengo) to provide Paul Kopp with feedback and comments on the Interoperability Handbook. | Kengo Aizawa | 2007-07-01 | CLOSED | - 3 July 2007: AK provided comments to PK on the IO Handbook. CLOSED
23-24 | ATT (Kengo) to survey representitives (wgiss-reps@wgiss.ceos.org) all WGISS member agencies requesting a listing and details of their agency FDCRs to facilitate the completion of GEO climate action C-18. The wgiss-reps mailing list can be used to reach the appropriate. | Kengo Aizawa | 2007-07-01 | Open | - 2 August 2007: KA circulated a request for agencies to respond with the details of the FDCRs by the end of August.
23-25 | Martha to give a copy of the Climate Action Status document Kengo for analysis and to Lyn for posting on the WGISS-23 FTP site. | Martha Maiden | Complete | CLOSED | - WGISS-23: CLOSED
23-26 | Ben Burford to inform the WA-06-02 GEO Task Team of the existence of the WTF-CEOP in situ database for use in this task. | Ben Burford | 2007-06-01 | CLOSED | - 12 October 2007: I have just received an email from John Schaake where he acknowledges understanding of the WTF-CEOP in-situ database. He is currently receiving information on the in-situ data from Steve Williams, leader of the CEOP in-s itu data archive. CLOSED
23-27 | Stu to create a WGISS email list relating to the Virtual Constellations project. (Initial members: Martha, JP, Kathy, Ivan, Satoko) | Stuart Doescher | 2007-06-01 | CLOSED | - 11 August 2007: SD created the list and sent the details to Ivan. CLOSED
23-28 | Martha Maiden to inquire with Ken MacDonald on his interest in being involved in the WGISS response to DA-07-06. | Martha Maiden | 2007-06-15 | CLOSED | - 6 July 2007: MM reported that KM responded that he would like to be involved in DA-07-06. CLOSED
23-29 | Guoqing to inquire with Luigi Fusco about the registration of ESA GRID on-Demand with the GEO component registry. | Guiqing Li | 2007-06-01 | CLOSED | - 27 June 2007: Li has coordinated with Luigi, and ESA has registered its component (Earth Observation Grid Processing on Demand) in the GEO Component Registry. CLOSED
23-30 | Ivan to ask Christophe Caspar to share his experience in working with GML-2 and GML-3 for contribution to recommendation 11 of the Interoperability Handbook. | Ivan Petiteville | 2007-06-01 | CLOSED | - 7 July 2007: IP reported his findings as input to the IO Handbook process. CLOSED
23-31 | George to request WGISS Task Team leaders to review the WGISS-23 GFZ agency report (Include FTP Link) to identify topics of interest to their Task Teams and follow up with Bernd on possible WGISS-24 presentations. | George Dyke | 2007-06-01 | CLOSED | - 27 September 2007: GD sent email. CLOSED
24-1 | Ivan Petiteville to distribute the draft paper published by IGOS and the GEO SEC outlining the plan to transition the IGOS Themes to GEO. | Ivan Petiteville | 2007-11-01 | CLOSED | - 30 October 2007: IP distributed he paper. CLOSED
24-2 | Ken McDonald (WITT) to have the DNS pointing for data.ceos.org removed from the CEOS DNS settings. | Ken McDonald | 2007-11-01 | Open
24-3 | Ken McDonald (WITT) to have the wgedu.ceos.org DNS entry re-pointed to the homepage WGEdu homepage in order to ensure consistency with WGISS and WGCalVal. WITT should contact the WGEdu representative to determine the correct IP address for their homepage. | Ken McDonald | 2007-11-01 | Open
24-4 | Martha Maiden (WGISS Chair) to work with the WGCV Chair to add the CalVal Portal topic to the joint WGISS-WGCV meeting. | Martha Maiden | WGISS-25 | Open
24-5 | Lyndon Oleson to provide a closure report for the WTF Core Sites portal. | Lyndon Oleson | WGISS-25 | Open
24-6 | Lyndon Oleson to add a link to calval.ceos.org and the WTF Core Sites closure report to the WTF Core Site homepage. | Lyndon Oleson | WGISS-25 | Open
24-7 | Wyn Cudlip to register the guidelines documents for implementing OGC Web Coverage and Web May Server to Serve Global Scale in the GEO components registry. The document should be re-hosted on the WGISS website and it should be pointed to at its WGISS URL. | Wyn Cudlip | 2007-12-01 | Open
24-8 | Ken McDonald (WITT) to create a services.ceos.org sub-domain which points to the ‘CEOS Services’ area of the IDN. Coordination with Tyler Stevens/IDN to determine where to point the sub-domain will be required. | Ken McDonald | 2007-11-15 | Open | - 1 November 2007: TS requetsted deadline bump to 11/15.
24-9 | Wyn Cudlip to coordinate with Tyler Stevens/IDN to ensure that CEOS member agencies services are registered in the ‘CEOS Services’ IDN portal. | Wyn Cudlip | COMPLETE | CLOSED | - 19 October 2007: This coordination has taken place. CLOSED
24-10 | Tyler Stevens (IDN) to register the services.ceos.org service in the GEO registry of services. | Tyler Stevens | 2007-11-15 | Open | - 1 November 2007: TS requetsted deadline bump to 11/15.
24-11 | Wyn Cudlip to write a report to summarize the accomplishments of the EO Data Portal Task Team to formalize the closure of this Task Team. | Wyn Cudlip | WGISS-25 | Open
24-12 | Ken McDonald (WITT) to review the historical task team repository on the WGISS website to capture the accomplishments and records of task teams that have been closed. | Ken McDonald | WGISS-25 | Open
24-13 | Kengo Aizawa to populate the ATT historical task team area of the WGISS website. | Kengo Aizawa | WGISS-25 | Open
24-14 | Ken McDonald (WITT) to migrate the WGISS Menu pages to the historical task archive on the WGISS website. Coordination with Wyn may be required. | Ken McDonald | 2007-11-01 | Open
24-15 | Wyn Cudlip to coordinate the presentation of options for how WGISS and WGCV could jointly contribute to the creation of an integrated global 30M DEM, specifically looking at how WGISS-WGCV could assist in filling the gaps in the US-Japanese Global 30m DEM. Martha will be involved on the WGISS-25 agenda scheduling for these presentations. | Wyn Cudlip | WGISS-25 | Open
24-16 | Kengo Aizawa to distribute his WGISS-24 presentation for WGISS member agencies to review for both accuracy and completeness of the data listings and portal websites outlined and provide comments to Kengo. | Kengo Aizawa | 2007-11-02 | Open
24-17 | WGISS member agencies to review for both accuracy and completeness of the data listings and portal websites outlined in Kengo's WGISS-24 presentation on GCOS actions C-18 and C-21 and provide comments to Kengo. | WGISS ALL | 2007-11-30 | Open
24-18 | Kengo to distribute a summary of responses received on the GCOS actions (WGISS-24-17) to WGISS ALL. | Kengo Aizawa | 2007-12-31 | Open
24-19 | Kengo Aizawa to prepare a final report of the Archive Task Team outlining the work and accomplishments of the task team. | Kengo Aizawa | WGISS-25 | Open
24-20 | Lyndon Oleson to lead a small group (former ATT members) who will generate a proposal to be presented at WGISS-25 of what steps could reinvigorate and refocus the handling of data preservation and archiving topics within WGISS. | Lyndon Oleson | WGISS-25 | Open
24-21 | Jean-Pierre Antikidis to check within CNES for a contributor to the discussion on the future of WGISS archiving topics and provide any possible names to Lyn. | Jean-Pierre Antikidis | 2007-11-01 | Open
24-22 | Karen Moe to check within NASA for contributors to the discussion on the future of WGISS archiving topics and provide any possible names to Lyn. | Karen Moe | 2007-11-01 | Open
24-23 | Guoquing Li to contact Mette LoycheWilkie (Mette.LoycheWilkie@fao.org) to explore possible links between WGISS GRID efforts, the work of China’s DFG and GEO Task and GEO Task AG-06-04. Ivan Petiteville should be kept in the loop on these communications. | Guoquing Li | COMPLETE | CLOSED | - 19 October 2007: This email contact has been initiated. CLOSED
24-24 | Tyler Stevens to coordinate the group of Bernd Ritschel, Jolyon Martin, Jean-Pierre Antikidis, Karen Moe, Wyn Cudlip and Terence van Zyl to create a list of requirements for evaluation by the IDN team and presentation at WGISS-25. These requirements shall describe an cross-mission search capability which would enable users to search missions and sensors by application. | Tyler Stevens | 2007-12-31 | Open
24-25 | Lyndon Oleson to coordinate a group to draft of new terms of reference for the DSTT for review and action at WGISS-25. | Lyndon Oleson | WGISS-25 | Open
24-26 | Chuang Liu to put Chinese experts in touch with the mid-decadal study group’s (Garik G.) data gap working group in order to coordinate possible gap filling data. | Chuang Liu | 2007-11-01 | Open
24-27 | Ivan Petiteville to distribute the web locations for the GEO videos to WGISS-ALL. | Ivan Petiteville | COMPLETE | CLOSED | - 19 October 2007: Ivan distributed this information to WGISS-ALL.
24-28 | Ken McDonald (WITT) to remove the WGISS ad hoc Sensor Web Use Case team email list. | Ken McDonald | 2007-11-01 | CLOSED | - 19 October 2007: This mailing list has been removed. CLOSED
24-29 | Ivan Petiteville to discuss with the CEOS SEC the possibility of CEOS becoming a supporting organization of CODATA/ICSU. | Ivan Petiteville | 2007-12-01 | Open
24-30 | Nataliia Kussul to speak with the organizers of CODATA-21 to determine what the emphasis of CODATA-21 will be, the details of a WGISS program for CODATA-21, the deadlines for submissions and report back to WGISS-25. | Nataliia Kussul | 2007-11-01 | Open
24-31 | Chuang Liu to distribute the description of the Global Road Task Force to WGISS-EXEC in order to assess if there is any WGISS role within this Task Force. | Chuang Liu | 2007-11-01 | Open
24-32 | Martha Maiden, with support from Dingsheng, to contact the WGISS-25 host organizer, Changyong Cao, to coordinate a letter of invitation to support the Chinese VISA application process for WGISS-25 participants. | Martha Maiden | 2007-10-26 | CLOSED | - 26 October 2007: Martha emailed instructions to WGISS-ALL on how to get the invitation letter sent to support VISA applications. CLOSED
24-33 | Ivan Petiteville (WGISS Chair) to create a draft update of the WGISS 5-Year plan for review by the incoming chair and discussion and agreement at WGISS-25. | Ivan Petiteville | 2007-12-15 | Open
24-34 | WGISS Task Team leaders to provide a list of activities for 2008 to be reported at WGISS-25. Task Team leaders are encouraged to circulate their task lists ahead of WGISS-25 to get feedback. | WGISS Task Team Leaders | WGISS-25 | Open
24-35 | Task Team, Subgroup leaders and WGISS Chair to review their WGISS web pages and send content updates to the Ken McDonald (WITT). | WGISS Task Team, Subgroup Leaders and Chair | 2007-12-31 | Open
24-36 | WITT (Ken McDonald) to add space for the WGISS Sensor Web Task Team to the WGISS Website in consultation with the SWTT leader, Terence van Zyl. | Ken McDonald | WGISS-25 | Open

## WGISSEXECActions
WGISS EXEC Action Items
| Last Updated | Last Updated By
| 2007-09-27 | G. Dyke
No. | Action | Who | By | Open/CLOSED | Status
EXEC1-1 | Circulate a high-level agenda for review to subgroup chairs plus IP/KF/KM for comment. | George Dyke | 2006-06-01 | CLOSED | - June 30, GD: Email sent, CLOSED.
EXEC1-2 | Circulate the draft WGISS response to the GEO WP. | Ken McDonald | 2006-07-01 | CLOSED | - Aug 18, KM: Emailed the summary of the WGISS response.
EXEC2-1 | Paul Kopp to send an updated version of Technology & Services Subgroup agenda. | Paul Kopp | 2006-08-06 | CLOSED | - Aug 31, PK: Emailed updated version.
EXEC2-2 | Ken McDonald and Ivan Petiteville to propose a detailed agenda for the WGISS-22 Thursday PM WGISS-GEO session. | Ken McDonald, Ivan Petiteville | 2006-08-06 | CLOSED | - Information provided
EXEC2-3 | George Dyke to poll WGISS-ALL to determine who would like to make an Agency and Representative Report at WGISS-22. | George Dyke | 2006-08-06 | CLOSED | - Aug 29, GD: Email sent.
EXEC2-4 | George Dyke to send out the most recent revision of the WGISS-22 agenda following the EXEC telecon. | George Dyke | 2006-08-06 | CLOSED | - Sept 1, GD: Emailed.
EXEC2-5 | All to review the participants list and remind key/regular people who are missing to register. The current attendance list can be found here: http://www.infonetic.com/tis/ceos-wgiss/documents/AttendeeList.pdf | All | 2006-08-06 | CLOSED
EXEC2-6 | Kathy Fontaine to provide detailed schedule for the WGISS-22 host workshop. | Kathy Fontaine | 2006-08-06 | CLOSED | - Information provided
EXEC3-1 | Ken to propose a plan for future WGISS meeting formats for the 2008 timeframe to the EXEC. A discussion of this plan to follow at WGISS-23. | Ken McDonald | 2006-12-01 | CLOSED
EXEC3-2 | George to follow up with ISO to determine the origins of the WGISS account request and report back to the WGISS-EXEC. | George Dyke | 2006-11-01 | CLOSED | - Nov 21, GD: Email sent a while back, no response yet. - Jan-31, 2007: No response, item closed.
EXEC3-3 | George to coordinate the time of day for the WGISS-EXEC-4 (Nov-2006) and WGISS-EXEC-5 (Dec-2006) meetings. | George Dyke | 2006-11-01 | CLOSED | - Nov 21, GD: Meeting time set for these meetings. CLOSED
EXEC4-1 | George to undertake the process of reviewing and closing and/or closing and re-opening WGISS Action Items that were open prior to WGISS-21. | George Dyke | 2007-01-07 | CLOSED | - 27 September 2007: Process complete. CLOSED
EXEC5-1 | Kathy to report back to WGISS EXEC and WGISS GEO POCs on the outcome of the ADC meeting being held on December 19-20. | Kathy Fontaine | 2006-12-01 | Open | - Jan 31, 2007: This report was given by Ivan and Kathy. CLOSED
EXEC5-2 | Kathy to send out a list of revised GEO Task POCs for distribution to the relevant people by way of the WGISS EXEC email list. | Kathy Fontaine | 2007-12-06 | CLOSED | - Jan 31, 2007: The list has been sent out. CLOSED
EXEC5-3 | George to coordination of the selection of a WGISS EXEC meeting date for late January. | George Dyke | 2007-12-06 | CLOSED | - Meeting scheduled.
EXEC6-1 | Ivan to inquire with all CEOS Representatives on the availability of expertise on the Sensor Web task. | Ivan Petiteville | 2007-02-01 | CLOSED
EXEC6-2 | Ivan to contact the South African CEOS Representative to inquire if they have any members who would be willing to join WGISS to provide expertise on the Sensor Web task. | Ivan Petiteville | 2007-02-01 | CLOSED | - March 14, 2007: IP forwarded positive response from CSIR representitive reguarting Sensor Web participant. CLOSED
EXEC6-3 | Ivan to ask WGISS members to inquire with their agencies as to what efforts are going on in support of the Sensor Web task and report back to the WGISS-EXEC. | Ivan Petiteville | 2007-02-01 | CLOSED
EXEC6-4 | Pakorn to coordinate the Workshop planning for WGISS-23, and report back to the WGISS EXEC on the proposed details. | Pakorn Apaphant | 2007-02-01 | CLOSED | - March 21, 2007: Pakorn provided current draft of the Host Workshop agenda. CLOSED
EXEC6-5 | George to put together a skeleton of the WGISS-23 agenda, including items identified in the previous meetings, and actions to kick-off the WGISS-23 agenda planning process. | George Dyke | 2007-02-01 | CLOSED | - Feb 12, 2007: GD sent a draft to IP and KM for review and eventual distribution to WGISS-EXEC. CLOSED
EXEC6-6 | Ivan to circulate the Definition of Terms document discussed at the ADC meeting. | Ivan Petiteville | 2007-02-01 | CLOSED | - March 14, 2007: IP forwarded definition of terms document. CLOSED
EXEC6-7 | Ivan to send a reminder to WGISS members to provide input to Paul Kopp on the most recent version of the Interoperability Handbook. | Ivan Petiteville | 2007-02-01 | CLOSED
EXEC6-8 | Paul to send a reminder to the ATT (Chapter 2) and DSTT (Chapter 3) for their contributions to the Interoperability Handbook. | Paul Kopp | 2007-02-01 | CLOSED | - April 24: Paul confirmed that the reminder has been sent.
EXEC6-9 | George to coordination of the selection of a WGISS EXEC meeting date for the week of March 5th. | George Dyke | 2007-02-01 | CLOSED | - Feb 1, 2007: Email sent by George requesting date inputs. - Feb 12, 2007: Likely date is 15th March 2007. Sent email to Ken and Ivan asking for confirmation before sending date to EXEC. CLOSED
EXEC7-1 | George to update the current draft of the WGISS-23 agenda to reflect Martha’s leadership of the GEO related topics. | George Dyke | 2007-03-31 | CLOSED | - A draft has been preprated and distributed. CLOSED
EXEC7-2 | Ken and Martha to solicit an update from the WGISS GEO POC’s on the progress made to date. | Ken McDonald, Martha Maiden | EXEC-8 | CLOSED
EXEC7-3 | Ken and Martha to review the newly accepted GEO 2007-2009 Work Plan to begin the process of identifying potential WGISS contributions. | Ken McDonald, Martha Maiden | EXEC-8 | CLOSED
EXEC7-4 | Ivan to coordinate a technical session at WGISS-23 to discuss GEO Data Architecture and what the WGISS contribution could be to this the GEO Data Architecture. | Ivan Petiteville | EXEC-8 | CLOSED | - April 24: This has been included in the WGISS-23 agenda.
EXEC7-5 | Pakorn to distribute a draft agenda to WGISS-EXEC for the WGISS-23 Host Workshop. | Pakorn Apaphant | 2007-03-31 | CLOSED | - March 21, 2007: Pakorn sent current draft. CLOSED
EXEC-8-1 | Ivan to distribute the new GEO Task Sheets to the WGISS-EXEC list. | Ivan Petiteville | 2007-04-30 | Open | - April 26, 2006: Ivan sent the updated task sheets. CLOSED
EXEC-8-2 | Ivan to inquire with CEOS and/or GEO representatives when the 2007-2009 Work Plan will be released to support the process development of WGISS support to GEO. | Ivan Petiteville | WGISS-23 | Open | - April 24, 2006: Ivan has sent the most recent draft of the 2007-2009 work plan. CLOSED.
EXEC8-3 | Martha to coordinate the planning of the Thursday afternoon GEO session at WGISS-23 along with Ivan, Ken and George. | Martha Maiden | 2007-05-07 | CLOSED
EXEC8-4 | George to inquire with Satako and Pakorn on who will give the Welcome Address at WGISS-23 to update the agenda. | George Dyke | 2007-05-07 | CLOSED
EXEC8-5 | Kathy to distribute a draft of the P&A subgroup agenda for WGISS-23. | Kathy Fontaine | 2007-05-02 | CLOSED
EXEC8-6 | Paul to distribute a draft of the T&S subgroup agenda for WGISS-23. | Paul Kopp | 2007-05-02 | CLOSED
EXEC8-7 | George to ask Satoko about general adjournment requirements, as well as if there are any specific evening events planned for the week, or anything specifically on Wednesday. | George Dyke | 2007-05-07 | CLOSED
EXEC8-8 | George to renew the call for liaison and agency reports. | George Dyke | 2007-05-07 | CLOSED
EXEC8-9 | Ivan to invite EXEC members for the evening of Sunday, 20th May. | Ivan Petiteville | 2007-05-07 | CLOSED
EXEC9-1 | Ivan to contact the Indian CEOS representative to discuss Indian support of the CEOS Working Groups. | Ivan Petiteville | EXEC-10 | Open
EXEC9-2 | Martha to work with Kengo on the GCOS action items discussed at WGISS-23. | Martha Maiden | EXEC-10 | Open
EXEC9-3 | Martha to contact the CEOS Plenary support team (Tim Stryker) to offer WGISS support for the CEOS Presentation to the GEO Ministerial. | Martha Maiden | EXEC-10 | Open
EXEC9-4 | Ivan to send an invitation to the PV 2007 Conference Chair to attend WGISS-24. | Ivan Petiteville | EXEC-10 | Open
EXEC10-1 | Martha to coordinate the videos that were recently shown at the GEO ADC during the Thursday afternoon GEO session at WGISS-24. A focus should be made on topics to which WGISS members have contributed. | Martha Maiden | 2007-10-01 | Open
EXEC10-2 | Bernhard to send the Host Workshop schedule to George. | Bernhard Buckl | 2007-09-28 | CLOSED | - 20 September 2007: BB sent George the schedule.
EXEC10-3 | Bernhard to distribute an overview of the bus logistics for WGISS-24 to WGISS-ALL. | Bernhard Buckl | 2007-10-05 | CLOSED | - 21 September 2007: BB send email to WGISS-ALL.
EXEC10-4 | Dingsheng to send George the detailed schedule for the T&S Subgroup session at WGISS-24. | Dingsheng Liu | 2007-09-28 | Open
EXEC10-5 | Pakorn to send George the detailed schedule for the P&A Subgroup session at WGISS-24. | Pakorn Apaphant | 2007-09-28 | Open
EXEC10-6 | George to distribute the action items due at WGISS-24. | George Dyke | 2007-09-26 | CLOSED | - 27 September 2007: Distributed by email. CLOSED
EXEC10-7 | Ivan to contact Bernhard to suggest a location near or at the hotels for a pre-WGISS-24 meeting on the Sunday evening before WGISS-24 and distribute the details to WGISS-EXEC. | Ivan Petiteville | 2007-10-01 | CLOSED | - 21 September 2007: Ivan sent email.