## Slide 1: Status of Current WGISS/CEOS -GEO Tasks and Actions
Pakorn Apaphant
September 22, 2008

## Slide 2: WGISS Contribution
Currently WGISS engages in 8 GEO tasks
  AR-07-02, CL-06-02, DA-07-03, DA-07-04, DA-07-06, HE-06-03, HE-07-01, WA-06-07
Actions on these tasks are considered as
  category 1 5 actions
  category 2 2 actions
  category 3 3 actions
  category 4 0 actions
WGISS Action leads have been actively contribute to those actions
WGISS chair also regularly reported the significant process to CEO monthly telecon
CEOS GEO category 1 actions are on schedule
The Task Sheets of the GEO 2007-2009 Work Plan have been updated and are now available on the GEO FTP site ftp://ftp.wmo.int/Projects/GEO/TaskSheets/2008-09/

## Slide 3: CL-06-02
Key Climate Data from Satellite Systems
led by the USA, CEOS, GCOS and WMO
Establish actions securing the provision of key data for climate studies and forecasting from satellite systems. Make relevant synergies with Tasks DI-06-13, CL-06-01, WA-07-02, AG-06-04, AG-07-01, AR-06-09, DA-07-01, DA-07-02, and AR-07-03 ("Virtual Constellations") in particular.

## Slide 4: CL-06-02_13
Conduct ACC/Climate Workshop for plans to construct CDRs for atmospheric ECVs
CAT 1
Contributing: Martha Maiden
Deliverable: October 15-17, 2008- Conduct CEOS ACC-3 / Climate Workshop at GISS
Status: “Workshop on Long Term Data Sets and Climate Modeling” planned by CEOS, and SPARC. Invitation letter sent Aug 6, signed by NASA (Hilsenrath/Maiden) and ESA (Zehner/Langen).
Next Steps: Workshop October 15-17 at GISS/NYC (will constitute 3rd ACC Meeting), and outcomes captured.

## Slide 5: CL-06-02_14 (Closed)
WGISS demonstrate access to visualization of long-term trends of CDRs of ECVs
CAT 1
Lead, Lola Olsen
April 1, 2008: Demonstrate initial portal prototype
Milestone: Complete IDN Portal for Climate Data Records demonstration (Sep 08)
Status: Draft URL for Climate Diagnostics Portal sent to Dr. Mitch Goldberg Aug 29 for comment and received enthusiastic feedback.

## Slide 6
Next Steps: Demo at WGISS-26. A plan and schedule for further development of features, additions of content, and updates are planned. When mature, advertise presence of this capability and provide tool for scientists to share their climate diagnostics visualizations.

## Slide 7: AR-07-02
Interface Implementation for GEOSS
Initial support has been expressed by CEOS, EC, ESA, IEEE, USGS, OGC, the Architecture and Data Committee, User Interface Committee and Capacity Building Committee.
With the objective to facilitate the implementation of information system interfaces, the "Clearinghouse Task" (AR-06-05) and the "GEO Webportal Task" (DA-06-07) are merged into this Task. The primary outcome of this Task will be to solicit an official GEOSS Web Portal and Clearinghouse search facility to be able to access GEOSS components. In addition, this Task will include development of services accessible through GEOSS Interoperability Arrangement to support the GEOSS Societal Benefit Areas. Such web services are particularly needed for Health, Biodiversity and Ecosystem. This Task should develop the implementation framework of GEOSS in coordination with the AR-07-01. Further it will include the relevant information on existing Earth Observation Capacity Building efforts and resources. The User Interface Committee and Capacity Building Committee will support the Architecture and Data Committee in overviewing this Task.

## Slide 8: AR-07-02_1
Contribute to implementation of Sensor Interoperability Session in GEO Architecture Implementation Pilot (AIP)
CAT 1
Lead, Terence Van Zyl
Milestone: Kick off workshop (Sep 08)
Status: WGISS Sensor Web Project and Terrence Van Zyl responded to CFP, attended the Kick-Off Workshop in Boulder
Next Steps: Engage in architecture implementation phase 2.

## Slide 9: AR-07-02_2
Participate in AIP to evaluate GEOSS portal/clearinghouse interface
CAT 1
Lead: Satoko Miura
Milestones:
  AIP Kick off meeting will be held . More detailed work plan for CY2008 and beyond will be clarified (Sep 08)
  Evaluation result interface protocol between JAXA server and one of GEOSS portal/clearinghouse candidates (Mar 09)
Status: Responded to CFP, attended the Kick-Off Workshop in Boulder
Next Steps: Participate with catalog server, WMS server and client to provide evaluation of interface protocol between JAXA server and GEOSS portal/clearinghouse (when identified).

## Slide 10: DA-07-03
Virtual Constellations
Initial support has been expressed by CEOS
The Task has the purpose to advocate rapid development of the “CEOS Constellations Concept”. Observations from a virtual constellation would provide better temporal, spatial, and spectral resolution and related data management and dissemination. A series of virtual constellations are in definition by space agencies, in consultation with user communities within the CEOS framework, each being designed to address a significant implementation challenge, and each addressing key GEOSS observation gaps in the process.

## Slide 11: DA-07-03_5
Provide a demonstration of prototype of an LSI Constellation Portal
CAT 1
Lead, Lyndon Oleson
Milestone: Demonstrate a prototype LSI Constellation Portal at the CEOS WGISS #26 (Sep 08)
Status: Portal Project Progress Since Feb, 2008
  Comprise Team
  Construct Initial Build: Draft Prototype sent to LSI Study Team August 21 for comment and feedback.
  2nd Iteration to LSI Study Team focused content

## Slide 12: HE-06-03
Forest Health Hazards
Led by France and WMO
Facilitate the formation of international consortia and coordinate, besides advocating funding for, the implementation of major demonstration pilot-projects integrating Earth observations, health and epidemiological as well as socio-economic data. As a priority, a project initiated by THORPEX will focus on the use of advanced weather and climate ensemble forecasting methods to develop and improve the predictability of major health hazards and impacts in developing countries (e.g., West Africa).
The “Health and Climate Partnership for Africa”, established by THORPEX will be developed. Demonstration research projects and other relevant activities under the “Biodiversity, Ecosystem Services and Health” theme will be supported and co-ordinated internationally.

## Slide 13
The Task will also initiate projects to improve the processing of real-time and historical data and the development of models relating remotely sensed, in-situ, socio-economic and epidemiological data for detecting disease trends and the provision of early warning systems.
Part of this Task will include addressing the health impacts of a polluted and warming coastal ocean (e.g. contamination of seafood and bathing water, increased growth of harmful algal blooms, water-borne diseases, such as cholera, etc.).

## Slide 14: HE-06-03_2
Demonstrate a global smoke plume and dust forecasting product using multiple satellite product inputs
CAT 2
Contributing: Karen Moe (Sensor Web Interest Group)
Milestones:
  Conduct a statistical evaluation of the developmental automated aerosol forecast products. (May 09)
  Submit ROSES proposal (Applied Sciences, Decision Support) for global web-based satellite aerosol product distribution. (Aug 09)
Status: Jack Fishman/NASA is the lead; Karen Moe/NASA is the WGISS sensor web liaison to this health task
Next Step: supporting

## Slide 15: HE-07-01
Strengthen Observation and Information Systems for Health
Initial support has been expressed by CEOS.
The assessments carried out under tasks HE-06-05 and CB-06-01 will indicate how current observation systems can be better coordinated and will identify how gaps can be filled with new observational data. The consultations on requirements and priorities envisaged in Task HE06-01 will continue under this Task.

## Slide 16
Pilot projects will be initiated to improve in-situ environmental and health data collection for the utilisation and validation of remotely sensed data relevant to health, as well as to explore how the GEOSS will provide for the collection and distribution of information relevant to the diverse needs of the health community. To meet the target of developing an integrated global public health ﻿information network database, it will be necessary to begin the planning process to define necessary tools, interoperability standards, architecture and infrastructure, and user communities, in order to provide input into the GEO architecture and data development phase. This process will be initiated with a workshop involving all stakeholders.

## Slide 17: HE-07-01_1
Develop plan for efficient imagery access to support modeling, forecast and monitoring of health issues
CAT 2
Led by Murielle Lafaye (CNES) (WGISS is requested and offered to provide support)
Milestones: to be planned (June 09)
Status: CEOS Health SBA to participate in WGISS-26
Next Step: To find possible contribution and Task lead

## Slide 18: DA-07-04
Sensor Web Enablement for In-Situ Observing Network Facilitation
Initial support has been expressed by OGC, South Africa and IEEE.
﻿
The GEOSS scope includes spaceborne, airborne and ground based observing systems of the Earth’s environment. While the infrastructure for acquisition, processing and distribution of spaceborne sensing has become active in the past few decades, there has been less development of ground based sensing networks. With advances in communications technology and ground-based in-situ technologies it is now feasible to consider webs of sensors on all types of platforms with rapid access for observations. This technology has been developed

## Slide 19
under the names of Sensor Webs and Sensor Networks. The Task should develop scenarios or us e cases that demonstrate the value of Sensor Webs to the GEOSS SBAs. For example, specific domains that can benefit from sensor web are possibly disasters, health (relevant synergies with HE-07-01), biodiversity, ecosystem and water. The Task should evaluate the applicable standards and coordinate with AR-07-01 suitable for Sensor Webs.

## Slide 20: DA-07-04_1
Sensor Web Interest Group work with Fishman/Hilsenrath to agree on prototype to support HE-06-03 by EO-1 tasking in support of smoke plume modeling.
CAT 3
Participating (WGISS): led by Terence Van Zyl (CSIR/WGISS)
Milestones:
  Use case and project plan for the prototype (Sep 08)
  Demonstration of prototype (Sep 09)
Status: finalizing discussions around use case
Next Step: Project plan for prototype

## Slide 21: DA-07-06
Data Integration and Analysis System
Initial support has been expressed by Japan.
It is expected that there will be a large increase in the volume of Earth Observation to distributed data archives and integration system, data management facilities will be used for diverse and large-volume Earth Observation data from inhomogeneous information sources in cooperation with existing data centers. This Task is to coordinate data management approaches that encompass a broad perspective of the observation data life cycle, from input through processing, archiving, and dissemination, including reprocessing, analysis and visualization of large volumes and diverse type of data.

## Slide 22: DA-07-06_1
Establish a Task Team, which would assist the Task Leads of DA-07-06 in enlisting interested data providers, sharing data integration methods, and organizing and participating in planned workshops
CAT 3
Lead, Satoko Miura
Milestones:
  Clarify the requirements to WGISS (Sep 08)
  Establishment of a Task team (Dec 08)
Status: preparing the letter and questionnaire to be sent to several "major" data centers in order to survey their activities/status/plan on data integration and analysis (Phase I survey). They are now preparing the plan to analyze the results of Phase I survey.
Next Steps: When requirements to WGISS is clarified, a Task team (interesting group or/& project) will be established.

## Slide 23: WA-06-07
﻿Capacity Building Program for Water Resource Management
led by IGOS-P.
Initiate capacity building programs to develop tools for using remote sensing data in support of water management, and to show the value of Earth observations generally in water resource management. The program will be initiated in Latin America and will then be extended to Asia and Africa. Linkages with existing efforts of GEO Members and Participating Organisations will be made.

## Slide 24: WA-06-07_4
Demonstrate Open Knowledge Environment (OKE), platform for showcase of applications.
CAT 3
Lead: Liu Chuang
Due Date: Dec 08
Status: Preparing showcase of applications
Next Step: Progress to be reported at WGISS-26