## Slide 1: Closing Report on WTF-CEOP Project Team
<number>
Satoko Horiyama MIURA/JAXA

## Slide 2: Contents
Project History
Lessons & Learned
Notes: <number>

## Slide 3: Purpose of WTF-CEOP
To provide assistance to the CEOP (Coordinated Energy and water cycle Observations Project ) science community in the development of data services associated with CEOP data integration.

## Slide 4: Goals and how they relate to WGISS
Develop a WTF-CEOP system, based on existing CEOS WGISS member tools and technology, for distribution of CEOP data, including:
  Support gathering satellite data from providers (JAXA, NASA, ESA, EUMETSAT)
  Support data discovery (search for CEOP data)
  Support data selection (through menu selection)
  Provide basic functions: plotting, viewing data, comparing data, downloading data
  Provide data integration functions: methods of integration of in-situ, model output and satellite data.

## Slide 5: Distributed Data Integration Services
Spatial and Temporal Data Integration - In-situ, MOLTS, Satellite, Model Output
Data location
Standalone physical location
Distributed sites reference by links
Data types
Model output data
Insitu data
Satellite data
Data sources
Services
Metadata keyword search
Data value search
File format translation
Reprojection
Regridding
Data Interpolation
Integrated datasets
Multiple files from individual member datasets
Spatial
Temporal
rectification
Spatial
Subsetting
Intercomparison
Of
Integrated Datasets

## Slide 6: WTF-CEOP Prototype
JAXA Prototype:
“Distributed Data Integration Prototype System for CEOP ”
Perl Module
Ferret
Web Browser
NCAR Archive [In-situ]
(U.S.)
MPI Archive
[MOLTS, Model Output]
(Germany)
CSDIC Archive [Satellite]
(Japan)
CEOP Data Archives
WCS Server
(satellite data)
NASA Prototype:
Enable OPeNDAP client access to WCS Servers to facilitate access to satellite data
OPeNDAP Interface
Custom Interface
GrADS
Live Access Server
Ferret
IDV
IDL
Matlab
NCO
Analysis / Display Tools
OPeNDAP Server
WCS Handler

## Slide 7: Development Schedule
Inputs from NASA needed
2006
2007
CEOP
CEOP Phase1
CEOP Phase2
2008
JAXA
Prototype
Development
March, 2008
Final version released
Development Completed
June, 2005
1st version released
2009
NASA
Prototype
Development
WTF-CEOP
Task Team
WGISS-26 (Septemebr, 2008)
Task Team Closed
2001
2002
2003
2004
2005

## Slide 8: Outreach Activities
Presentation at
  IGARSS-06 & 07
  AGU-06 & 07
  CEOP Science Meeting in March 2007
  CEOP Satellite Data Server proof of concept demo at eGY booth at 2006 Dec AGU meeting

## Slide 9: GEO Related Status & Issues
CEOS/GEO Task
  WA-07-01_2 : Release final version the WTF-CEOP JAXA Prototype system
    Closed in March, 2008
GEOSS Registries
  JAXA Prototype
    Registered on October 11th, 2007
  NASA Prototype
    To be registered soon

## Slide 10: Lessons & Learned
Transition
  Prototype activities completed.
  The target of WTF(WGISS Test Facility) is now satisfied.
  So what is the next step ?  to be explained in JAXA/NASA status.
Data Quality in meta data
Other details will be also reported in JAXA/NASA status.