## Slide 1: WGISS Way Forward on GEO actions and Plenary Agreement on Contributions to GEO
Pakorn Apaphant
September 26, 2008

## Slide 2: Way Forward on current GEO actions

## Slide 3: Way Forward on current GEO actions
5 closed actions
  CAT 1: CL-06-02_13, CL-06-02_14, AR-07-02_1 , DA-07-03_5,
  CAT 3: DA-07-04_1
5 ongoing Actions
  CAT 1: AR-07-02-2
  CAT 2: HE-06-03_2, HE-07-01_1
  CAT 3: DA-07-06_1, WA-06-07_4

## Slide 4: CL-06-02_13 (to be Closed)
Conduct ACC/Climate Workshop for plans to construct CDRs for atmospheric ECVs
CAT 1
Contributing: Martha Maiden
Deliverable: October 15-17, 2008- Conduct CEOS ACC-3 / Climate Workshop at GISS
Status: “Workshop on Long Term Data Sets and Climate Modeling” planned by CEOS, and SPARC. Invitation letter sent Aug 6, signed by NASA (Hilsenrath/Maiden) and ESA (Zehner/Langen).
Next Steps: Workshop October 15-17 at GISS/NYC (will constitute 3rd ACC Meeting), and outcomes captured.

## Slide 5: CL-06-02_14 (Closed)
WGISS demonstrate access to visualization of long-term trends of CDRs of ECVs
CAT 1
Lead, Lola Olsen
April 1, 2008: Demonstrate initial portal prototype
Milestone: Complete IDN Portal for Climate Data Records demonstration (Sep 08)
Status: Demo at WGISS-26. Awaiting for comments and input by Nov 1 for further development of features, additions of content, and updates are planned.
Next Steps: To be proposed for demonstration in the GEO-V plenary

## Slide 6: AR-07-02_1 (closed )
Contribute to implementation of Sensor Interoperability Session in GEO Architecture Implementation Pilot (AIP)
CAT 1
Lead, Terence Van Zyl
Milestone: Kick off workshop (Sep 08)
Status: closed with participation by many WGISS members, CFP has been answered

## Slide 7: AR-07-02_2
Participate in AIP to evaluate GEOSS portal/clearinghouse interface
CAT 1
Lead: Satoko Miura
Milestones: Evaluation result interface protocol between JAXA server and one of GEOSS portal/clearinghouse candidates (Mar 09)
Status: Attended the AIP Kick-Off Workshop in Boulder
Next Steps: Participate with catalog server, WMS server and client to provide evaluation of interface protocol between JAXA server and GEOSS portal/clearinghouse (when identified).

## Slide 8: DA-07-03_5 (Closed)
Provide a demonstration of prototype of an LSI Constellation Portal
CAT 1
Lead, Lyndon Oleson
Milestone: Demonstrate a prototype LSI Constellation Portal at the CEOS WGISS #26 (Sep 08)
Status: Beta version is ready. Demonstrated in WGISS 26.
Next Step: Lyn will coordinate with constellation lead for further comments and recommendations for the final version (by Oct 31) for the GEO-V Plenary

## Slide 9: HE-06-03_2
Demonstrate a global smoke plume and dust forecasting product using multiple satellite product inputs
CAT 2
Contributing: stephan Falke
Milestones:
  Conduct a statistical evaluation of the developmental automated aerosol forecast products. (May 09)
  Submit ROSES proposal (Applied Sciences, Decision Support) for global web-based satellite aerosol product distribution. (Aug 09)
Status: established atmospheric Constellation led by Stephan Falke, NASA
Next Step: WGISS (stephan Falke) collaborate with ACC members to
  Draft recommendations for a value-added ACC portal
  Evaluate extension of AIP air quality prototype for a smoke monitoring sensor web proposal

## Slide 10: HE-07-01_1
Develop plan for efficient imagery access to support modeling, forecasting and monitoring of health issues
CAT 2
Led by Murielle Lafaye (CNES) (WGISS is requested and offered to provide support)
Milestones: to be planned (June 09)
Status: CEOS Health SBA could not participate in WGISS-26
Next Step: CEOS Health SBA could not participate in WGISS-27 in Toulouse to find possible contribution and Task lead

## Slide 11: DA-07-04_1(Closed)
Sensor Web Interest Group work with Fishman/Hilsenrath to agree on prototype to support HE-06-03 by EO-1 tasking in support of smoke plume modeling.
CAT 3
Participating (WGISS): led by Terence Van Zyl (CSIR/WGISS)
Milestones:
  Use case and project plan for the prototype (Sep 08)
  Demonstration of prototype (Sep 09)
Status: Closed (duplication with HE-06-03_2)
Next Step: Project plan for prototype

## Slide 12: DA-07-06_1
Establish a Task Team, which would assist the Task Leads of DA-07-06 in enlisting interested data providers, sharing data integration methods, and organizing and participating in planned workshops
CAT 3
Lead, Satoko Miura
Milestones:
  Clarify the requirements to WGISS (Sep 08)
  Establishment of a Task team (Dec 08)
Status: preparing the letter and questionnaire to be sent to several "major" data centers in order to survey their activities/status/plan on data integration and analysis (Phase I survey). They are now preparing the plan to analyze the results of Phase I survey.
Next Steps: When requirements to WGISS is clarified, a Task team (interesting group or/& project) will be established.

## Slide 13: WA-06-07_4
Demonstrate Open Knowledge Environment (OKE), platform for showcase of applications.
CAT 3
Lead: Liu Chuang
Due Date: Dec 2008
Status: Preparing showcase of applications
Next Step: Preparing the demonstration, with URL to be informed

## Slide 14: Plenary agreement on Contributions to GEO

## Slide 15: Potential contributions to GEOSS (before remapping workshop)
LSI portal (WGISS PoC: Lyn)
  Expand LSI portal (inputs from GEO-V attendees)
  Proposed to be lead by the LSI Lead, with support of WGISS
Support Precipitation Constellation contribution to GEOSS (WGISS PoC: Karen)
  WGISS and Precipitation Constellation want to better understanding the scope of each group’s respective contributions to CEOS and GEOSS

## Slide 16: Potential contributions to GEOSS (Cont’)
To participate in DA-07-01 but not yet specify the actionable actions (WGISS PoC: Wyn)
  WGISS (Wyn) will work with the GEO Task lead to discuss and refine the requirements.
GRID Potential contribution to GEOSS (WGISS PoC: Dingsheng and Pakorn)
  NASU Flood Monitoring testbed (Natalia)
  CNES international WAG Project (Paul)
  NRSCC Disaster EO Data Aid Action (Li)
  WGISS Grid experts should be deeply involved in GEOSS ADC work. (Li)

## Slide 17: Demo at GEO-V Plenary
LSI Portal (finalized in Oct 08)
  WGISS PoC: Lyn
Climate Diagnostics Portal (to be proposed)
  WGISS PoC: Lola