## StatusSummary
WGISS Action Item Status Summary as of June-29-2006
| Due: Pre-June-2006 | Due: June-2006 | Due: WGISS-22 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 3 | 1 | 5 | 19 | 28
WGISS-21 | 1 | 9 | 6 | 7 | 23
Total | 7 | 10 | 11 | 30 | 58
WGISS Action Item Status Summary as of September 15, 2006
| Due: Pre-WGISS-22 | Due: WGISS-22 | Due: Post WGISS-22 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 9 | 0 | 0 | 19 | 28
WGISS-21 | 7 | 5 | 0 | 11 | 23
WGISS-22 | 0 | 0 | 27 | 0 | 27
Total | 19 | 5 | 27 | 34 | 85
WGISS Action Item Status Summary as of October 27 2006
| Due: WGISS-22 | Due: Oct-2006 | Due: Post Oct-2006 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 6 | 0 | 0 | 22 | 28
WGISS-21 | 7 | 0 | 1 | 15 | 23
WGISS-22 | 0 | 14 | 13 | 8 | 35
Total | 16 | 14 | 14 | 49 | 93

## WGISS-25 Actions
WGISS-25 Action Items
Last Updated 26 September, 2008 by M. Piepgrass
No. | Action | Who | By | Open/CLOSED | Status
25-1 | Martha will support Kengo to fulfill the CEOS IP CL-21 Action | Martha Maiden | 2008-05-01 | Closed | The GCOS ECVs provided by CEOS agencies have been made available on a protal in the CEOS IDN.
25-2 | Determine how to post on WGISS website the WGISS-GEO support information | Ken McDonald & Pakorn | 2008-05-01 | Closed | Incorporated into wgiss 26 action
25-3 | Provide a demonstration of a prototype LSI portal at WGISS-26 | Lyn Oleson | WGISS 26 | Closed
25-4 | Present a plan with milestones for continued enhancement and development of an LSI portal | Lyn Oleson | WGISS 26 | Closed | Ongoing in LSI interest group
25-5 | Contact WGISS all with information with request for interest in LSI Interest Group and LSI Portal Project | Lyn Oleson | 2008-04-02 | Closed
25-6 | Devise a way to capture WGISS lessons learned and best practices. | Karen Moe & Ken McDonald | 2008-05-01 | Closed | Developed a proposal for capturing WGISS lessons learned to present at WGISS-26
25-7 | Report to subgroup chair whether your task team should become an interest group, a project, or an interest group with one or more projects. | Task Team Leaders | 2008-04-02 | Closed | In process of moving to Interest Groups and Projects
25-8 | Get back to Pakorn about GEO action CL-06-02_14. | Ken McDonald | 2008-03-05 | Closed | Climate Diagnostics Portal created by Lola Olsen working with SBA lead Mitch Goldberg. GEO action is closed.
25-9 | Get back to Pakorn about GEO action HE-06-03_02 | Karen Moe | 2008-03-05 | Closed
25-10 | Investigate HE-06-03_3 and get back to Pakorn | Nataliia Kussul | 2008-03-05 | Closed
25-11 | Contact Murielle Lafaye on GEO task HE-07-01_1 and ask specifically what her interest in WGISS participation might be | Paul Kopp | 2008-03-04 | Closed | I had a conversation with Murielle Lafaye about the GEO task HE-07-01_1. She would be happy to get support from WGISS, namely through the IDN, at least as a first step. A second step could be to set up a dedicated IDN portal. 04-Mar-08
25-12 | Get back to Pakorn on GEO task AR-07-02_1 and DA-07-04_1 | Terence vanZyl | 2008-03-05 | Closed
25-13 | Send text to Pakorn for DA-07-03_5 | Lyn Oleson | 2008-03-05 | Closed
25-14 | Contact Doug Nebert concerning DA-06-04 | Pakorn Apaphant & Karen Moe | 2008-03-05 | Closed
25-15 | Send out CEOS Interoperability Handbook version 1.1 in "Track Changes" format. | Paul Kopp | 2008-03-08 | Closed | Here is the version 1.1 of the CEOS Interoperability Handbook. It includes change bars as requested. Modifications from version 1.0 to 1.1 are at pages iii, 24, 25, 45, 46, 49, 50. 04-Mar-08
25-16 | Review issue 1.1 of CEOS Interoperability Handbook and give comments to Paul Kopp | WGISS-all | 2008-05-08 | Closed
25-17 | Provide a process to review and update WGISS website and 5-Year Plan | WGISS Exec and WISP chair | 2008-05-01 | Closed
25-18 | ACC (Hilsenrath) and WGISS (Maiden, Moe) to discuss joint ACC/WGSS areas of interest and expertise to determine specific joint near-term activities. Working to include CEOS member Atmospheric Composition assets into SERVIR is one possibility. Another is WGISS inputs into ACC short-term projects. | Hilsenrath, Maiden, Moe | 2008-04-02 | Closed | We discussed joint areas of interest (ACC Portal and Sensor Web), and presented status at WGISS -26.
25-19 | Review all the presentations from the joint sessions to identify possible activities or topics to explore by WGISS, subgroups, interest groups, or projects. | WGISS exec | 2008-04-02 | Closed

## WGISS-26 Actions
WGISS-26 Action Items
Last Updated 26 September 2008 by M. Piepgrass
No. | Action | Who | By | Open/Closed | Status
26-1 | Decide whether to follow the CEOS-style website | WGISS-All | 2008-09-26 | closed | All agreed.
26-2 | Develop a plan to post Best Practices/Lessons Learned/other items on the WGISS website when it has been redesigned. Establish the requirements for internal and external lessons learned, best practices, and WGISS-GEO support information | Ken, Karen, Yonsook | 2009-01-15 | Open
| Plan with milestones to implement the WGISS website | Ken, SEO | 2008-12-15 | Open
26-3 | Identify and contact the agencies/individuals that WGISS projects can intercact with to provide services during disasters. Use GRID and Wenchuan Earthquake experience and recommendations to outline a clear process. (This is a contribution to DI-06-09) | Lorant (organizer) Nataliia, Guoqing, Pakorn | WGISS-27 | Open
26-4 | Send the WAG draft Architecture document to WGISS-All for feedback | Paul Kopp | 2008-10-15 | Open
26-5 | Send the GEOSS Sensor Web Workshop report to WGISS-All | Terence | 2008-10-01 | Open
26-6 | Send Technology Infusion report to WGISS-All | Karen | 2008-10-01 | Open
26-7 | Determine milestones for acceptance and publication of new Climate Diagnostics Portal; must be published for CEOS Plenary | Lola, Dingsheng | 2008-10-01 | Open
26-8 | Send URL for Climate Diagnostics Portal to WGISS-All, include response deadline | Lola | 2008-10-05 | Open
26-9 | Include a presentation on Quality Metadata Status on WGISS-27 agenda. | WGISS-Exec | 2009-03-01 | Open
26-11 | WGISS to review presentation and comment for ISO 19130 and copy Liping. | WGISS-All | 2008-10-31 | Open
26-12 | Include a session on Security on WGISS-27 agenda, with outside experts. | WGISS-Exec | 2009-03-01 | Open
26-13 | Identify liason candidates for PC and WGISS. | Satoko, Karen | WGISS-27 | Open
26-15 | Create a new template for project proposals in Applications Subgroup, including a list of needed resources if the project has a sustainable component; a section on a project closeout. | Karen, Ken, Yonsook | 2009-02-15 | Open
26-18 | Include a session on Data topics (refer to Data Services in wgiss-26 minutes) on WGISS-27 agenda, with outside experts. | WGISS-Exec | 2009-03-01 | Open