## StatusSummary
WGISS Action Item Status Summary as of June-29-2006
| Due: Pre-June-2006 | Due: June-2006 | Due: WGISS-22 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 3 | 1 | 5 | 19 | 28
WGISS-21 | 1 | 9 | 6 | 7 | 23
Total | 7 | 10 | 11 | 30 | 58
WGISS Action Item Status Summary as of September 15, 2006
| Due: Pre-WGISS-22 | Due: WGISS-22 | Due: Post WGISS-22 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 9 | 0 | 0 | 19 | 28
WGISS-21 | 7 | 5 | 0 | 11 | 23
WGISS-22 | 0 | 0 | 27 | 0 | 27
Total | 19 | 5 | 27 | 34 | 85
WGISS Action Item Status Summary as of October 27 2006
| Due: WGISS-22 | Due: Oct-2006 | Due: Post Oct-2006 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 6 | 0 | 0 | 22 | 28
WGISS-21 | 7 | 0 | 1 | 15 | 23
WGISS-22 | 0 | 14 | 13 | 8 | 35
Total | 16 | 14 | 14 | 49 | 93

## WGISS-26 Actions
No. | WGISS-26 Action Items Last Updated 16 March 2009 by M. Piepgrass | Who | By | Open/ Closed
26-1 | Decide whether to follow the CEOS-style website. | WGISS-All | 2008-09-26 | Closed | All agreed on the last day of WGISS-26.
26-2 | Develop a plan to post Best Practices/Lessons Learned/other items on the WGISS website when it has been redesigned. Establish the requirements for internal and external lessons learned, best practices, and WGISS-GEO support information. | Ken, Karen, Yonsook | 2009-02-01 | Open | December 5: Karen requested an extension to February 1
26-3 | Develop a plan with milestones to implement the WGISS website. | Ken, SEO | 2008-12-15 | Open
26-4 | Identify and contact the agencies/individuals with which WGISS projects can interact to provide services during disasters. Use GRID and Wenchuan Earthquake experience and recommendations to outline a clear process. (This is a contribution to DI-06-09). | Lorant (organizer) Nataliia, Guoqing, Pakorn, cc. Liu Chuang | WGISS-27 | Open | Reminded actionees 27 October.
26-5 | Send the WAG Architecture (draft) document to WGISS-All for feedback. | Paul Kopp | 2008-10-15 | Closed | Paul notified WGISS-All of the availability of the document on 27 November.
26-6 | Send the GEOSS Sensor Web Workshop report to WGISS-All. | Terence | 2008-10-01 | Closed | Sent to WGISS-All October 3.
26-7 | Send Technology Infusion report to WGISS-All. | Karen | 2008-10-01 | Closed | Sent to WGISS-All October 2.
26-8 | Determine milestones for acceptance and publication of new Climate Diagnostics Portal; must be published for CEOS Plenary. | Lola, Dingsheng | 2008-10-05 | Closed | Received the milestones from Lola on 15 October.
26-9 | Send URL for Climate Diagnostics Portal to WGISS-All; include response deadline. | Lola | 2008-10-12 | Closed | The URL for the Climate Diagnostic Portal will be sent to WGISS-All no later than October 23rd, 2008. Response deadline requested will be 28 October, 2008. [ Encourage the WGISS-All members to use the authoring tool if they wish to contribute a sample visualization.] Move software to final location on CEOS IDN Web Site for the CEOS Plenary (one full week before the plenary).
26-10 | Include a presentation on Quality Metadata Status on WGISS-27 agenda. | WGISS-Exec | 2009-03-01 | Closed | Added to WGISS-27 Agenda
26-11 | Review presentation and comment for ISO 19130 and copy Liping. | WGISS-All | 2008-10-31 | Closed | Reminded WGISS-All on 27 October.
26-12 | Include a session on Security on WGISS-27 agenda, with outside experts. | WGISS-Exec | 2009-03-01 | Closed | Added to WGISS-27 Agenda
26-13 | Identify liaison candidates for Precipitation Constellation and WGISS. | Satoko, Karen | WGISS-27 | Open
26-14 | Create a new template for project proposals in Applications Subgroup. Include a secion on project closeout. | Karen, Ken, Yonsook | 2009-02-15 | Open
26-15 | Include a session on Data topics on WGISS-27 agenda, with outside experts (refer to Data Services in WGISS-26 minutes). | WGISS-Exec | 2009-03-01 | Closed | Lyn Oleson agreed to be the facilitator of a discussion for 30 minutes about whether and how we might form a Data Services Interest Group to address data topics in the future

## 2009 Exec Actions
No. | 2009 WGISS-Exec Action Items. Last Updated 16 March 2009 by M. Piepgrass | Who | By | Open/ Closed | Comments
01-01 | Look at the DI-06-09 document sent out by Pakorn and send responses to Pakorn. | Exec | 2009-01-15 | Closed
01-02 | Review and develop GEO task sheets and return to Pakorn. | Exec | 2009-01-15 | Closed
02-01 | Work with Ken and Yonsook on the issue of data harmonization. | Karen | 2009-03-12 | Closed | Added to WGISS-27 agenda
02-02 | Populate the WGISS-27 agenda starting from security special session on Monday to the end of Thursday, making sure that the new GEO tasks are covered, with the expectation of having a draft in time fro the next Exec teleconference. | Karen, Nataliia | 2009-03-12 | Closed | Added to WGISS-27 agenda
02-03 | Work on preparing a list for the GEO priorities for CEOS report, including expected outcomes and strategy for 2009 and 10, to be discussed at WGISS-27. | Martha | 2009-03-12
03-01 | Contact to Wyn about 5-Year Plan document and sessions for WGISS-27. | Martha | 2009-03-30 | Closed | Email sent March 13
03-02 | Send to WGISS-Exec the title and name of invited speaker for security session using GRID. | Nataliia | 2009-03-13 | Open
03-03 | Take charge of developing the security session in the WGISS-27 agenda, in cooperation with Nataliia and Karen. | Terence | 2009-05-01 | Open | Begun March 13.
03-04 | Exchange emails regarding the disaster SBA so that it could added to the purposes and outcomes of May meeting. | Martha, Nataliia | 2009-03-30 | Open
03-05 | Update the Thursday morning session of WGISS-27 agenda for the disaster management project | Karen | 2009-03-16 | Closed | Agenda updated March 13
03-06 | Provide a specific title for Professor Koike's session | Satoko | 2009-03-12 | Closed | Provided March 12
03-07 | Look at the greenhouse gas monitoring task to see if some presentation can be made at WGISS-27 for some germ of contribution by WGISS. | Satoko, Osamu | 2009-05-01 | Open
03-08 | Send to Lyn Oleson (cc Exec) to remind him of Action 25-15 - Include a session on Data topics in the WGISS-27 agenda, with outside experts (refer to Data Services in WGISS-26 minutes). | Michelle | 2009-03-16 | Closed | Email sent March 16, and reply received same day.
03-09 | Have final contributions on WGISS-27 agenda to Michelle, and sent to Paul Kopp by the 18th for publication. | Exec, Michelle | 2009-03-16 | Open
03-10 | Prepare and send an invitational email with the agenda and website to circulate among CEOS members. | Pakorn, Martha | 2009-04-01 | Open
03-11 | Invite two scientists involved in Wenchuan earthquake to WGISS-27. | Liu | 2009-04-01 | Open
03-12 | Sharpen and improve the WGISS-27 Expected Outcomes presentation for posting on the meeting website so everyone will know what they are expected to contribute. | Exec | 2009-04-01 | Open
03-13 | Paul to contact Ken McDonald to put WGISS-27 meeting link on WGISS website. | Paul | 2009-03-18 | Open
03-14 | Work with Ken and Courtney to update WGISS website. | Michele | 2009-04-01 | Open
03-15 | Work on preparing a list for the GEO priorities for CEOS report, including expected outcomes and strategy for 2009 and 2010, to be discussed at WGISS-27; demonstrable outcomes are needed, as this information must be submitted to GEO immediately after the meeting in May. | Martha |  | Open
03-16 | focus and work together to get the first draft agenda. | Exec | 2009-03-18 | Open
03-17 | Martha to send to WGISS-all an email about the 5-Year Plan and the Session on security. | Martha | 2009-03-18 | Open