## Sheet1
Action Number | Action Description; Last updated April 25, 2013 | Actionee | Due Date | Status | Comments
WGISS-34-1 | Richard Moreno to contact to ESA to consider the agenda of sessions with ESA during WGISS-36. | Richard Moreno | WGISS-35 | Closed | 14 December: Richard is waiting for output of upcoming meetings with European agencies. At WGISS-36 there may be a 26 February: Richard suggested that this session will not need to be organized since there is now an active exchange. At WGISS-36 there will likely be a session and discussion with ESA colleagues.
WGISS-34-2 | WGISS members to dialogue with colleagues at INPE, GEO, and ESA to develop workshops or special sessions at WGISS-35 and WGISS-36. Yonsook Enloe will dialogue with CWIC and GCI, Karen Moe with SBA Disasters, John Faundeen with SDCG. | Yonsook Enloe, Karen Moe, John Faundeen | WGISS-35 | Closed | 22 January: John stated that these sessions will not align for September.
WGISS-34-3 | John Faundeen and Andy Mitchell to contact the CEOS virtual constellations and working groups to ask what their data and portal needs are, and coordinate with Stephen Hosford, by December 31. | John Faundeen | 2012-12-31 | Closed | 11 December: email asking the VCs to engage with WGISS and provide an overview were sent out 18 October and follow-up on 16 November. 14 December: John reported that all the VCs have been contacted, and only Stephen Meek responded in support to the request, so he will follow up. Andy reported speaking with Hilcea Ferreira (WGCapD) who is very interested in developing a CWIC and IDN course in their e-learning curriculum. Should be handled through the VCs, not the WGs. CNES leading a CEOS portal study.
WGISS-34-4 | Martin Yapur to prepare WGISS outreach materials by WGISS-35. | Martin Yapur | WGISS-35 | Closed | Martiln will present at WGISS-35; flyer and a logo.
WGISS-34-5 | Karen Moe to approach the Charter regarding a repository of Charter data and reference to un-retained data; report at WGISS-35. | Karen Moe | WGISS-35 | Closed | 14 December: Karen has found a contact person with whom to follow up. 25 April: Karen will report at WGISS-35.
WGISS-34-6 | John Faundeen to send browse statement to Satoko Miura for final distribution/approval. | John Faundeen, Satoko Miura | 2012-10-24 | Closed | 25 April: Karen will report at WGISS-35.
WGISS-34-7 | Technology Exploration Interest Group will take responsibility for a survey of existing quality metadata within WGISS members selected data products, and provide a report by WGISS-35. | Technology Exploration IG | WGISS-35 | Closed | 14 December: Andy said the survey is going well; he has gathered a checklist and distributed it in NASA. He also met with Dr. Lucy Bastin (GeoViqua), and she is very interested as they have done something very similar as part of GEOSS. Sent a draft to Satoko who provided feedback. 25 April: Andy reported that the questionnaire was distributed, but it transpired that the email distribution list failed. Andy will resend, and await responses. The topic is on the WGISS-35 agenda.
WGISS-34-8 | Michael Morahan and John Faundeen to contact WGCV Chair to dialogue over naming issues of DIFs, to allow for uniqueness and clarity. | Michael Morahan | 2012-12-31 | Closed | 14 December: John reported that this incident is now closed, and INPE and CONAE are working on the naming issues.
WGISS-34-9 | Brian Killough and Andy Mitchell to work with Michael Morahan and Lola Olsen to map the MIM keywords into the GCMD. | Brian Killough, Andy Mitchell, Michael Morahan, Lola Olsen | 2012-12-31 | Closed | 14 December: Andy said he has worked with Lola and Michael, and is waiting on final response from Brian Killough. 18 January: Andy reported that the IDN pages have been updated and Brian is satisfied with the improvements.
WGISS-34-10 | IDN to review the GEONETCAP Portal and suggest where it should be linked in time for the CEOS Plenary. | IDN team | 2012-10-24 | Closed | 21 October: Michael reported that linking the GEONETCAP portal to the CEOS site is a better place than to the IDN. The IDN will create a Data Service entry (SERF) for the portal.
WGISS-34-11 | Richard Moreno to design a session at WGISS-35 to discuss WGISS way forward/ future strategy. | Richard Moreno | WGISS-35 | Closed | 14 December: Richard asked for ideas on how to proceed, given that the object is to make WGISS more attractive and useful. He suggested some technical presentations from CNES and others from the point of view of emerging technologies and interoperability. Richard’s colleague Jerome will be present at WGISS-35, and Yonsook suggested that it be part of the Technology Exploration, followed by a session of discussion on WGISS strategy and future plan. Approximately two hours will be needed in the agenda. 26 January, working on this, working with Steven, and hopefully next month will have something the report. 26 February: Satoko noted that the CEOS Self Study report was received today, and there are interest points there related to WGISS and interaction with working groups. Satoko’s report on Monday will be an introduction to the CEOS Self Study.
WGISS-34-12 | Michelle Piepgrass to consolidate discussion of 5-Year Plan and send to WGISS-All by October 3, 2012. | Michelle Piepgrass | 2012-10-03 | Closed | October 8: Michelle distributed the 5-Year Plan to WGISS-All, and Satoko submited it to the CEOS Plenary.
WGISS-34-13 | IG/P leads to update their page of the WGISS website in time for CEOS Plenary, October 24, 2012. | IG/P Leads | 2012-10-24 | Closed
WGISS-34-14 | Karen Moe to document lessons learned on sensor web activities by WGISS-35. | Karen Moe | WGISS-35 | Open | 14 December: Karen commented that she needs to go back to historical files to gather the information. Martin added that there is a section on the WGISS website where lessons learned are reported/stored. 22 January: Martin noted on the topic of sensor web that NASA, NOAA, OGC, and WGISS are organizing a sensor web workshop March 26-28. It will be co-hosted with OGC making it also a GEOSS architecture workshop. They are expecting 50-60 people to explore new ways forward. Martin officially requested if WGISS can be listed as a co-sponsor. Satoko agreed, and there were no objections. 25 April: Karen is continuing to gather old documents and files.