## Sheet1
Action Number | Action Description; Last updated May 10, 2013 | Actionee | Due Date | Status | Comments
WGISS-35-1a | Martin Yapur to send the WGISS-All mailing list to WGISS agency representatives for review and to suggest additions and deletions; by May 21, 2013. | Martin Yapur | 2013-05-21 | Open
WGISS-35-1b | WGISS agency representatives to review th WGISS-All mailing list and return edited version to Martin Yapur; by May 31, 2013. | WGISS agency representatives | 2013-05-31 | Open
WGISS-35-2 | WGISS members to contact Martin Yapur with suggestions for improvements to the WGISS website; by June 30, 2013. | WGISS members | 2013-06-30 | Open
WGISS-35-3 | Interest Groups and Projects to propose to WGISS Chair their 2014 activity plan; by August 19, 2013. | Interest Group and Project leads | 2013-08-19 | Open
WGISS-35-4 | IDN Interest Group to provide Satoko with the number of registered datasets in the IDN (as existed before SIT-28 and before SIT Workshop); by August 19, 2013. | IDN Interest Group | 2013-08-19 | Open
WGISS-35-5a | Brian Killough to notify WGISS-All when the changes and improvements to the Data Policy Portal are complete; by May 31, 2013. | Brian Killough | 2013-05-31 | Open
WGISS-35-5b | WGISS-All to review the Data Policy Portal and provide Brian Killough with feedback; by June 30, 2013. | WGISS-All | 2013-06-30 | Open
WGISS-35-6 | The IDN Interest Group to produce an automated report of DIF information for each agency, and to set up a periodic distribution to the agency contact list; by June 30, 2013. | IDN Interest Group | 2013-06-30 | Open
WGISS-35-7 | The IDN Interest Group to investigate a DIF Management Tool; by WGISS-36. | IDN Interest Group | WGISS-36 | Open
WGISS-35-8 | The Technology Exploration and IDN Interest Groups to create a Best Practices document for easily leading users to products after data discovery; by WGISS-36. | Technology Exploration and IDN Interest Groups | WGISS-36 | Open
WGISS-35-9a | Yoshiyuko Kudo to incorporate the comments of Costas Theophilos and Nitant Dube into the Browse Guidelines document; by June 1, 2013. | Yoshiyuki Kudo | 2013-06-01 | Open
WGISS-35-9b | Satoko Miura to circulate the Browse Guidelines document among WGISS-All for 60-day review; by June 1, 2013 (contigent on review of WGISS-All mailing list). | Satoko Miura | 2013-06-01 | Open
WGISS-35-10 | John Faundeen and Mirko Albani to develop an agenda for a collaborative session at WGISS-36 on the topic of data stewardship; by August 31, 2013. | John Faundeen and Mirko Albani | 2013-08-31 | Open
WGISS-35-11 | Satoko Miura to ask the WGISS representatives to consider being the WGISS representative to the LSSG; by May 27, 2013. | Satoko Miura | 2013-05-27 | Closed | Email sent to WGISS-All May 9, 2013.
WGISS-35-12 | VCIG to update their page on WGISS website; by July 1, 2013. | VCIG | 2013-07-01 | Open
WGISS-35-13 | WGISS Chair (Satoko Miura) to follow up with the GEO Secretariat to get the IDN approved as the registry for CEOS data; by August 31, 2013. | WGISS Chair | 2013-08-31 | Open
WGISS-35-14a | Pedro Gonçalves to distribute the OGC Opensearch Extension for EO Products draft for review to the Opensearch Project team; by May 27, 2013. | Pedro Gonçalves | 2013-05-27 | Open
WGISS-35-14b | The Opensearch Project team to send comments on the OGC Opensearch Extension for EO Products draft to Pedro Gonçalves; by August 15, 2013. | Opensearch Project Team | 2013-08-15 | Open
WGISS-35-14c | The Opensearch Project team to prepare the CEOS Opensearch Best Practice Document, based on comments from the OGC Opensearch Extension for EO Products; by release date of OGC Opensearch Extension for EO Products document. | Opensearch Project Team | Release date of OGC Opensearch Extension for EO Products document | Open
WGISS-35-15 | Mirko Albani to organize a CEOS Opensearch Best Practices Workshop with the OGC team for 23 September, 2013; by 31 August, 2013. | Mirko Albani, Opensearch Project Team | 2013-08-31 | Open
WGISS-35-16 | The Opensearch Project Team to develop a TOR and a WGISS website page; by August 31, 2013. | Opensearch Project Team | 2013-08-31 | Open
WGISS-35-17 | Andy Mitchell to investigate whether Dr. Chris Lynnes (NASA) can support the CEOS Water Portal development with the ESRI GeoPortal; by July 1, 2013. | Andy Mitchell | 2013-07-01 | Open
WGISS-35-18 | The IDN IG and CWIC Project teams to provide to the WGCapD (for their resources web page) a summary of IDN and CWIC, and the link to the CWIC video; by May 31, 2013. | IDN IG, CWIC Project Team | 2013-05-31 | Open
WGISS-35-19 | WGISS Exec, Ken McDonald and Wyn Cudlip to meet by teleconference to discuss the document repository and to create and load the “What is WGISS” Summary on the WGISS website; by June 30, 2013. | WGISS Exec, Ken McDonald and Wyn Cudlip | 2013-06-30 | Open
WGISS-35-20a | Richard Moreno to ask WGISS-All for a list of open source software (or code snipets) related to EO and used by their agencies; by May 31, 2013. | Richard Moreno, WGISS-All | 2013-05-31 | Open
WGISS-35-20b | WGISS-All to return the list of open source software used by their agencies; by June 30, 2013. | WGISS-All | 2013-06-30 | Open
WGISS-35-20c | Richard Moreno to compile and categorize the list of open source software and give the relevant set as a contribution to WGCapD for their resources page; by WGISS-36. | Richard Moreno | WGISS-36 | Open
WGISS-35-21 | Andy Mitchell to send to WGISS-All several topics (Product Formats, cloud computing, big data, other suggestions???) as possible topics for a technical workshop session at future meetings; by May 31, 2013. | Andy Mitchell | 2013-05-31 | Open
WGISS-35-22 | Richard Moreno to make a summary of the WGISS Way Forward session and distribute it to WGISS-All; by May 31, 2013. | Richard Moreno | 2013-05-31 | Open