## Original
Action Number | Action Description | Actionee | Due Date | Status | Comments
WGISS-38-1 | Richard to discuss with WGDisasters how the RO interacts with other disaster systems, not just at the agency level, but also UNSPIDER, Sentinel-Asia, Google (this is a strategic level question). | Richard Moreno | 2014-10-31
WGISS-38-2 | Martin and Andy to ensure a GoToMeeting is scheduled and publicized to WGISS-38 participants for the side meeting at the Plenary. | Martin Yapur, Andy Mitchell | 2014-10-27
WGISS-38-3 | WGISS Exec to review the GEO task sheets to identify areas where WGISS can contribute. | WGISS-Exec | 2014-11-21
WGISS-38-4 | WISP to organize a teleconference to gather thoughts on best way to advertise important documents or recent document releases on CEOS website, and discuss with Kim Keith at the CEOS Plenary. | WISP | 2014-11-30
WGISS-38-5 | WISP to organize a webpage for Open Source code, organized into categories (e.g. Interoperability). WGISS IG and Project leads to add links. These links should be the same as the links to Open Source code found on their webpages. | WISP | 2014-11-21
WGISS-38-6 | WGISS Exec to identify a lead of the Interoperability Interest Group. | WGISS-Exec | 2014-11-21
WGISS-38-7 | Lead of Interoperability Interest Group to develop a page on the WGISS website. | Lead of Interoperability Interest Group | 2014-12-31
WGISS-38-8 | Interest groups and projects to update their pages on the WGISS website. | Interest groups and projects | 2014-11-30
WGISS-38-9 | Michael Morahan to check whether the SKOS description of satellite and missions is in the GCMD and IDN. | Michael Morahan | 2014-10-31 | Closed
WGISS-38-10 | Andy to review the use of the term DOI in the GCMD DIF metadata field to determine if it is appropriate to use PI instead. | Andy Mitchell | WGISS-39
WGISS-38-11 | WGISS to develop a glossary of terms. | WGISS-All | WGISS-39
WGISS-38-12 | Andy write a summary of what NASA is doing with OPeNDAP (UNIDATA) and to organize a session on OPeNDAP at WGISS-39 (inviting presenters from OPeNDAP). | Andy Mitchell | WGISS-39
WGISS-38-13a | Michelle, Ken, Jonathon and Wyn to finalize the “What is WGISS” text by end of October. | Michelle Piepgrass, Ken McDonald, Jonathon Ross, Wyn Cudlip | 2014-10-27
WGISS-38-13b | Michelle, Ken, Jonathon and Wyn to complete ToR for submission to CEOS Plenary. | Michelle Piepgrass, Ken McDonald, Jonathon Ross, Wyn Cudlip | WGISS-39
WGISS-38-14a | Andy and Jonathon to investigate an existing project for a few GFOI or GEOGLAM prototypes that would benefit from data exploitation that WGISS could promote. | Andy Mitchell, Jonathon Ross | 2015-02-01
WGISS-38-14b | Technology Exploration IG to work with Brian to investigate options for supporting cloud processing, so Brian can present these to Barbara Ryan with a common voice between WGISS and SEO. | Technology Exploration IG | 2015-02-01
WGISS-38-15 | Jonathon to get the GA holdings into the IDN and available through CWIC. | Jonathon Ross
WGISS-38-16 | WGISS Exec to discuss the possibility of creating an interest group for Disasters. | WGISS Exec | 2014-10-27
WGISS-38-17 | WGISS-All to provide comments on the draft OpenSearch Best Practice document by end of November | WGISS-All | 2014-11-30
WGISS-38-18 | WGISS-All to provide comments to Preservation Workflow once they are sent out by Mirko. | WGISS-All | One month after delivery of document.
WGISS-38-19 | DSIG to finalize the purge alert process using CEOS principles. | DSIG | WGISS 39

## Revised
Revised January 11, 2015
Action Number | Action Description | Actionee | Status | Due Date | Comments
WGISS-38-1 | Richard to discuss with WGDisasters how the RO interacts with other disaster systems, not just at the agency level, but also UNSPIDER, Sentinel-Asia, Google (this is a strategic level question). | Richard Moreno |  | 2014-10-31 | Richard has two questions from the ROSCOSMOS team to add to the discussion
WGISS-38-2 | Martin and Andy to ensure a GoToMeeting is scheduled and publicized to WGISS-38 participants for the side meeting at the Plenary. | Martin Yapur, Andy Mitchell | Closed | 2014-10-27 | WGISS will need to supply this account. Andy will ask if resources are available for a teleconference.
WGISS-38-3 | WGISS Exec to review the GEO task sheets to identify areas where WGISS can contribute. | WGISS-Exec |  | 2014-11-21 | Michelle to add to the agenda for next WGISS Exec teleconference. Richard will prepare a discussion for the January Exec teleconference
WGISS-38-4 | WISP to organize a teleconference to gather thoughts on best way to advertise important documents or recent document releases on CEOS website, and discuss with Kim Keith at the CEOS Plenary. | WISP |  | 2014-11-30 | Martin suggested that Michelle organize the teleconference, but to wait until after the Plenary, based on progress SEO has made. Kim Holloway attended this December teleconference.
WGISS-38-5 | WISP to organize a webpage for Open Source code, organized into categories (e.g. Interoperability). WGISS IG and Project leads to add links. These links should be the same as the links to Open Source code found on their webpages. | WISP |  | 2014-11-21 | Martin and Anne are working on this and expect to have it ready for the next Exec teleconference.
WGISS-38-6 | WGISS Exec to identify a lead of the Interoperability Interest Group. | WGISS-Exec |  | 2015-01-31 | WGISS Exec to send nominations to Richard and Andy. Considering changing this into a Liaison activity. Andy will work on a ToR.
WGISS-38-7 | Lead of Interoperability Interest Group to develop a page on the WGISS website. | Lead of Interoperability Interest Group |  | 2014-12-31
WGISS-38-8 | Interest groups and projects to update their pages on the WGISS website. | Interest groups and projects |  | 2015-01-31 | Michelle to send a reminder to the leads.
WGISS-38-9 | Michael Morahan to check whether the SKOS description of satellite and missions is in the GCMD and IDN. | Michael Morahan | Closed |  | Michael gave him the descriptions from static links. The action is closed.
WGISS-38-10 | Andy to review the use of the term DOI in the GCMD DIF metadata field to determine if it is appropriate to use PI instead. | Andy Mitchell | Closed | WGISS-39 | Michael reported that the DIF-10 release has been changed to use “PI”, allowing for DOI and ARK as secondary points. It will be released next year. DIF-9 will still be maintained; Andy recommended adding the same changes to DIF-9.
WGISS-38-11 | WGISS to develop a glossary of terms. | WGISS |  | WGISS-39 | Michelle to ask IG and P leads to send commonly used terms to Michelle to merge and pass on to the lead of the Interoperability IG.
WGISS-38-12 | Andy write a summary of what NASA is doing with OPeNDAP (UNIDATA) and to organize a session on OPeNDAP at WGISS-39 (inviting presenters from OPeNDAP). | Andy Mitchell |  | WGISS-39
WGISS-38-13a | Michelle, Ken, Jonathon and Wyn to finalize the “What is WGISS” text by end of October. | Michelle, Ken, Jonathon, Wyn | Closed | 2014-10-27 | Michelle to initiate this.
WGISS-38-13b | Michelle, Ken, Jonathon and Wyn to complete ToR for submission to CEOS Plenary. | Michelle, Ken, Jonathon, Wyn |  | WGISS-39 | Michelle will work initiate this in January
WGISS-38-14a | Andy and Jonathon to investigate an existing project for a few GFOI or GEOGLAM prototypes that would benefit from data exploitation that WGISS could promote. | Andy Mitchell, Jonathon Ross |  | 2015-02-15 | Andy will discuss this Jonathon at the Plenary.
WGISS-38-14b | Technology Exploration IG to work with Brian to investigate options for supporting cloud processing, so Brian can present these to Barbara Ryan with a common voice between WGISS and SEO. | Technology Exploration IG |  | 2015-02-15
WGISS-38-15 | Jonathon to get the GA holdings into the IDN and available through CWIC. | Jonathon Ross |  | Mar-15-2015 | Michael believes that they may start next year. Yonsook will have the conversation with Jonathon about CWIC aspects.
WGISS-38-16 | WGISS Exec to discuss the possibility of creating an interest group for Disasters. | WGISS Exec |  | 2014-10-27 | Karen suggested a separate discussion; quite a few from WGISS are interested so the potential is there. Michelle to add to agenda of next teleconference.
WGISS-38-17 | WGISS-All to provide comments on the draft OpenSearch Best Practice document by end of November | WGISS-All |  | 2015-01-31 | Richard will ask the CEOS agencies to review this, and Yoshiyuki will resend the review request to WGISS-All. Collect public comments by January 31.
WGISS-38-18 | WGISS-All to provide comments to Preservation Workflow once they are sent out by Mirko. | WGISS-All |  | One month after delivery of document.
WGISS-38-19 | DSIG to finalize the purge alert process using CEOS principles. | DSIG |  | WGISS 39