## Sheet1
Last Updated October 1, 2015, Michelle Piepgrass
Number | Action Description | Assignee(s) | Due Date | Comments | Status
WGISS 39-01 | WISP to talk to SEO about transferring the WGISS email distribution lists to CEOS and the WGISS documents to the CEOS Document Management System. | WISP | August 1 2015 | The team has met and is resolving these issues. | Closed
WGISS 39-02 | Mirko Albani, Richard Moreno, Andy Mitchell and Wyn Cudlip to select a team that will review GEO Task IN-02-C1: Advances in Life-cycle Data Management, and make recommendations looking toward the GEO 2016 Work Plan. | Mirko Albani, Richard Moreno, Andy Mitchell and Wyn Cudlip | Sept 1 2015 | The deadline for the workplan is in August. | Closed
WGISS 39-03 | Richard Moreno and Andy Mitchell to approach Jonathon Ross about taking on the role of WGISS Collaboration Facilitator, then approach the SIT and the SEC for adoption. | Richard Moreno, Andy Mitchell | August 1 2015 | Jono replied that the CEO/DCEO are not the right persons and will discuss this at WGISS 40. | Closed
WGISS 39-04 | Michelle Piepgrass to include a session at WGISS 40 for deciding the future of the OpenSearch Project. | Michelle Piepgrass | Sept 1 2015 | Added to the agenda. | Closed
WGISS 39-05 | Michelle Piepgrass to work with WISP to implement the recommended changes to the WGISS website, including the short WGISS “purpose/description” paragraph. | Michelle Piepgrass | Sept 1 2015 | The team has met and is progressing on this. | Closed
WGISS 39-06 | IG/P leads to implement recommended changes to their pages on the WGISS website. | IG/P leads | Sept 1 2015 | Added to the agenda. | Closed
WGISS 39-07 | Michelle Piepgrass to work with WISP to migrate WGISS documents to the CEOS document management system; also discuss with the SEO the wording on the CEOS documents landing page. | Michelle Piepgrass | Sept 1 2015 | The team reports that the documents are present and acounted for. | Closed
WGISS 39-08 | Andy Mitchell to consider a session for WGISS 40 on the retirement of FTP. | Andy Mitchell | Sept 1 2015 | Added to the agenda. | Closed
WGISS 39-09 | Mirko Albani to prepare a presentation for WGISS 40 on ESA’s cloud processing. | Mirko Albani | Sept 1 2015 |  | Closed
WGISS 39-10 | Technology Exploration Interest Group to plan a session on Open Source Software practices inviting each agency to present at WGISS 40. | Technology Exploration IG | Sept 1 2015 | Added to the agenda. | Closed
WGISS 39-11 | WGISS Exec to respond to SEO’s request to conduct a data format study to analyze the advantages and disadvantages of using GEOTIFF, NetCDF, and HDF formats in a Data Cube. Are there computational and data assimilation advantages? The SEO/GA can provide WGISS with a small data cube for testing. | WGISS Exec | Sept 1 2015 | Brian has revised the actions for WGISS. | Closed
WGISS 39-12 | WGISS Exec to respond to SEO’s request to develop an automated data ingestion scheme that utilizes CWIC/FedEO to ingest new data products into the Data Cube infrastructure as functional layers. The SEO is working with USGS to create automated scripting and requests for Landsat data. Can this work for the Sentinel missions? No other missions have open access or would be desired as “regular” data layers. | WGISS Exec | Sept 1 2015 | Brian has revised the actions for WGISS. | Closed
WGISS 39-13 | WGISS Exec to respond to SEO’s request to conduct a data compression study to compare different compression approaches (e.g., JPEG-2000, HDF-5) for the Data Cube storage. Consider initial Data Cube formation, delivery to countries and deployment, Data Cube re-gridding, and regular operations of algorithms. | WGISS Exec | Sept 1 2015 | Brian has revised the actions for WGISS. | Closed
WGISS 39-14 | Mirko Albani and WGISS Chair to discuss the process of the data purge alert at a near-future CEOS-SEC meeting. | Mirko Albani | July 1 2015 | Richard brought it up at the SEC meeting, but more information needs to be presented to them. | Closed
WGISS 39-15 | Mirko Albani to discover if NOAA and EUMETSAT are using DOIs for near-real-time data. | Mirko Albani | Sept 1 2015 |  | Closed
WGISS 39-16 | Andy Mitchell to reach out to the NASA working groups on data stewardship for possible presentations at WGISS 40. | Andy Mitchell | Sept 1 2015 | Wyn commented this might be appropriate for the Ground Segment Evolution workshop. | Closed
WGISS 39-17 | Mirko Albani to plan a session for WGISS 40 on document and software preservation. | Mirko Albani | Sept 1 2015 | Added to the agenda. | Closed
WGISS 39-18 | IDN Interest Group to reword the phrase “create CEOS dataset” on the new IDN website by WGISS-40. | IDN Interest Group | Sept 1 2015 | Michael Morahan reported that this has been done. | Closed
WGISS 39-19 | IDN Interest Group to identify alternate terminology for the term “portals” used on the IDN website by WGISS-40. | IDN Interest Group | Sept 1 2015 | Michael Morahan reported that this has been done. | Closed
WGISS 39-20 | OpenSearch Interest Group to follow the WGISS procedure for releasing the Developer’s Guide (similar to what was done for the CEOS OpenSearch Best Practices document). Final comments should be due by June 15. | OpenSearch Interest Group | Sept 1 2015 | Yoshi recommends a discussion at WGISS-40. Comments were received, some were put in, others are thought to be better in the BP document. | Closed
WGISS 39-21 | Richard Moreno to prepare a two-minute video to present at the CEOS Plenary demonstrating discovery and access using FedEO and CWIC. | Richard Moreno | Sept 1 2015 | The team has come up with a story and is working on mock-ups. | Closed
\