## Sheet1
WGISS-41 Actions (last updated 18 September, 2016)
Action | Sub-task | Category | Description | Actionee | Due date | Status | Comments
WGISS-41-01 |  | Carbon | WGISS Exec to present jointly with WGCV at the 31st CEOS SIT Meeting (April 19-20) how the two WGs are performing an analysis of the Carbon Action items in order to sufficiently address them. | WGISS-Exec | 2016-04-16 | Closed
WGISS-41-02 |  | Data Quality | In order to support, with WGCV, Metadata Requirements for Quality (Quality fields), confirm with Albreacht if these are activities we should pursue:
| WGISS-41-02a | Data Quality | Review and comment on GEOSS Data Quality Requirements (DDQ -Documentation on Data Quality) | Andy Mitchell |  | Deferred | This is not a current priority of WGCV
| WGISS-41-02b | Data Quality | Include validation metrics (possibly calibration metrics and sensor performance indicator). Include the reference to validation guidelines into the metadata information. | Andy Mitchell |  | Deferred | This is not a current priority of WGCV
| WGISS-41-02c | Data Quality | Develop a White Paper on Recommendations for improving Data Quality in Metadata. | Andy Mitchell |  | Deferred | This is not a current priority of WGCV
WGISS-41-03 |  | FDA | Confirm with Albrecht the possibility to work with WGCV to develop Best Practices on Data Reprocessing – including current and future practices (i.e. on-demand ARD Processing). | Andy Mitchell |  | Deferred | This is not a current priority of WGCV
WGISS-41-04 |  | FDA | WGISS to review relevant CEOS and agency activities and ambitions in order to support the study on future data architectures: WGISS efforts on Big Data and Cloud Computing; and Provide Technology Exploration Interest Group summary on past efforts. |  |  | Closed | WGISS provided input to the CEOS FDA Study Report, and we will be convening a Cloud Computing workshop at WGISS-42
WGISS-41-05 |  | Data Stewardship | Richard and Mirko to organize telecon with RDA on the best practice and recommendations for DOI/PI. | Richard Moreno, Mirko Albani | 2016-04-30 | Closed | Richard clarified the differences.
WGISS-41-06 |  | New Initiatives | WGISS to work on the following new initiatives:
| WGISS-41-06a | New Initiatives | A Unified Architecture for WGISS Assets. | Yonsook Enloe, Mirko Albani |  | In progress | Mirko is setting up a team for this.
| WGISS-41-06b | New Initiatives | Discuss the concept of developing and sustaining a WGISS discovery and access system level team. | Yonsook Enloe, Mirko Albani |  | In progress | Mirko is setting up a team for this.
| WGISS-41-06c | New Initiatives | A Thesaurus (EO keywords) (Discussion for WGISS-42) | Michael Morahan, Richard Moreno |  | Closed | Michael will present on the GCMD/IDN science keywords at WGISS-42
| WGISS-41-06d | New Initiatives | Interoperability of metrics, user requirements, user profiles, unified metadata model. |  |  | Deferred | WGISS will be discussing parts of this at future meetings
| WGISS-41-06e | New Initiatives | Metadata catalog that supports the CEOS Handbook |  |  | Deferred | Deferred due to lack of resources
WGISS-41-07 |  | Outreach | Develop monthly webinars; several topics have been suggested and should be prioritized. | Technology Exploration IG |  | In progress | First one in October; topic of cloud computing.
WGISS-41-08 |  | Outreach | In order to discover how WGISS can assess the needs of other CEOS working groups, virtual constellations, and ad-hoc groups with regards to WGISS capabilities: | WGISS-Exec
| WGISS-41-08a | Outreach | WGISS members to identify, from within their own agencies, members of said groups. | WGISS members |  | Deferred
| WGISS-41-08b | Outreach | WGISS-Exec to coordinate one-on-one interactions with said contacts. | WGISS-Exec |  | Deferred | Andy will discuss this at the WG/VC side meeting at September SIT
WGISS-41-09 |  | Outreach | In order to improve WGISS outreach:
| WGISS-41-09a | Outreach | WGISS-Exec to investigate ways to develop additional outreach materials. | WGISS-Exec |  | Closed
| WGISS-41-09b | Outreach | WGISS Exec to start planning personal engagement for invitations to future meetings. | WGISS-Exec |  | In progress | The first step is to invite participants to the Cloud Computing Workshop; The Exec is actively recruiting DLR and EUMETSAT.
| WGISS-41-09c | Outreach | WGISS Exec to put together a list of the benefits and capabilities of WGISS to assist the conversation. This list will also be put on the WGISS website. | WGISS-Exec |  | In progress | This task began with the completion of “What is WGISS?” slides. This action needs to be expanded.
| WGISS-41-09d | Outreach | WGISS-Exec to provide a news item for the CEOS webpage using the Recovery Observatory as a story of good collaboration between working groups. | WGISS-Exec, Richard Moreno |  | In progress | Richard agreed to look into this.
| WGISS-41-09e | Outreach | WGISS to consider contributions to inform the GSDI community about WGISS achievements. | WGISS-Exec |  | Closed
WGISS-41-10 |  | GEO | WGISS Exec to review: | WGISS-Exec | 2016-03-31
| WGISS-41-10a | GEO | GEO Foundational Task GD-03 to identify where WGISS can contribute. | WGISS-Exec | 2016-03-31 | Closed
| WGISS-41-10b | GEO | GEO Foundational Task GD-08 to identify where WGISS can contribute, and propose this to the CEO, as it is linked with G05. | WGISS-Exec | 2016-03-31 | Closed
WGISS-41-11 |  | GEO | WGISS Exec to suggest to CEO: | WGISS-Exec | 2016-03-31
| WGISS-41-11a | GEO | To merge GEO Foundational Subtask GD07.05 into GD07.01. | WGISS-Exec | 2016-03-31 | Closed
| WGISS-41-11b | GEO | To remove GEO Foundational Subtask GD07.03 from GEO Foundational Task GD07, and make it a separate Foundational Task or move into GD01. | WGISS-Exec | 2016-03-31 | Closed
WGISS-41-12 |  | WGISS-42 | WGISS Exec to include the following in the planning for WGISS-42: | WGISS-Exec | WGISS-42
| WGISS-41-12a | WGISS-42 | WGISS Exec to work on identifying objectives and target audience for the FDA Workshop and present these plans to the SIT at the April meeting. | WGISS-Exec | WGISS-42 | Closed
| WGISS-41-12b | WGISS-42 | Andy to give a presentation at WGISS-42 on what NASA is doing with the UMM to standardize the metadata model. | Andy Mitchell | WGISS-42 | Closed
| WGISS-41-12c | WGISS-42 | DSIG to give a presentation on the investigation of a CEOS-recommended metadata model. | DSIG | WGISS-42 | Closed
WGISS-41-13 |  | MIM | Regarding the MIM:
| WGISS-41-13a | MIM | Michelle to send to agency representatives instructions about updating the MIM spreadsheet with URLs to the mission website and a URL to the data access portal for the mission data. | Michelle Piepgrass | 2016-03-31 | In Progress | The plan is to send this out as a follow-up to the CEOS survey in August.
| WGISS-41-13b | MIM | Agency representatives to populate the MIM with their changes to the mission website url and the mission data access portal URL. | Agency Representatives | 2016-04-30 | In Progress | Andy will obtain a status on this from George Dyke.
| WGISS-41-13c | MIM | Andy to follow up with the MIM team about suggestions to enhance the MIM and give an update at WGISS-42. | Andy Mitchell | WGISS-42 | Deferred | This is an ongoing discussion.
| WGISS-41-13d | MIM | Brian to talk with Michael, Yonsook and Mirko about the unique ID for mission and instrument combination in CWIC and FedEO. | Brian Killough
WGISS-41-14 |  | Website | WGISS Exec to work on the organization of the Documents web page and content of documents. | WGISS-Exec | WGISS-42 | Closed | WISP team has implemented changes.
WGISS-41-15 |  | GEO | Andy and Martin to check to see if the USGEO Data Management Principles information is feeding to GEO. | Andy Mitchell, Martin Yapur | 2016-03-31 | Closed