## Slide 1: WGISS Working Group for Information Systems & Services
Andrew Mitchell - NASA
WGISS-44
Beijing, China
25th September 2017
Committee on Earth Observation Satellites
Chair report

## Slide 2
Full exploitation of EO data requires critical user feedback informing current implementations and future directions
Future Data Architectures
CARD4L-compliant data feed FDAs
MRI identifies good practices for implementation of multi-sensor data sets
Moderate Resolution Interoperability
- Addresses how to combine data / scientific methods to maximize interoperability
    CARD4L is the first step
    - MRI provides feedback to CARD4L
CEOS Analysis Ready Data for Land
Product family specifications facilitate uptake of EO data by the user community
CEOS SIT Technical Workshop – VC/WG Day 19th of September 2017

## Slide 3
CEOS Analysis Ready Data (ARD)
  Implement and provision CEOS Analysis Ready Data for Land (CARD4L)-compliant products
  Advance ARD for marine and atmosphere domains
Interoperable Open Source Tools
  Continue supporting the CEOS Data Cube (CDC) initiative
  Demonstrate new technologies through ongoing support of ‘pilot projects’ and consideration of alternate candidate architectures
Data, Processing, and Architecture Interface Standards
  Develop standards for pixel-level data discovery, access, and common analytical processing requests (e.g., cloud free mosaics of ARD) exploiting EO satellite data among various CEOS exploitation platforms
Analytical Processing Capabilities
  Prototype portable web-based analytical processing APIs/Web Services that work across CEOS exploitation platforms in full computing environments for time series and other analysis
User Metrics
  Develop a data use metrics framework through which agencies can contribute to how EO data is being used, rather than just downloaded data quantities
FDA Themes and Outcomes

## Slide 4
Access to Copernicus data and information and additional data, in a flexible tool environment for data exploitation – introducing Copernicus DIAS for CEOS
A number of partnership approaches with large industrial players in the cloud/data domain are currently being trialled by CEOS agencies.
  In 2018 the Commission in cooperation with ESA and EUMETSAT is launching Copernicus Data and Information Access Services (DIAS) that aim at facilitating access, further processing and integration of Copernicus data and information with other data sources in a cloud environment without having to pay for the storage of Copernicus data and information.
The Commission proposes to organise a workshop where the DIAS and in particular their added value service offerings are presented. This workshop should also allow exchanging lessons learnt from other initiatives underway.
2018 CEOS Chair – European Commission

## Slide 5
Users of WGISS Connected Data Assets
  Cove (MDA – Radarsat and INPE CBRS2)
  GEOSS Evolve – Data Access Broker (DAB)
  GEO Portal
  AMERIGEOSS Data and Services Portal
  ??
Connected Data Assets
Success Stories

## Slide 6
The CWIC Team participated in the USGS Community for Data Integration (CDI) Workshop/API Plugfest in Denver, CO on May 15-17.
  During the workshop, attendees used geospatial Application Programming Interfaces (APIs) from the GEO Data Access Broker (DAB), NOAA, NASA, USGS, FEMA, EPA, USDA and CEOS (CWIC) to provide various data and service resources of selected thematic areas (Water, Environment, Agriculture and Hazard/Disaster) in the US Federal Geographic Data Committee (FGDC) Geoplatform
WGISS (Richard Moreno-CNES) gave a presentation during the GEO Data Provider’s Workshop in April 2017 on the GEO/GCI Success story of GCI-CEOS Interoperability Achievements and Collaboration.
  He presented on how WGISS has made over 300 million CEOS data resources accessible to GEO via recent developments in the WGISS interoperable standards architecture with IDN, FedEO, and CWIC.
Participation at Recent Meetings

## Slide 7
Invited presenter to WGISS-43
Richard Moreno (CNES) representing WGISS on the NextGEOSS Advisory Board
Beginning dialogue with NextGEOSS on federated authentication
  WGISS 44 Federated Authentication Session
WGISS participation in NextGEOSS

## Slide 8
Relevancy Ranking of Data Search Results
  14th of March 2017
Data Cubes for Large Scale Data Analytics
  19th of June 2017
Burgeoning Role of Python for Earth Observation Data Analysis
  22nd of August 2017
Technology Webinars

## Slide 9
CEOS is not a standards body but WGISS partnerships have led to the development of standards endorsed by standards bodies like Open Geospatial Consortium - OGC (OpenSearch) and International Organization for Standardization - ISO (Preservation)
  ISO recently approved a new work item proposal to begin the development of ISO 19165-2 (Geographic information – Preservation of digital data and metadata – Part 2: Content specifications for Earth observation data and derived digital products)
WGISS Approved Standards

## Slide 10
31st CEOS Plenary
18th – 20th of October
Rapid City, South Dakota, USA

## Slide 11: CEOS 2017-2019 Work Plan
Action Items assigned to WGISS
Committee on Earth Observation Satellites

## Slide 12
Objective/Deliverable | Projected Completion Date | Background Information | Status
DATA-8: Improve WGISS Interoperability Standards Architecture | Q3 2017 Date needs updating in CEOS Work plan | Consolidation of current CWIC/FedEO/IDN overall architecture to address identified issues including duplicate datasets holdings | This is an ongoing activity being led by the WGISS System Level Team which includes partners from CWIC, FedEO and IDN.
DATA-9: ECVs/CDRs Discovery and Access through WGISS Systems | Q3 2017 Date needs updating in CEOS Work plan | Facilitate discoverability and accessibility of ECV Products and space-born CDRs relevant for the CEOS Carbon Action via WGISS Interoperability Systems & Standards (FedEO/CWIC/IDN, OpenSearch). | Once WGClimate has completed their (meta) gap-analysis across the Carbon ECVC, WGISS will begin the longer objective of data discoverability and access. Web based ECV Inventory V2.0 will be published in October 2017 http://climatemonitoring.info/ Represents the first baseline. Will be updated once a year.

## Slide 13
Objective/Deliverable | Projected Completion Date | Background Information | Status
DATA-10: Reference model for data stewardship planning and implementation | Q4 2017 | Consolidate a reference model that provides guidelines and recommendations for the preservation and improvement of data including a roadmap for scientific data stewardship improvement; | In progress by ESA’s Long Term Data Preservation (LTDP) Working Group. Complete
DATA-11: Technology Exploration webinars and workshops | Ongoing | WGISS will host at least one workshop annually to serve as a forum for exchange of technical information and lessons-learned experience about current, trending and future software technologies, services and other WWW / Internet related software technologies. | Three webinars held in 2017. The webinars were recorded and a Youtube link to the recording was made available on the WGISS website

## Slide 14
Objective/Deliverable | Projected Completion Date | Background Information | Status
DATA-12: CEOS data holdings reported in GEO | Ongoing | Provide support to GEO in their efforts of reconciling metrics of CEOS data holdings provided through WGISS interoperable standards and systems. | Holding regular meetings with the GEO Data Access Broker (GEODAB) team to improve data discoverability and access of CEOS data in GEO. Providing new support for incremental harvesting of collection metadata from IDN, in response to the requests from GEODAB team.
DATA-2: Full representation of CEOS Agency datasets in the IDN and accessible via supported WGISS standards | Ongoing | As the IDN contains OpenSearch endpoints for data access and is also the link with GCI, it is essential that all CEOS Agencies keep information on the data up-to-date in the IDN. | New entries were added to the International Directory Network (IDN) from ESA, EUMETSAT, ISRO, and JAXA datasets.

## Slide 15
Objective/Deliverable | Projected Completion Date | Background Information | Status
FDA-:6 Technical best practices relating to future data architectures opportunities | Q4 2017 Date needs updating in CEOS Work plan | WGISS will ensure necessary structures are established to enable sharing of lessons learnt and practices relating to the exploitation of the technical opportunities identified in the interim FDA report. WGISS will present at least one ‘best practice’ document for endorsement at the 31st CEOS Plenary Meeting. | A FDA Tiger Team (Andy Mitchell – NASA, JonoRoss - GeoScience Australia, Bianca Hoersch – ESA, Rob Woodcock - CSIRO, Brian Killough - SEO) has been formed to do the analysis and writing of materials of the FDA Strategic Assessment Survey. In particular, this first analysis is looking to present the findings surrounding the question ‘What should CEOS agencies do together’ in regards to FDA. The findings will be presented at the SIT-32 meeting in Paris. The objectives and implementation planning will be presented at the CEOS Plenary.

## Slide 16
Objective/Deliverable | Projected Completion Date | Background Information | Status
CARB-15: Carbon data portal | Q4 2017 | Implement a carbon data portal to facilitate the discoverability and accessibility of ECV products and space-borne CDRs. The portal is designed with service-oriented architecture and follows the principles outlined by the GEOSS Community Portal white paper. The portal will seamlessly access data both in CWIC and FedEO to provide necessary data and services to the carbon science community of both CEOS and GEOSS. | Working with Mark Dowell (CEOS Carbon lead) and Pascal LeComte (WG Climate Chair), WGISS will begin defining a preliminary set of “requirements” for a future Carbon Portal. WGISS will start with the initial list of ECVs that are key for Carbon and start putting together a list of relevant data collections from identified data providers. A prototype portal was developed and will be demonstrated this week.