## Orizontal Activities
Task Objective | Deliverables | Projected Completion Date | Background Information | WORKING GROUP (IG) | Responsible | Contributors | STATUS
WGISS-01: Promotional Material | Production and distribution of outreach material (Brochures, Flyers, Video etc.). • WGISS Brochure • DSIG Video • SLT Video | Continuous Task with milestones set at CEOS Plenary meetings | WGISS recognizes the need to publicize the output of its work within its own agencies and with external organizations in order to ensure the adoption of its results and recommendations for the benefit of CEOS agencies and associates. This should also ensure WGISS sustainability through continued participation to its activities. | WGISS | WGISS Chair (Mirko Albani) | All Interest Groups upon request
WGISS-02: Support and participation to Seminars, Conferences, and Workshops | Production and presentation of papers and material at conferences, seminars and workshops. | Continuous Task | WGISS recognizes the need to publicize its results and work outside CEOS through taking part to conferences, workshops and seminars. | WGISS | WGISS Chair (Mirko Albani) | All Interest Groups upon request
WGISS-03: Foster new collaboration opportunities | Explore and set-up new collaborations within and outside CEOS for information and knowledge sharing | Continuous Task | WGISS recognizes the benefits of sharing its knowledge and the results of its work with relevant CEOS and non-CEOS organizations and Working Groups to maximize mutual impact and benefits. | WGISS | WGISS Chair (Mirko Albani) | All Interest Groups upon request
CB-13: Develop and/or deliver webinars for users in developing countries | Technical webinars | Continuous Task | Webinars will provide information and training on advanced satellite Earth observation topics, such as data access/availability, data processing, and more. | WGCapD with the support of WGISS | Chris Lynnes | All Interest Groups upon request
WGCV-1: Data Formats and Interoperability in the frame of FDA | Perform analysis of quality/uncertainty parameters for Analysis Ready data (ARD). | Q2 2018 | Work to define a set of quality/uncertainty parameters to be included within ARD and determine an initial method to incorporate these along with their provenance into the data stream, including education of the data community on how to provide provenance information. Coordinate with relevant working groups and stakeholders within CEOS. | WGCV with the support of WGISS | Robert Woodcock, Medhavy Thankappan | Interoperability Interest Group
WGCV-2: Quality Indicators in Discovery Metadata | Report on QI test Case: Definition of Quality Indicators for an identified Test Case and approach for inclusion in discovery metadata in the frame of the WGISS Connected Data Assets Infrastructure. | Q4 2018 | QI Test case: Evaluate whether Sea Surface Temperature (SST) would provide a suitable test case for QI development that can act as an expressive case for QI access and implement this or an alternate case as determined through this activity. | WGCV and WGISS | Michael Morahan, Nigel Fox | System Level Team
WGCV-3: CEOS Data Cubes and CEOS Test Sites Data Access in support to WGCV Activities | Improved user access to the LPV supersite data sets and analytics tools | Q4 2018 | LPV supersite data access test case: LPV supersites are a good test case related to validation with a broad user community. Objective is to provide an improved user access to the LPV supersite data sets coupled with analytics tools to provide improved results for the users. | WGISS with the support of WGCV | Robert Woodcock, Greg Stensaas | System Level Team and Interoperability Interest Group
WGCV-4: Standardization and Best Practices | Update CEOS Best Practices | Q3 2018 | Revisit and update WGISS- 41/WGCV-40 actions: Define a point of contact within WGCV to work with WGISS to reinvigorate the actions of WGISS-41 in terms of more recent CEOS activities and move towards closure of these items to provide a good practice white paper for inclusion on the CEOS website. | WGISS with the support of WGCV | Iolanda Maggio, Greg Stensaas | Interoperability Interest Group

## Data Pres&Stewardship
Task Objective | Deliverables | Projected Completion Date | Background Information | WORKING GROUP (IG) | Responsible | Contributors | STATUS
WGISS-04: Drafting of Best Practices and guidelines | Updating of existing Best Practices, Guidelines and White papers and drafting of new ones. | Continuous Task | WGISS exploits knowledge of its participating agencies for the benefit of all CEOS and non-CEOS members by producing recommendations and guidelines concerned with all aspects of data and information management. | WGISS (DSIG) | DSIG Lead (Mirko Albani) | DSIG members
WGISS-05: Organize topic sessions during WGISS meetings on data stewardship to exchange information and lessons learned | Sessions presentations and related material | Continuous Task | Data Preservation and Stewardship sessions on topics of interest for CEOS agencies. | WGISS (DSIG) | DSIG Lead (Mirko Albani) | DSIG members

## Data Discovery and Access
Task Objective | Deliverables | Projected Completion Date | Background Information | WORKING GROUP (IG) | Responsible | Contributors | STATUS
WGISS-06: IDN Guide | Procedure and Guide Document | Q4 2018 | How-To Guides to register datasets in the IDN | WGISS (SLT) | Michael Morahan
WGISS-07: FedEO Guide | Procedure and Guide Document | Q4 2018 | Review and update FedEO How- To Guides for Data Partner and Client Partner | WGISS (SLT) | Andrea Della Vecchia
WGISS-08: CWIC Guide | Procedure and Guide Document | Q4 2018 | Review and update CWIC How-To Guides for Data Partner and Client Partner | WGISS (SLT) | Yonsook Enloe
WGISS-09: WGISS Connected Data Assets Guide | Procedure and Guide Document | Q4 2019 | Produce a How-to Guide for Client partners that describes how to connect and search for data in IDN, FedEO, and CWIC. | WGISS (SLT) | Yonsook Enloe, Andrea Della Vecchia, Michael Morahan | System Level Team
DATA-2: Full representation of CEOS Agency datasets in the IDN and accessibility via supported WGISS systems and standards | 1) Compared analysis of IDN registered datasets wrt CEOS agencies available datasets (e.g. through MIME or COVE tools comparison). 2) Periodic reports on WGISS Connected Data Assets registered and accessible datasets. | Q2 2019 | As the IDN contains OpenSearch endpoints for data access and is also the CEOS Data Collections access point for the GEOSS Platform (former Common Infrastructure, GCI) and GEO Portal, it is essential that all CEOS Agencies keep information on their data collections, including Analysis Ready Data, up-to-date in the IDN according to its metadata model (DIF-10). This requires interaction with CEOS agencies and data providers. | WGISS (SLT) and CEOS agencies / data providers | WGISS (SLT) and CEOS agencies / data providers | System Level Team and CEOS agencies for registration activities
DATA-8: Maintain and evolve WGISS Connected Data Assets Infrastructure and Systems for CEOS Agencies data and services discovery and access. | WGISS Connected Data Assets system description document and periodic reports describing the status. | Q4 2018 | Consolidation, operation, maintenance and evolution of current CWIC/FedEO/IDN overall Architecture | WGISS (SLT) | Yonsook Enloe | System Level Team | New Due Date suggested: Q4 2019
DATA-9: ECVs/CDRs Discovery and Access through WGISS Systems | 1) Compared analysis of IDN registered datasets ECVs/CDRs inventory. 2)Periodic Report on ECVs/CDRs registrations. | Q3 2018 | Facilitate discoverability and accessibility of ECV Products and space-born CDRs relevant for the CEOS Carbon Action via WGISS Connected Data Assets Systems & Standards (FedEO/CWIC/IDN, OpenSearch). | WGISS (SLT) supported by WGClimate | Michael Morahan | System Level Team | New Due Date suggested: Q4 2019
DATA-12: CEOS data holdings reported in GEO | Production of Periodic Reports on CEOS assets discoverable and accessible through the GEOSS Platform | Q3 2018 | Provide support to GEO in their efforts of reconciling metrics of CEOS data holdings provided through WGISS Connected Data Assets standards and systems. | WGISS (SLT) | Yonsook Enloe | System Level Team | New Due Date suggested: Q4 2019

## Interoperability & Use
Task Objective | Deliverables | Projected Completion Date | Background Information | WORKING GROUP (IG) | Responsible | Contributors | STATUS
FDA-5: Promote awareness of FDAs. | Material for FDA promotion | Q4 2018 (Interim reports) | With growing interest in Future Data Architectures, WGCapD will identify required CB material to support rollout of FDA technologies. Materials will range from basic introductions to information relevant to decision makers. | WGCapD supported by WGISS | Robert Woodcock, Richard Moreno
FDA-8: Establish a common description of Future Data Architecture functional blocks and identify interfaces and interoperability approaches. | FDA Functional Building Blocks description with interfaces. | Q3 2018 | Based on the outputs of the inventory and review of existing standards and approaches at CEOS agencies, on the pilot projects and using the various workshops (listed below) where FDA activities are discussed, FDA-AHT will establish a common understanding and develop a white paper describing the functional blocks and typical interoperability approaches for a generic FDA. | FDA AHT supported by WGISS | Mirko Albani, Steven Hosford | Robert Woodcock, Richard Moreno and Chris Lynnes. All Interest Groups when requested.
FDA-9: Inventory and characterise existing FDAs operated by both public and private entities including the standards and approaches they use (e.g. Data Cubes, Exploitation Platforms, Copernicus DIAS, etc). | FDAs inventory | Q3 2018 | As CEOS agencies are defining their processing and data dissemination standards, they seek to apply and follow international standards and best practices, including those generated by WGISS. This does not only concern common standards in terms of catalogs, metadata, terminology, and semantics, but it also involves interoperability standards for data discovery and download and for EO data analysis Application Programming Interfaces (APIs), as well as common interface standards such as INSPIRE, OGC, and W3C, and interoperability with other data access services (e.g., European Data Portal, international, GEOSS). WGISS will inventory and review existing standards and approaches in use by different FDA systems and platforms at CEOS agencies (e.g. Data Cubes, Exploitation Platforms, Copernicus DIAS, etc). | WGISS (IIG) | Mirko Albani, Steven Hosford | IIG members as needed | New Due Date suggested: Q1 2019
FDA-10: Finalise inventory of Software and Tools available or used at CEOS agencies for EO data exploitation and use focusing on Open Source but remaining as broad and inclusive as possible and implement a mechanism for discovery and access. | Inventory of SW and Tools | Q3 2018 | Each CEOS agency will continue to develop its data and computational infrastructures consistent with its capacity and user service mandates. CEOS has a role in identifying tools to support complementarity and interoperability across CEOS agencies in support of the FDA strategy objectives. WGISS will finalise the ongoing work of inventorying the software and tools available or used at CEOS agencies for EO data exploitation and use (e.g. EO data visualization, analysis, processing, readers/writers, etc), and implement a mechanism for discovery and access. Focus will be on Open Source but remaining as broad and inclusive as possible. | WGISS | Iolanda Maggio and Robert Woodcock | IIG members as needed | New Due Date suggested: Q1 2019
FDA-11: Organise several sessions/workshops to share lessons learned and outcomes from FDA systems and platform pilots and Interoperability Projects. | Workshop / Sessions for sharing of lessons learned and outcomes. Related material. | Throughout 2018 until Q4 | Several CEOS agencies have already carried out initial pilot projects and CEOS seeks to share the experience gained from these to ensure the discussions on the strategic dimensions of FDA are informed by practical evidence. Sessions (including but not limited to those detailed below) should focus on several issues ranging from technical to programmatic lessons learned will be shared and considered as input for the definition of technical FDA recommendations. | FDA AHT supported by WGISS | Mirko Albani, Robert Woodcock and Steven Hosford | IIG members as needed
FDA-13: Develop a User Metrics Best Practices. | User Metrics Best Practices | Q4 2018 | The proposed User Metrics initiative seeks to ensure planning and responsibilities are put in place for CEOS to leverage the experience being gained by individual agencies and to have an ongoing effort to collate available user metrics and to adapt the FDA strategy as these metrics are analysed beyond what is simply being downloaded. WGISS will perform a survey on existing user metrics in Earth Observation and other domains (e.g. social media) and develop a best practice for User Metrics recommended for application by CEOS agencies; these will include a user questionnaire to allow classifying the final user in terms of use of the data products and allowing generation of summary statistics on how EO data is being used and for what. | WGISS | Mirko Albani, Iolanda Maggio | Chris Lynnes, Richard Moreno, Katrin Molch, Steven Hosford. IIG members as needed.
DATA-14: Develop a White Paper on Single Sign-On (SSO) authentication. | SSO White Paper | Q4 2018 | Single sign-on (SSO) allows user login with a single ID and password to gain access to connected (federated) systems. This capability is crucial for interoperability between different FDA platforms and systems. WGISS will develop a white paper on single-sign-on (SSO) authentication best practices to support machine- to-machine authentication for EO analysis services. | WGISS (IIG) with support of ESA | Damiano Guerrucci Marco Leonardi | IIG members as needed | New Due Date suggested: Q1 2019
CARB-15: Carbon data Portal prototype | Deployment of a Carbon Data Portal Prototype | Q3 2018 | Implement a carbon data portal to facilitate the discoverability and accessibility of ECV products and space-borne CDRs. The portal is designed with a service-oriented architecture and follows the principles outlined by the GEOSS Community Portal white paper. The portal will seamlessly access data both in CWIC and FedEO to provide necessary data, tools and services to the carbon science community of both CEOS and GEOSS. The reference implementation can be shared with the broader CEOS carbon community. | WGISS (IIG) | Ken Casey and Ken McDonald |  | New Due Date suggested: Q1 2019

## Technology Exploration
Task Objective | Deliverables | Projected Completion Date | Background Information | WORKING GROUP (IG) | Responsible | Contributors | STATUS
DATA-11: Data and Technology Exploration webinars and workshops | Technical Webinars | Q4 2019 | WGISS will host at least one workshop annually to serve as a forum for exchange of technical information and lessons-learned experience about current, trending and future data management approaches and technologies, services and other Internet-related technologies. | WGISS (Technology Exploration Interest Group) | Chris Lynnes | Experts team