## Slide 1: Data Stewardship Session Summary of Actions
Mirko Albani (ESA)
WGISS-48
Hosted by VAST/VNSC, Ha Noi, Vietnam
8-11 October 2019
Committee on Earth Observation Satellites
WGISS

## Slide 2
Actions from previous meetings
Number | Description | Actionees | Due Date | Status | Comments
WGISS-47-26a | Iolanda to liaise with Ge Peng to find out when the WMO documents on stewardship are approved by October 31, 2019 | Iolanda Maggio | 31-Oct-19 | In progress | September 18: ongoing
WGISS-47-26b | Iolanda to liaise with WGCV to collect comments on WGISS and WMO maturity matrices (once the WMO documents are approved) by December 31, 2019 | Iolanda Maggio | 31-Dec-19 |  | September 18: first meeting held with ESA quality team; dedicated presentation at WGISS#48 meeting
WGISS-47-27 | Iolanda to define way forward for finalization of WGISS Maturity Matrix using WMO matrix and RDA-FAIR WG results; finalise input for DMP by June 30, 2019 | Iolanda Maggio | 30-Jun-19 | In progress | July 17: The proposal has been finalized and it will be presented at WGISS-48.

## Slide 3
New Actions from WGISS#48
Number | Description | Actionees | Due Date | Status | Comments
WGISS-48-29 |  |  | 31-Dec-19 | To be started |