## Sheet1
WGISS-54-01 | Makoto Natsuisaka and WGISS Exec to begin drafting a list of CEOS Workplan deliverables for the period 2023-2025. Due January/February 2023.
WGISS-54-02 | WGISS Exec to request from the SEO a copy of the charter that describes the goals and objectives of cloud prototyping efforts. If a charter does not exist, create a follow-up action to work with SEO to charter the efforts so that CEOS has defined goals and objectives.
WGISS-54-03 | Iolanda Maggio and Mirko Albani to participate in the discussion with GEO on 24th of October regarding the self-assessment tool in the GEO Knowledge Hub, to share experiences based on the WGISS Data Management and Stewardship Maturity Matrix which is based on the GEO Data Management Principles.
WGISS-54-04 | Data Stewardship Interest Group to issue a plan for data stewardship best practices refreshment with priorities and schedule. Due by October 2022
WGISS-54-05 | WGISS Exec to review prior browse data best practices and guidelines, and consider updating to reflect newer cloud capabilities.
WGISS-54-06 | Mirko Albani to organize a session at WGISS-55 on AVHRR data recovery including dedicated presentations on European and North America LAC Archives and progress on other worldwide archives. Due by WGISS-55.
WGISS-54-07 | Mirko Albani to contact CGMS rapporteur (Simon Elliott, EUMETSAT) to understand if/how a join session with WGISS could be organized. (Note: CGMS WG-IV will have dedicated meetings in January 2023 and March 2023; CGMS chair is Kotaro Bessho, kbessho@met.kishou.go.jp). Due by October 2022.
WGISS-54-08 | Data Stewardship Interest Group to evaluate potential extension/application of existing WGISS data preservation guidelines to ground-based (in-situ) data. Due by WGISS-55.
WGISS-54-09 | WGISS Exec to define a use case that clarifies the challenges of authenticating data replicas in the cloud, including related goals, options, and technologies. Due by WGISS-55.
WGISS-54-10 | Mirko Albani to organize a dedicated presentation at WGISS-55 on Copernicus Sentinels Ground segment architecture and authenticity and provenance approaches, inviting outside participants. Due by WGISS-55
WGISS-54-11 | WGISS Exec to study an approach to define and obtain useful and valid metrics of agency data use and access in the Cloud that quantify measures of success. Due by WGISS-55.
WGISS-54-12 | Makoto Natsuisaka to share CEOS Interoperability Framework to WGISS, and call for participants.
WGISS-54-13 | Technology Exploration Interest Group to add the production and publication of the AI/ML White Paper to the CEOS Work Plan. Due by WGISS-57 (April 2024)
WGISS-54-14 | Technology Exploration Interest Group to develop in-depth presentations at WGISS-55 on federation, including a call for proposals for federation. Due WGISS-55
WGISS-54-15 | Data Stewardship Interest Group to send the latest version of the Maturity Matrix to WGCV for review and fine tuning in order to finalize the White Paper that could be presented as a 2023 deliverable to CEOS.
WGISS-54-16 | Michelle Piepgrass to add the information on WGISS-55 and WGISS-56 to the CEOS calendar and the WGISS website. Due October 31, 2022.
WGISS-54-17 | Michelle Piepgrass to circulate the WGISS-All and WGISS-Internal email lists for review and update by November 30, 2022.