## Slide 1: WGISS-55 Meeting Summary

## Slide 2: Action Item Review Day 1
General
  Action: Michelle to find out number of downloads from CEOS website: BPs, WPs, presentations and provide the results to WGISS Exec.
CEOS Interoperability Framework
  Action: Each factor Lead to finalize the factor name, coordinator (lead), collaborator(s), description (1-2 paragraphs), scope (included and excluded).
  Action: Doug Newman to brief the CEOS Interoperability Framework Team on STAC.
  Action: WGISS to work with Thomas Huang to consider the digital twins as a use case in the Interoperability Framework.
Technology Exploration
  Action: Esther and team to schedule two Jupyter Notebooks workshops (July/September): one on access metadata, and one on technical dependencies.

## Slide 3: Action Item Review Day 2
Data Discovery and Access
  Action: DSIG/SLT to confirm that content of the Open Source Software page (http://ec2-3-208-162-171.compute-1.amazonaws.com/ossi/browse) has been correctly ingested in the FedEO operational system accessible to end users.
  Action: DSIG to ask SEO to remove the Open Source Software page (http://ec2-3-208-162-171.compute-1.amazonaws.com/ossi/browse) from the CEOS website, upon completion of previous action.
  Action: SLT to define a procedure for registration of services/tools into IDN/FedEO (direct registration by users or through circulation of Open Source Software spreadsheet). SLT to inform WGISS-All on how to register their services and tools.
  Action: SLT to examine the emerging needs and possible solutions for user authentication and authorisation in the new scenario for data access. Provide a status report at WGISS-56.

## Slide 4: Action Item Review Day 3
Data Preservation and Stewardship
  Action: DSIG to prepare the white paper on in-situ data based on the study conducted, and submit to WGCV for review. Review the content by end of May circulate by end of June if no updates needed.
  Action: DSIG to prepare the white paper on software preservation based on the study conducted. Review the content by end of May circulate by end of June if no updates needed.
  Action: DSIG to circulate the package of updated documents and best practices by end of April, and publish by end of May if no comments received.
  Action: DSIG to go through the list of White Papers and Reports (above), and clearly state the issue date and suggested retirement date, as well as what is the type of paper (WP, technical note, BP). Submit the list to the VC leads for their consideration.

## Slide 5: Action Item Review Day 3
Data Preservation and Stewardship, continued
  Action: Makoto to ask the SEO and CEO to provide a method of governance on the process for “publication” of CEOS documents (White Papers, Best Practices, Technical Documents). Is there a process also for documents that are deliverables from the Work Plan.
  Action: DSIG to organize a session on AVHRR at WGISS-56.

## Slide 6: Summary of Meeting
Meeting Lessons Learned (around the room…)
  What did you find most valuable from WGISS-55?
  What could be improved in future meetings?