## Slide 1: Status about white paper for AI/ML
Yousuke Ikehata, JAXA
Agenda ID: 2024.3.5_13.45
WGISS-57
5th March 2024

## Slide 2: Progress
We can fill out sections for initiatives and programs by NOAA and ISRO.
  NASA also check their section by discussion by last WGISS-56.
  ISRO provides their white paper and they will introduce it in next presentation.
We invite new colleagues as contributor.
  NRCan: De Jong
  AIRCAS: Xuesong Li
  ESA:Filippo
  INPE: Lubia
They will add/write their work till next WGISS.

## Slide 3: Schedule updated
Share/Check Outline
In-house work
Allocate author to excels part.
Report in monthly meeting
Reorganize
Show draft
Publish
In-house work
Discussion
fulfill each section
Refinement
WGISS-54
WGISS-56
WGISS-57
12 month
6 month
WGISS-58
6 month